## Start Here
OPERATIONS & PROJECT DELIVERY ANALYSIS
Portfolio Project ¦ Excel Operations & Project Management Analytics
Scenario | A growing organization manages a portfolio of 30 cross-functional projects spanning Operations, Technology, Finance, Human Resources, Marketing, Procurement, and Facilities. Leadership needs a clear view of portfolio health, schedule performance, workload, budget variance, and operational risk.
Business Questions | 1. How many projects are completed, active, delayed, or at risk? 2. Which departments and projects are over or under budget? 3. Which projects and departments experience the largest schedule delays? 4. How is active workload distributed across project managers? 5. Where are high-risk tasks concentrated? 6. Which functions demonstrate the strongest schedule and budget performance?
Analysis Approach | Analyzed 750 task-level records using Excel PivotTables, calculated fields, formulas, project-level status logic, aggregations, and comparative analysis. Findings were consolidated into an executive dashboard designed to surface portfolio health, workload, risk, and schedule performance.
Deliverable | Interactive Excel workbook containing an executive portfolio dashboard, project health analysis, project manager workload analysis, department-level risk and budget analysis, schedule performance analysis, and supporting PivotTables.
Skills Demonstrated | Microsoft Excel • PivotTables • Data Analysis • Dashboard Design • KPI Development • Data Visualization • Conditional Logic • Budget Variance Analysis • Schedule Analysis • Risk Analysis • Project Portfolio Reporting • Executive Communication

## Executive Dashboard
OPERATIONS PROJECT PORTFOLIO DASHBOARD
|  |  |  | Project Status | Count | Department | High-Risk Tasks
REPORTING DATE: AUGUST 11, 2026 |  |  |  | Completed | 8 | Facilities | 19
|  |  |  | Delayed | 22 | Finance | 18
30 | 22 | 8 | 294 |  |  | Human Resources | 16
[6 empty] | Marketing | 14
Total Projects | Active Projects | Completed Projects | Unfinished Tasks | Avery Brooks | 43 | Operations | 14
|  |  |  | Cameron Diaz | 56 | Procurement | 17
|  |  |  | Jordan Lee | 36 | Technology | 24
|  |  |  | Morgan Patel | 57
|  |  |  | Riley Chen | 44
|  |  |  | Taylor Reed | 58
[6 empty] | Department | Cumulative Delay Days
[6 empty] | Facilities | 255
[6 empty] | Finance | 237
[6 empty] | Human Resources | 129
[6 empty] | Marketing | 158
[6 empty] | Operations | 239
[6 empty] | Procurement | 189
[6 empty] | Technology | 318
Key Insights
Portfolio Health: 22 of 30 projects remain active beyond their planned finish dates, while 8 projects are completed. Workload: Taylor Reed carries the largest unfinished workload with 58 tasks, closely followed by Morgan Patel (57) and Cameron Diaz (56). Risk: Technology has the highest concentration of high-risk work at 19.2% (24 of 125 tasks), followed closely by Facilities at 19.0%. Performance: Human Resources has the strongest schedule/budget balance with the lowest cumulative delay (129 days) while maintaining approximately $453K in favorable budget variance. Technology has the greatest schedule pressure at 318 cumulative delay days.

## Project Health
Project Name | Planned Finish | Completed Tasks | Total Tasks | On Hold Tasks | Project Status | Analysis Date | Target Status | Project Manager | Project Manager | Active Projects
Operations Facility Upgrade 01 | 2026-05-13 | 25 | 25 | 0 | Completed | 2026-08-11 | Completed | Avery Brooks | Avery Brooks | 3
Technology Compliance 02 | 2025-08-18 | 25 | 25 | 0 | Completed |  | Completed | Jordan Lee | Cameron Diaz | 4
Finance Vendor Transition 03 | 2025-06-29 | 25 | 25 | 0 | Completed |  | Completed | Morgan Patel | Jordan Lee | 3
Human Resources System Implementation 04 | 2026-07-04 | 25 | 25 | 0 | Completed |  | Completed | Taylor Reed | Morgan Patel | 4
Facilities Cost Reduction 05 | 2025-11-06 | 25 | 25 | 0 | Completed |  | Completed | Cameron Diaz | Riley Chen | 4
Marketing Automation 06 | 2025-10-19 | 25 | 25 | 0 | Completed |  | Completed | Riley Chen | Taylor Reed | 4
Procurement Process Improvement 07 | 2025-10-07 | 25 | 25 | 0 | Completed |  | Completed | Avery Brooks
Operations Facility Upgrade 08 | 2025-08-12 | 25 | 25 | 0 | Completed |  | Completed | Jordan Lee
Technology Compliance 09 | 2026-07-07 | 11 | 25 | 0 | Delayed |  | On Track | Morgan Patel
Finance Vendor Transition 10 | 2025-07-30 | 11 | 25 | 2 | Delayed |  | On Track | Taylor Reed
Human Resources System Implementation 11 | 2026-06-01 | 8 | 25 | 2 | Delayed |  | On Track | Cameron Diaz
Facilities Cost Reduction 12 | 2026-07-14 | 15 | 25 | 0 | Delayed |  | On Track | Riley Chen
Marketing Automation 13 | 2026-03-20 | 9 | 25 | 2 | Delayed |  | On Track | Avery Brooks
Procurement Process Improvement 14 | 2025-08-04 | 11 | 25 | 1 | Delayed |  | On Track | Jordan Lee
Operations Facility Upgrade 15 | 2026-04-27 | 11 | 25 | 0 | Delayed |  | On Track | Morgan Patel
Technology Compliance 16 | 2026-01-14 | 8 | 25 | 1 | Delayed |  | On Track | Taylor Reed
Finance Vendor Transition 17 | 2025-07-11 | 13 | 25 | 1 | Delayed |  | On Track | Cameron Diaz
Human Resources System Implementation 18 | 2025-06-26 | 13 | 25 | 2 | Delayed |  | At Risk | Riley Chen
Facilities Cost Reduction 19 | 2025-07-29 | 11 | 25 | 1 | Delayed |  | At Risk | Avery Brooks
Marketing Automation 20 | 2025-10-05 | 11 | 25 | 3 | Delayed |  | At Risk | Jordan Lee
Procurement Process Improvement 21 | 2025-10-16 | 9 | 25 | 0 | Delayed |  | At Risk | Morgan Patel
Operations Facility Upgrade 22 | 2026-03-13 | 10 | 25 | 1 | Delayed |  | At Risk | Taylor Reed
Technology Compliance 23 | 2026-05-01 | 10 | 25 | 1 | Delayed |  | At Risk | Cameron Diaz
Finance Vendor Transition 24 | 2025-06-17 | 14 | 25 | 1 | Delayed |  | Delayed | Riley Chen
Human Resources System Implementation 25 | 2026-04-08 | 12 | 25 | 3 | Delayed |  | Delayed | Avery Brooks
Facilities Cost Reduction 26 | 2025-09-26 | 17 | 25 | 1 | Delayed |  | Delayed | Jordan Lee
Marketing Automation 27 | 2026-06-10 | 12 | 25 | 1 | Delayed |  | Delayed | Morgan Patel
Procurement Process Improvement 28 | 2026-05-25 | 13 | 25 | 3 | Delayed |  | Delayed | Taylor Reed
Operations Facility Upgrade 29 | 2026-06-01 | 13 | 25 | 0 | Delayed |  | Delayed | Cameron Diaz
Technology Compliance 30 | 2026-03-31 | 14 | 25 | 2 | Delayed |  | Delayed | Riley Chen
Formulas:
Planned Finish = MAXIFS('Raw Project Data'!$M:$M,'Raw Project Data'!$C:$C,[Project Name])

## Raw Project Data
Task ID | Project ID | Project Name | Department | Project Type | Project Manager | Workstream | Task Name | Priority | Risk Level | Vendor | Planned Start | Planned Finish | Actual Finish | Status | Percent Complete | Planned Budget | Actual Cost | Issue Count | Days Delayed | Unique Project Flag | Budget Variance
TSK-0001 | PRJ-1001 | Operations Facility Upgrade 01 | Operations | Facility Upgrade | Avery Brooks | Planning | Planning Task 01 | Medium | Low | Internal Team | 2025-11-30 | 2025-12-27 | 2025-12-27 | Completed | 100% | 8300 | 7677.14 | 2 | 0 | 1 | 622.86
TSK-0002 | PRJ-1002 | Technology Compliance 02 | Technology | Compliance | Jordan Lee | Requirements | Requirements Task 01 | Low | Low | Summit Partners | 2025-05-10 | 2025-06-07 |  | Completed | 0% | 21500 | 0 | 3 |  | 1 | 21500
TSK-0003 | PRJ-1003 | Finance Vendor Transition 03 | Finance | Vendor Transition | Morgan Patel | Configuration | Configuration Task 01 | Low | Low | Northstar Consulting | 2025-04-20 | 2025-05-11 |  | Completed | 25% | 3500 | 4184.71 | 1 |  | 1 | -684.71
TSK-0004 | PRJ-1004 | Human Resources System Implementation 04 | Human Resources | System Implementation | Taylor Reed | Execution | Execution Task 01 | Low | Low | Internal Team | 2026-04-01 | 2026-04-18 | 2026-04-26 | Completed | 100% | 17400 | 16848.48 | 2 | 8 | 1 | 551.52
TSK-0005 | PRJ-1005 | Facilities Cost Reduction 05 | Facilities | Cost Reduction | Cameron Diaz | Testing | Testing Task 01 | Medium | High | Northstar Consulting | 2025-07-08 | 2025-07-28 | 2025-08-03 | Completed | 100% | 44500 | 51706.33 | 2 | 6 | 1 | -7206.33
TSK-0006 | PRJ-1006 | Marketing Automation 06 | Marketing | Automation | Riley Chen | Training | Training Task 01 | High | Medium | Vertex Systems | 2025-07-08 | 2025-08-06 |  | Completed | 0% | 15200 | 0 | 2 |  | 1 | 15200
TSK-0007 | PRJ-1007 | Procurement Process Improvement 07 | Procurement | Process Improvement | Avery Brooks | Launch | Launch Task 01 | Critical | High | Internal Team | 2025-09-04 | 2025-09-19 | 2025-09-26 | Completed | 100% | 29500 | 32674.49 | 4 | 7 | 1 | -3174.49
TSK-0008 | PRJ-1008 | Operations Facility Upgrade 08 | Operations | Facility Upgrade | Jordan Lee | Closeout | Closeout Task 01 | High | Medium | Vertex Systems | 2025-07-05 | 2025-07-26 |  | Completed | 40% | 44900 | 49516.48 | 3 |  | 1 | -4616.48
TSK-0009 | PRJ-1009 | Technology Compliance 09 | Technology | Compliance | Morgan Patel | Discovery | Discovery Task 01 | High | High | Internal Team | 2026-02-27 | 2026-03-27 | 2026-03-23 | Completed | 100% | 27400 | 27626.5 | 2 | 0 | 1 | -226.5
TSK-0010 | PRJ-1010 | Finance Vendor Transition 10 | Finance | Vendor Transition | Taylor Reed | Planning | Planning Task 01 | Medium | High | Vertex Systems | 2025-03-28 | 2025-04-21 | 2025-04-24 | Completed | 100% | 34200 | 36993.98 | 2 | 3 | 1 | -2793.98
TSK-0011 | PRJ-1011 | Human Resources System Implementation 11 | Human Resources | System Implementation | Cameron Diaz | Requirements | Requirements Task 01 | Medium | Low | Internal Team | 2026-02-23 | 2026-03-14 | 2026-03-13 | Completed | 100% | 28700 | 29201.75 | 2 | 0 | 1 | -501.75
TSK-0012 | PRJ-1012 | Facilities Cost Reduction 12 | Facilities | Cost Reduction | Riley Chen | Configuration | Configuration Task 01 | Medium | Low | Internal Team | 2026-06-04 | 2026-06-07 | 2026-06-02 | Completed | 100% | 22800 | 25073.28 | 2 | 0 | 1 | -2273.28
TSK-0013 | PRJ-1013 | Marketing Automation 13 | Marketing | Automation | Avery Brooks | Execution | Execution Task 01 | Critical | Medium | Internal Team | 2025-12-12 | 2026-01-02 |  | On Hold | 10% | 33300 | 38044.54 | 0 |  | 1 | -4744.54
TSK-0014 | PRJ-1014 | Procurement Process Improvement 14 | Procurement | Process Improvement | Jordan Lee | Testing | Testing Task 01 | Medium | Low | Northstar Consulting | 2025-07-09 | 2025-07-17 |  | In Progress | 90% | 27900 | 35339 | 1 |  | 1 | -7439
TSK-0015 | PRJ-1015 | Operations Facility Upgrade 15 | Operations | Facility Upgrade | Morgan Patel | Training | Training Task 01 | High | Medium | Vertex Systems | 2026-02-14 | 2026-03-10 | 2026-03-04 | Completed | 100% | 6800 | 7278.47 | 2 | 0 | 1 | -478.47
TSK-0016 | PRJ-1016 | Technology Compliance 16 | Technology | Compliance | Taylor Reed | Launch | Launch Task 01 | High | Low | Internal Team | 2025-08-28 | 2025-09-22 | 2025-09-30 | Completed | 100% | 11500 | 13807.05 | 0 | 8 | 1 | -2307.05
TSK-0017 | PRJ-1017 | Finance Vendor Transition 17 | Finance | Vendor Transition | Cameron Diaz | Closeout | Closeout Task 01 | Low | Low | Northstar Consulting | 2025-03-17 | 2025-04-06 |  | Not Started | 0% | 42200 | 0 | 1 |  | 1 | 42200
TSK-0018 | PRJ-1018 | Human Resources System Implementation 18 | Human Resources | System Implementation | Riley Chen | Discovery | Discovery Task 01 | High | Medium | Internal Team | 2025-02-14 | 2025-03-10 |  | In Progress | 60% | 19400 | 20255.08 | 1 |  | 1 | -855.08
TSK-0019 | PRJ-1019 | Facilities Cost Reduction 19 | Facilities | Cost Reduction | Avery Brooks | Planning | Planning Task 01 | High | Medium | Internal Team | 2025-05-19 | 2025-06-16 | 2025-06-18 | Completed | 100% | 21000 | 22920.48 | 1 | 2 | 1 | -1920.48
TSK-0020 | PRJ-1020 | Marketing Automation 20 | Marketing | Automation | Jordan Lee | Requirements | Requirements Task 01 | Medium | High | Internal Team | 2025-09-14 | 2025-09-20 |  | Not Started | 0% | 45000 | 0 | 5 |  | 1 | 45000
TSK-0021 | PRJ-1021 | Procurement Process Improvement 21 | Procurement | Process Improvement | Morgan Patel | Configuration | Configuration Task 01 | Critical | Medium | Internal Team | 2025-09-06 | 2025-09-24 |  | In Progress | 60% | 40800 | 31473.08 | 2 |  | 1 | 9326.92
TSK-0022 | PRJ-1022 | Operations Facility Upgrade 22 | Operations | Facility Upgrade | Taylor Reed | Execution | Execution Task 01 | Medium | High | Vertex Systems | 2025-12-03 | 2025-12-19 | 2025-12-21 | Completed | 100% | 33300 | 36753.47 | 1 | 2 | 1 | -3453.47
TSK-0023 | PRJ-1023 | Technology Compliance 23 | Technology | Compliance | Cameron Diaz | Testing | Testing Task 01 | Medium | Low | Internal Team | 2025-11-24 | 2025-12-15 | 2025-12-23 | Completed | 100% | 3700 | 3905.95 | 0 | 8 | 1 | -205.95
TSK-0024 | PRJ-1024 | Finance Vendor Transition 24 | Finance | Vendor Transition | Riley Chen | Training | Training Task 01 | Medium | Low | Apex Solutions | 2025-03-07 | 2025-03-12 | 2025-03-16 | Completed | 100% | 30900 | 31677.47 | 2 | 4 | 1 | -777.47
TSK-0025 | PRJ-1025 | Human Resources System Implementation 25 | Human Resources | System Implementation | Avery Brooks | Launch | Launch Task 01 | High | Low | Northstar Consulting | 2025-11-09 | 2025-11-25 | 2025-11-21 | Completed | 100% | 12800 | 12566.69 | 1 | 0 | 1 | 233.31
TSK-0026 | PRJ-1026 | Facilities Cost Reduction 26 | Facilities | Cost Reduction | Jordan Lee | Closeout | Closeout Task 01 | Medium | Low | Northstar Consulting | 2025-08-12 | 2025-08-25 | 2025-08-22 | Completed | 100% | 42200 | 49500.61 | 1 | 0 | 1 | -7300.61
TSK-0027 | PRJ-1027 | Marketing Automation 27 | Marketing | Automation | Morgan Patel | Discovery | Discovery Task 01 | Medium | Low | Apex Solutions | 2026-05-16 | 2026-05-27 |  | Not Started | 0% | 16700 | 0 | 2 |  | 1 | 16700
TSK-0028 | PRJ-1028 | Procurement Process Improvement 28 | Procurement | Process Improvement | Taylor Reed | Planning | Planning Task 01 | Medium | Low | Apex Solutions | 2026-02-19 | 2026-03-13 |  | On Hold | 65% | 1800 | 1904.35 | 0 |  | 1 | -104.35
TSK-0029 | PRJ-1029 | Operations Facility Upgrade 29 | Operations | Facility Upgrade | Cameron Diaz | Requirements | Requirements Task 01 | High | High | Internal Team | 2026-01-29 | 2026-02-04 | 2026-02-09 | Completed | 100% | 10700 | 12242.5 | 2 | 5 | 1 | -1542.5
TSK-0030 | PRJ-1030 | Technology Compliance 30 | Technology | Compliance | Riley Chen | Execution | Execution Task 01 | High | Low | Internal Team | 2025-10-25 | 2025-10-30 | 2025-11-10 | Completed | 100% | 37600 | 41936.03 | 2 | 11 | 1 | -4336.03
TSK-0031 | PRJ-1001 | Operations Facility Upgrade 01 | Operations | Facility Upgrade | Avery Brooks | Testing | Testing Task 02 | Medium | High | Internal Team | 2026-03-22 | 2026-04-11 | 2026-04-10 | Completed | 100% | 42600 | 44729.63 | 3 | 0 | 0 | -2129.63
TSK-0032 | PRJ-1002 | Technology Compliance 02 | Technology | Compliance | Jordan Lee | Training | Training Task 02 | Low | Low | Apex Solutions | 2025-06-22 | 2025-06-29 |  | Completed | 0% | 17400 | 0 | 4 |  | 0 | 17400
TSK-0033 | PRJ-1003 | Finance Vendor Transition 03 | Finance | Vendor Transition | Morgan Patel | Launch | Launch Task 02 | Low | Low | Vertex Systems | 2025-02-13 | 2025-02-27 | 2025-02-21 | Completed | 100% | 40000 | 35703.39 | 2 | 0 | 0 | 4296.61
TSK-0034 | PRJ-1004 | Human Resources System Implementation 04 | Human Resources | System Implementation | Taylor Reed | Closeout | Closeout Task 02 | Medium | High | Summit Partners | 2026-03-06 | 2026-03-22 |  | Completed | 0% | 33500 | 0 | 6 |  | 0 | 33500
TSK-0035 | PRJ-1005 | Facilities Cost Reduction 05 | Facilities | Cost Reduction | Cameron Diaz | Discovery | Discovery Task 02 | High | High | Summit Partners | 2025-08-02 | 2025-08-10 | 2025-08-23 | Completed | 100% | 38800 | 46953.87 | 3 | 13 | 0 | -8153.87
TSK-0036 | PRJ-1006 | Marketing Automation 06 | Marketing | Automation | Riley Chen | Planning | Planning Task 02 | Medium | Low | Summit Partners | 2025-07-08 | 2025-07-18 |  | Completed | 0% | 9900 | 0 | 0 |  | 0 | 9900
TSK-0037 | PRJ-1007 | Procurement Process Improvement 07 | Procurement | Process Improvement | Avery Brooks | Requirements | Requirements Task 02 | Critical | Low | Northstar Consulting | 2025-08-10 | 2025-09-03 |  | Completed | 65% | 15900 | 19299.77 | 4 |  | 0 | -3399.77
TSK-0038 | PRJ-1008 | Operations Facility Upgrade 08 | Operations | Facility Upgrade | Jordan Lee | Configuration | Configuration Task 02 | Medium | Medium | BluePeak Services | 2025-03-27 | 2025-04-02 | 2025-04-06 | Completed | 100% | 16500 | 17271 | 0 | 4 | 0 | -771
TSK-0039 | PRJ-1009 | Technology Compliance 09 | Technology | Compliance | Morgan Patel | Execution | Execution Task 02 | Critical | Low | BluePeak Services | 2026-03-07 | 2026-03-18 |  | Not Started | 0% | 20500 | 0 | 1 |  | 0 | 20500
TSK-0040 | PRJ-1010 | Finance Vendor Transition 10 | Finance | Vendor Transition | Taylor Reed | Testing | Testing Task 02 | High | High | Vertex Systems | 2025-04-18 | 2025-05-02 |  | In Progress | 85% | 41600 | 39682.08 | 2 |  | 0 | 1917.92
TSK-0041 | PRJ-1011 | Human Resources System Implementation 11 | Human Resources | System Implementation | Cameron Diaz | Training | Training Task 02 | Medium | High | Apex Solutions | 2026-04-01 | 2026-04-14 |  | In Progress | 50% | 25600 | 28880.11 | 5 |  | 0 | -3280.11
TSK-0042 | PRJ-1012 | Facilities Cost Reduction 12 | Facilities | Cost Reduction | Riley Chen | Launch | Launch Task 02 | Medium | Medium | Internal Team | 2026-06-14 | 2026-06-26 |  | In Progress | 90% | 1500 | 1489.79 | 3 |  | 0 | 10.21
TSK-0043 | PRJ-1013 | Marketing Automation 13 | Marketing | Automation | Avery Brooks | Closeout | Closeout Task 02 | High | Medium | Apex Solutions | 2026-02-02 | 2026-02-26 |  | In Progress | 60% | 36000 | 42977.86 | 1 |  | 0 | -6977.86
TSK-0044 | PRJ-1014 | Procurement Process Improvement 14 | Procurement | Process Improvement | Jordan Lee | Discovery | Discovery Task 02 | High | Low | Northstar Consulting | 2025-05-15 | 2025-05-20 | 2025-05-22 | Completed | 100% | 11300 | 9668.05 | 1 | 2 | 0 | 1631.95
TSK-0045 | PRJ-1015 | Operations Facility Upgrade 15 | Operations | Facility Upgrade | Morgan Patel | Planning | Planning Task 02 | Medium | Low | Summit Partners | 2025-11-22 | 2025-12-09 |  | In Progress | 85% | 26500 | 27645.43 | 1 |  | 0 | -1145.43
TSK-0046 | PRJ-1016 | Technology Compliance 16 | Technology | Compliance | Taylor Reed | Requirements | Requirements Task 02 | Medium | Low | Vertex Systems | 2025-09-06 | 2025-10-03 |  | In Progress | 40% | 36500 | 33355.74 | 1 |  | 0 | 3144.26
TSK-0047 | PRJ-1017 | Finance Vendor Transition 17 | Finance | Vendor Transition | Cameron Diaz | Configuration | Configuration Task 02 | Medium | High | Internal Team | 2025-02-25 | 2025-03-25 | 2025-03-20 | Completed | 100% | 24600 | 24117.91 | 3 | 0 | 0 | 482.09
TSK-0048 | PRJ-1018 | Human Resources System Implementation 18 | Human Resources | System Implementation | Riley Chen | Execution | Execution Task 02 | High | Low | Summit Partners | 2025-05-30 | 2025-06-15 | 2025-06-03 | Completed | 100% | 33800 | 32126.3 | 0 | 0 | 0 | 1673.7
TSK-0049 | PRJ-1019 | Facilities Cost Reduction 19 | Facilities | Cost Reduction | Avery Brooks | Testing | Testing Task 02 | Medium | Medium | Vertex Systems | 2025-07-05 | 2025-07-23 | 2025-07-26 | Completed | 100% | 13400 | 14736.71 | 2 | 3 | 0 | -1336.71
TSK-0050 | PRJ-1020 | Marketing Automation 20 | Marketing | Automation | Jordan Lee | Training | Training Task 02 | Medium | Low | Apex Solutions | 2025-06-01 | 2025-06-08 |  | In Progress | 85% | 8100 | 8469.14 | 3 |  | 0 | -369.14
TSK-0051 | PRJ-1021 | Procurement Process Improvement 21 | Procurement | Process Improvement | Morgan Patel | Launch | Launch Task 02 | Medium | Low | Internal Team | 2025-08-20 | 2025-09-04 | 2025-08-28 | Completed | 100% | 38800 | 36258.3 | 1 | 0 | 0 | 2541.7
TSK-0052 | PRJ-1022 | Operations Facility Upgrade 22 | Operations | Facility Upgrade | Taylor Reed | Closeout | Closeout Task 02 | Low | Low | Vertex Systems | 2026-01-06 | 2026-01-26 | 2026-01-21 | Completed | 100% | 25300 | 24240.58 | 1 | 0 | 0 | 1059.42
TSK-0053 | PRJ-1023 | Technology Compliance 23 | Technology | Compliance | Cameron Diaz | Discovery | Discovery Task 02 | Medium | Low | Internal Team | 2026-02-04 | 2026-02-28 | 2026-02-27 | Completed | 100% | 21800 | 23050.68 | 2 | 0 | 0 | -1250.68
TSK-0054 | PRJ-1024 | Finance Vendor Transition 24 | Finance | Vendor Transition | Riley Chen | Planning | Planning Task 02 | Low | Low | Apex Solutions | 2025-01-25 | 2025-01-30 | 2025-02-08 | Completed | 100% | 7400 | 7294.06 | 1 | 9 | 0 | 105.94
TSK-0055 | PRJ-1025 | Human Resources System Implementation 25 | Human Resources | System Implementation | Avery Brooks | Requirements | Requirements Task 02 | Medium | Low | Internal Team | 2026-01-25 | 2026-02-05 | 2026-02-10 | Completed | 100% | 5100 | 4829.66 | 3 | 5 | 0 | 270.34
TSK-0056 | PRJ-1026 | Facilities Cost Reduction 26 | Facilities | Cost Reduction | Jordan Lee | Configuration | Configuration Task 02 | Critical | Low | Northstar Consulting | 2025-04-27 | 2025-05-24 |  | Not Started | 0% | 12300 | 0 | 2 |  | 0 | 12300
TSK-0057 | PRJ-1027 | Marketing Automation 27 | Marketing | Automation | Morgan Patel | Execution | Execution Task 02 | Medium | Low | Internal Team | 2026-03-03 | 2026-03-20 | 2026-03-14 | Completed | 100% | 34900 | 38190.16 | 3 | 0 | 0 | -3290.16
TSK-0058 | PRJ-1028 | Procurement Process Improvement 28 | Procurement | Process Improvement | Taylor Reed | Testing | Testing Task 02 | High | Low | Summit Partners | 2026-02-21 | 2026-02-27 | 2026-03-09 | Completed | 100% | 41000 | 39267.89 | 0 | 10 | 0 | 1732.11
TSK-0059 | PRJ-1029 | Operations Facility Upgrade 29 | Operations | Facility Upgrade | Cameron Diaz | Training | Training Task 02 | Medium | Medium | Summit Partners | 2026-03-03 | 2026-03-09 | 2026-03-23 | Completed | 100% | 14600 | 13725.35 | 0 | 14 | 0 | 874.65
TSK-0060 | PRJ-1030 | Technology Compliance 30 | Technology | Compliance | Riley Chen | Closeout | Closeout Task 02 | High | Medium | Internal Team | 2026-02-25 | 2026-03-13 | 2026-03-24 | Completed | 100% | 2100 | 2282.06 | 0 | 11 | 0 | -182.06
TSK-0061 | PRJ-1001 | Operations Facility Upgrade 01 | Operations | Facility Upgrade | Avery Brooks | Discovery | Discovery Task 03 | Medium | Low | BluePeak Services | 2026-03-26 | 2026-04-20 |  | Completed | 0% | 9200 | 0 | 0 |  | 0 | 9200
TSK-0062 | PRJ-1002 | Technology Compliance 02 | Technology | Compliance | Jordan Lee | Planning | Planning Task 03 | High | High | Vertex Systems | 2025-07-01 | 2025-07-17 | 2025-07-18 | Completed | 100% | 27300 | 28221.85 | 4 | 1 | 0 | -921.85
TSK-0063 | PRJ-1003 | Finance Vendor Transition 03 | Finance | Vendor Transition | Morgan Patel | Requirements | Requirements Task 03 | Critical | Low | Apex Solutions | 2025-05-16 | 2025-06-06 | 2025-06-07 | Completed | 100% | 38500 | 39974.34 | 2 | 1 | 0 | -1474.34
TSK-0064 | PRJ-1004 | Human Resources System Implementation 04 | Human Resources | System Implementation | Taylor Reed | Configuration | Configuration Task 03 | High | Low | Summit Partners | 2026-03-31 | 2026-04-20 |  | Completed | 0% | 42700 | 0 | 3 |  | 0 | 42700
TSK-0065 | PRJ-1005 | Facilities Cost Reduction 05 | Facilities | Cost Reduction | Cameron Diaz | Execution | Execution Task 03 | Medium | Medium | Vertex Systems | 2025-09-28 | 2025-10-15 | 2025-10-23 | Completed | 100% | 5500 | 5774.78 | 4 | 8 | 0 | -274.78
TSK-0066 | PRJ-1006 | Marketing Automation 06 | Marketing | Automation | Riley Chen | Testing | Testing Task 03 | Medium | Medium | Apex Solutions | 2025-09-23 | 2025-10-07 |  | Completed | 85% | 25400 | 24073.83 | 3 |  | 0 | 1326.17
TSK-0067 | PRJ-1007 | Procurement Process Improvement 07 | Procurement | Process Improvement | Avery Brooks | Training | Training Task 03 | Medium | Low | Vertex Systems | 2025-07-19 | 2025-07-25 | 2025-08-06 | Completed | 100% | 9800 | 9494.71 | 1 | 12 | 0 | 305.29
TSK-0068 | PRJ-1008 | Operations Facility Upgrade 08 | Operations | Facility Upgrade | Jordan Lee | Launch | Launch Task 03 | High | Medium | Northstar Consulting | 2025-04-12 | 2025-05-11 |  | Completed | 40% | 17200 | 16025.68 | 1 |  | 0 | 1174.32
TSK-0069 | PRJ-1009 | Technology Compliance 09 | Technology | Compliance | Morgan Patel | Closeout | Closeout Task 03 | Medium | Low | Internal Team | 2026-04-02 | 2026-04-27 |  | In Progress | 50% | 6000 | 7100.27 | 2 |  | 0 | -1100.27
TSK-0070 | PRJ-1010 | Finance Vendor Transition 10 | Finance | Vendor Transition | Taylor Reed | Discovery | Discovery Task 03 | Medium | Low | BluePeak Services | 2025-05-02 | 2025-06-01 | 2025-06-03 | Completed | 100% | 37300 | 36739.44 | 1 | 2 | 0 | 560.56
TSK-0071 | PRJ-1011 | Human Resources System Implementation 11 | Human Resources | System Implementation | Cameron Diaz | Planning | Planning Task 03 | High | Low | Internal Team | 2026-05-11 | 2026-05-23 |  | Not Started | 0% | 12300 | 0 | 1 |  | 0 | 12300
TSK-0072 | PRJ-1012 | Facilities Cost Reduction 12 | Facilities | Cost Reduction | Riley Chen | Requirements | Requirements Task 03 | High | Medium | Vertex Systems | 2026-04-27 | 2026-05-14 | 2026-05-13 | Completed | 100% | 20200 | 23435.09 | 1 | 0 | 0 | -3235.09
TSK-0073 | PRJ-1013 | Marketing Automation 13 | Marketing | Automation | Avery Brooks | Configuration | Configuration Task 03 | Critical | Low | Vertex Systems | 2025-12-05 | 2025-12-16 | 2025-12-17 | Completed | 100% | 8300 | 8632.14 | 2 | 1 | 0 | -332.14
TSK-0074 | PRJ-1014 | Procurement Process Improvement 14 | Procurement | Process Improvement | Jordan Lee | Execution | Execution Task 03 | Low | Low | Northstar Consulting | 2025-05-04 | 2025-05-08 |  | In Progress | 85% | 13800 | 14446.73 | 1 |  | 0 | -646.73
TSK-0075 | PRJ-1015 | Operations Facility Upgrade 15 | Operations | Facility Upgrade | Morgan Patel | Testing | Testing Task 03 | Medium | Low | Summit Partners | 2026-04-03 | 2026-04-27 | 2026-04-30 | Completed | 100% | 11300 | 12107.09 | 2 | 3 | 0 | -807.09
TSK-0076 | PRJ-1016 | Technology Compliance 16 | Technology | Compliance | Taylor Reed | Training | Training Task 03 | Medium | Low | Summit Partners | 2026-01-02 | 2026-01-14 |  | In Progress | 60% | 31500 | 34322.6 | 0 |  | 0 | -2822.6
TSK-0077 | PRJ-1017 | Finance Vendor Transition 17 | Finance | Vendor Transition | Cameron Diaz | Launch | Launch Task 03 | Medium | Low | Internal Team | 2025-02-01 | 2025-02-17 | 2025-02-03 | Completed | 100% | 27800 | 30531.97 | 1 | 0 | 0 | -2731.97
TSK-0078 | PRJ-1018 | Human Resources System Implementation 18 | Human Resources | System Implementation | Riley Chen | Closeout | Closeout Task 03 | High | High | Northstar Consulting | 2025-01-26 | 2025-02-22 | 2025-02-24 | Completed | 100% | 34400 | 37884.27 | 1 | 2 | 0 | -3484.27
TSK-0079 | PRJ-1019 | Facilities Cost Reduction 19 | Facilities | Cost Reduction | Avery Brooks | Discovery | Discovery Task 03 | Critical | Low | Northstar Consulting | 2025-06-27 | 2025-07-02 | 2025-07-06 | Completed | 100% | 19300 | 19255.09 | 2 | 4 | 0 | 44.91
TSK-0080 | PRJ-1020 | Marketing Automation 20 | Marketing | Automation | Jordan Lee | Planning | Planning Task 03 | Medium | Low | Apex Solutions | 2025-08-07 | 2025-09-05 | 2025-09-10 | Completed | 100% | 12500 | 12884.93 | 3 | 5 | 0 | -384.93
TSK-0081 | PRJ-1021 | Procurement Process Improvement 21 | Procurement | Process Improvement | Morgan Patel | Requirements | Requirements Task 03 | High | Medium | Internal Team | 2025-09-20 | 2025-10-07 |  | In Progress | 40% | 24100 | 27618.81 | 1 |  | 0 | -3518.81
TSK-0082 | PRJ-1022 | Operations Facility Upgrade 22 | Operations | Facility Upgrade | Taylor Reed | Configuration | Configuration Task 03 | Medium | Low | Internal Team | 2025-10-24 | 2025-11-05 |  | In Progress | 85% | 22600 | 21017.7 | 3 |  | 0 | 1582.3
TSK-0083 | PRJ-1023 | Technology Compliance 23 | Technology | Compliance | Cameron Diaz | Execution | Execution Task 03 | High | Medium | Internal Team | 2025-11-13 | 2025-12-03 |  | In Progress | 40% | 44700 | 46844.87 | 3 |  | 0 | -2144.87
TSK-0084 | PRJ-1024 | Finance Vendor Transition 24 | Finance | Vendor Transition | Riley Chen | Testing | Testing Task 03 | Low | Medium | Apex Solutions | 2025-04-03 | 2025-04-22 | 2025-04-20 | Completed | 100% | 19600 | 17569.25 | 2 | 0 | 0 | 2030.75
TSK-0085 | PRJ-1025 | Human Resources System Implementation 25 | Human Resources | System Implementation | Avery Brooks | Training | Training Task 03 | Medium | Low | Internal Team | 2026-02-27 | 2026-03-25 | 2026-03-31 | Completed | 100% | 35900 | 34223.25 | 0 | 6 | 0 | 1676.75
TSK-0086 | PRJ-1026 | Facilities Cost Reduction 26 | Facilities | Cost Reduction | Jordan Lee | Launch | Launch Task 03 | Medium | Medium | Internal Team | 2025-07-02 | 2025-07-31 | 2025-08-10 | Completed | 100% | 45000 | 43098.22 | 2 | 10 | 0 | 1901.78
TSK-0087 | PRJ-1027 | Marketing Automation 27 | Marketing | Automation | Morgan Patel | Closeout | Closeout Task 03 | Medium | Low | Apex Solutions | 2026-05-26 | 2026-06-10 |  | In Progress | 50% | 39300 | 43256.29 | 1 |  | 0 | -3956.29
TSK-0088 | PRJ-1028 | Procurement Process Improvement 28 | Procurement | Process Improvement | Taylor Reed | Discovery | Discovery Task 03 | Medium | High | Internal Team | 2026-02-23 | 2026-03-21 | 2026-03-29 | Completed | 100% | 44500 | 45132.93 | 3 | 8 | 0 | -632.93
TSK-0089 | PRJ-1029 | Operations Facility Upgrade 29 | Operations | Facility Upgrade | Cameron Diaz | Planning | Planning Task 03 | Medium | High | Internal Team | 2026-03-25 | 2026-04-24 |  | Not Started | 0% | 38300 | 0 | 5 |  | 0 | 38300
TSK-0090 | PRJ-1030 | Technology Compliance 30 | Technology | Compliance | Riley Chen | Configuration | Configuration Task 03 | Low | Low | Summit Partners | 2025-11-20 | 2025-11-25 | 2025-12-06 | Completed | 100% | 43700 | 40673.72 | 3 | 11 | 0 | 3026.28
TSK-0091 | PRJ-1001 | Operations Facility Upgrade 01 | Operations | Facility Upgrade | Avery Brooks | Execution | Execution Task 04 | High | High | Summit Partners | 2026-04-14 | 2026-04-29 |  | Completed | 50% | 39400 | 43748.39 | 3 |  | 0 | -4348.39
TSK-0092 | PRJ-1002 | Technology Compliance 02 | Technology | Compliance | Jordan Lee | Testing | Testing Task 04 | High | High | BluePeak Services | 2025-03-27 | 2025-04-12 |  | Completed | 10% | 20800 | 20551.09 | 0 |  | 0 | 248.91
TSK-0093 | PRJ-1003 | Finance Vendor Transition 03 | Finance | Vendor Transition | Morgan Patel | Training | Training Task 04 | Low | Medium | Internal Team | 2025-04-23 | 2025-05-09 |  | Completed | 0% | 24600 | 0 | 1 |  | 0 | 24600
TSK-0094 | PRJ-1004 | Human Resources System Implementation 04 | Human Resources | System Implementation | Taylor Reed | Launch | Launch Task 04 | Medium | Low | Summit Partners | 2026-03-22 | 2026-04-09 | 2026-04-16 | Completed | 100% | 12500 | 13947.02 | 1 | 7 | 0 | -1447.02
TSK-0095 | PRJ-1005 | Facilities Cost Reduction 05 | Facilities | Cost Reduction | Cameron Diaz | Closeout | Closeout Task 04 | High | High | Vertex Systems | 2025-07-05 | 2025-07-10 |  | Completed | 50% | 44500 | 48287.28 | 2 |  | 0 | -3787.28
TSK-0096 | PRJ-1006 | Marketing Automation 06 | Marketing | Automation | Riley Chen | Discovery | Discovery Task 04 | High | Low | Internal Team | 2025-08-17 | 2025-09-16 | 2025-10-05 | Completed | 100% | 11800 | 10508.83 | 0 | 19 | 0 | 1291.17
TSK-0097 | PRJ-1007 | Procurement Process Improvement 07 | Procurement | Process Improvement | Avery Brooks | Planning | Planning Task 04 | Critical | Low | BluePeak Services | 2025-08-09 | 2025-08-20 |  | Completed | 0% | 39100 | 0 | 0 |  | 0 | 39100
TSK-0098 | PRJ-1008 | Operations Facility Upgrade 08 | Operations | Facility Upgrade | Jordan Lee | Requirements | Requirements Task 04 | Critical | Medium | Summit Partners | 2025-05-30 | 2025-06-26 | 2025-06-23 | Completed | 100% | 29200 | 27918.57 | 0 | 0 | 0 | 1281.43
TSK-0099 | PRJ-1009 | Technology Compliance 09 | Technology | Compliance | Morgan Patel | Configuration | Configuration Task 04 | High | Medium | Summit Partners | 2026-02-11 | 2026-03-06 | 2026-03-01 | Completed | 100% | 14900 | 13187.82 | 2 | 0 | 0 | 1712.18
TSK-0100 | PRJ-1010 | Finance Vendor Transition 10 | Finance | Vendor Transition | Taylor Reed | Execution | Execution Task 04 | High | Low | Internal Team | 2025-06-13 | 2025-06-21 |  | In Progress | 90% | 25000 | 28829.23 | 1 |  | 0 | -3829.23
TSK-0101 | PRJ-1011 | Human Resources System Implementation 11 | Human Resources | System Implementation | Cameron Diaz | Testing | Testing Task 04 | Critical | Medium | Internal Team | 2026-04-20 | 2026-05-18 |  | In Progress | 90% | 16200 | 19951.67 | 4 |  | 0 | -3751.67
TSK-0102 | PRJ-1012 | Facilities Cost Reduction 12 | Facilities | Cost Reduction | Riley Chen | Training | Training Task 04 | Medium | High | Summit Partners | 2026-05-01 | 2026-05-31 | 2026-05-25 | Completed | 100% | 2100 | 2552.13 | 2 | 0 | 0 | -452.13
TSK-0103 | PRJ-1013 | Marketing Automation 13 | Marketing | Automation | Avery Brooks | Launch | Launch Task 04 | High | Medium | Northstar Consulting | 2026-01-15 | 2026-01-21 | 2026-01-21 | Completed | 100% | 22000 | 18203.94 | 0 | 0 | 0 | 3796.06
TSK-0104 | PRJ-1014 | Procurement Process Improvement 14 | Procurement | Process Improvement | Jordan Lee | Closeout | Closeout Task 04 | Medium | Medium | Northstar Consulting | 2025-06-17 | 2025-07-12 |  | In Progress | 60% | 6600 | 6923.88 | 2 |  | 0 | -323.88
TSK-0105 | PRJ-1015 | Operations Facility Upgrade 15 | Operations | Facility Upgrade | Morgan Patel | Discovery | Discovery Task 04 | Critical | Low | Internal Team | 2026-03-21 | 2026-03-28 |  | In Progress | 50% | 30700 | 30962.46 | 0 |  | 0 | -262.46
TSK-0106 | PRJ-1016 | Technology Compliance 16 | Technology | Compliance | Taylor Reed | Planning | Planning Task 04 | Medium | Medium | Internal Team | 2025-11-24 | 2025-12-17 |  | Not Started | 0% | 22800 | 0 | 3 |  | 0 | 22800
TSK-0107 | PRJ-1017 | Finance Vendor Transition 17 | Finance | Vendor Transition | Cameron Diaz | Requirements | Requirements Task 04 | Low | Low | Internal Team | 2025-03-23 | 2025-04-22 |  | In Progress | 85% | 17500 | 20108.03 | 0 |  | 0 | -2608.03
TSK-0108 | PRJ-1018 | Human Resources System Implementation 18 | Human Resources | System Implementation | Riley Chen | Configuration | Configuration Task 04 | Low | Low | BluePeak Services | 2025-05-17 | 2025-05-22 | 2025-05-18 | Completed | 100% | 2400 | 2171.29 | 1 | 0 | 0 | 228.71
TSK-0109 | PRJ-1019 | Facilities Cost Reduction 19 | Facilities | Cost Reduction | Avery Brooks | Execution | Execution Task 04 | Medium | Medium | Internal Team | 2025-07-13 | 2025-07-22 | 2025-07-19 | Completed | 100% | 36900 | 38384.79 | 4 | 0 | 0 | -1484.79
TSK-0110 | PRJ-1020 | Marketing Automation 20 | Marketing | Automation | Jordan Lee | Testing | Testing Task 04 | High | Medium | Internal Team | 2025-06-03 | 2025-06-10 | 2025-06-13 | Completed | 100% | 39200 | 37998.96 | 3 | 3 | 0 | 1201.04
TSK-0111 | PRJ-1021 | Procurement Process Improvement 21 | Procurement | Process Improvement | Morgan Patel | Training | Training Task 04 | High | Medium | Internal Team | 2025-07-11 | 2025-07-15 |  | Not Started | 0% | 19800 | 0 | 2 |  | 0 | 19800
TSK-0112 | PRJ-1022 | Operations Facility Upgrade 22 | Operations | Facility Upgrade | Taylor Reed | Launch | Launch Task 04 | Medium | Low | Northstar Consulting | 2026-01-14 | 2026-02-02 |  | In Progress | 75% | 3400 | 3556.77 | 2 |  | 0 | -156.77
TSK-0113 | PRJ-1023 | Technology Compliance 23 | Technology | Compliance | Cameron Diaz | Closeout | Closeout Task 04 | Medium | Low | BluePeak Services | 2025-11-25 | 2025-12-13 | 2025-12-01 | Completed | 100% | 20000 | 23104.28 | 2 | 0 | 0 | -3104.28
TSK-0114 | PRJ-1024 | Finance Vendor Transition 24 | Finance | Vendor Transition | Riley Chen | Discovery | Discovery Task 04 | Medium | High | Internal Team | 2025-02-25 | 2025-03-02 |  | Not Started | 0% | 28700 | 0 | 2 |  | 0 | 28700
TSK-0115 | PRJ-1025 | Human Resources System Implementation 25 | Human Resources | System Implementation | Avery Brooks | Planning | Planning Task 04 | Medium | Medium | Internal Team | 2026-02-26 | 2026-03-20 |  | In Progress | 90% | 32000 | 35713.79 | 0 |  | 0 | -3713.79
TSK-0116 | PRJ-1026 | Facilities Cost Reduction 26 | Facilities | Cost Reduction | Jordan Lee | Requirements | Requirements Task 04 | High | Medium | Internal Team | 2025-08-10 | 2025-08-20 |  | In Progress | 90% | 21200 | 20723.43 | 2 |  | 0 | 476.57
TSK-0117 | PRJ-1027 | Marketing Automation 27 | Marketing | Automation | Morgan Patel | Configuration | Configuration Task 04 | Medium | Medium | Internal Team | 2026-02-15 | 2026-03-11 | 2026-03-25 | Completed | 100% | 5600 | 6188.17 | 3 | 14 | 0 | -588.17
TSK-0118 | PRJ-1028 | Procurement Process Improvement 28 | Procurement | Process Improvement | Taylor Reed | Execution | Execution Task 04 | High | Medium | Northstar Consulting | 2026-04-26 | 2026-05-16 |  | In Progress | 25% | 19400 | 21781.77 | 4 |  | 0 | -2381.77
TSK-0119 | PRJ-1029 | Operations Facility Upgrade 29 | Operations | Facility Upgrade | Cameron Diaz | Testing | Testing Task 04 | Medium | High | Internal Team | 2026-03-14 | 2026-04-05 |  | In Progress | 25% | 26600 | 23494.7 | 3 |  | 0 | 3105.3
TSK-0120 | PRJ-1030 | Technology Compliance 30 | Technology | Compliance | Riley Chen | Launch | Launch Task 04 | Medium | Low | Summit Partners | 2026-01-14 | 2026-01-20 | 2026-02-01 | Completed | 100% | 26500 | 29010.95 | 0 | 12 | 0 | -2510.95
TSK-0121 | PRJ-1001 | Operations Facility Upgrade 01 | Operations | Facility Upgrade | Avery Brooks | Closeout | Closeout Task 05 | Critical | Medium | Northstar Consulting | 2026-04-20 | 2026-04-23 | 2026-04-19 | Completed | 100% | 2800 | 2459.58 | 1 | 0 | 0 | 340.42
TSK-0122 | PRJ-1002 | Technology Compliance 02 | Technology | Compliance | Jordan Lee | Discovery | Discovery Task 05 | Critical | Low | Internal Team | 2025-04-09 | 2025-04-30 | 2025-05-14 | Completed | 100% | 4500 | 4515 | 0 | 14 | 0 | -15
TSK-0123 | PRJ-1003 | Finance Vendor Transition 03 | Finance | Vendor Transition | Morgan Patel | Planning | Planning Task 05 | Low | Medium | Internal Team | 2025-05-14 | 2025-05-27 |  | Completed | 0% | 15100 | 0 | 4 |  | 0 | 15100
TSK-0124 | PRJ-1004 | Human Resources System Implementation 04 | Human Resources | System Implementation | Taylor Reed | Requirements | Requirements Task 05 | High | High | Internal Team | 2026-02-01 | 2026-02-25 |  | Completed | 0% | 20800 | 0 | 4 |  | 0 | 20800
TSK-0125 | PRJ-1005 | Facilities Cost Reduction 05 | Facilities | Cost Reduction | Cameron Diaz | Configuration | Configuration Task 05 | Medium | Low | Apex Solutions | 2025-08-22 | 2025-09-07 |  | Completed | 0% | 31000 | 0 | 0 |  | 0 | 31000
TSK-0126 | PRJ-1006 | Marketing Automation 06 | Marketing | Automation | Riley Chen | Execution | Execution Task 05 | Medium | Low | BluePeak Services | 2025-05-25 | 2025-05-28 |  | Completed | 40% | 34900 | 35880.01 | 0 |  | 0 | -980.01
TSK-0127 | PRJ-1007 | Procurement Process Improvement 07 | Procurement | Process Improvement | Avery Brooks | Testing | Testing Task 05 | Low | Low | Internal Team | 2025-06-02 | 2025-06-17 | 2025-06-20 | Completed | 100% | 30600 | 35483.97 | 0 | 3 | 0 | -4883.97
TSK-0128 | PRJ-1008 | Operations Facility Upgrade 08 | Operations | Facility Upgrade | Jordan Lee | Training | Training Task 05 | High | Low | Apex Solutions | 2025-04-06 | 2025-05-06 |  | Completed | 60% | 26400 | 29245.57 | 1 |  | 0 | -2845.57
TSK-0129 | PRJ-1009 | Technology Compliance 09 | Technology | Compliance | Morgan Patel | Launch | Launch Task 05 | Low | Low | Internal Team | 2026-05-15 | 2026-06-13 | 2026-06-08 | Completed | 100% | 17200 | 16718.79 | 1 | 0 | 0 | 481.21
TSK-0130 | PRJ-1010 | Finance Vendor Transition 10 | Finance | Vendor Transition | Taylor Reed | Closeout | Closeout Task 05 | Medium | Low | Internal Team | 2025-05-17 | 2025-06-12 |  | In Progress | 50% | 35400 | 41000.21 | 2 |  | 0 | -5600.21
TSK-0131 | PRJ-1011 | Human Resources System Implementation 11 | Human Resources | System Implementation | Cameron Diaz | Discovery | Discovery Task 05 | Medium | Low | Vertex Systems | 2026-03-17 | 2026-04-12 |  | On Hold | 20% | 11800 | 12557.21 | 2 |  | 0 | -757.21
TSK-0132 | PRJ-1012 | Facilities Cost Reduction 12 | Facilities | Cost Reduction | Riley Chen | Planning | Planning Task 05 | High | Medium | Northstar Consulting | 2026-03-06 | 2026-04-02 | 2026-03-26 | Completed | 100% | 26700 | 28083.49 | 1 | 0 | 0 | -1383.49
TSK-0133 | PRJ-1013 | Marketing Automation 13 | Marketing | Automation | Avery Brooks | Requirements | Requirements Task 05 | High | High | Internal Team | 2025-12-31 | 2026-01-07 |  | In Progress | 60% | 20700 | 17874.98 | 3 |  | 0 | 2825.02
TSK-0134 | PRJ-1014 | Procurement Process Improvement 14 | Procurement | Process Improvement | Jordan Lee | Configuration | Configuration Task 05 | Low | Low | Internal Team | 2025-06-14 | 2025-06-18 |  | Not Started | 0% | 37700 | 0 | 4 |  | 0 | 37700
TSK-0135 | PRJ-1015 | Operations Facility Upgrade 15 | Operations | Facility Upgrade | Morgan Patel | Execution | Execution Task 05 | High | Medium | Apex Solutions | 2026-03-02 | 2026-03-23 | 2026-03-31 | Completed | 100% | 35900 | 40043.12 | 1 | 8 | 0 | -4143.12
TSK-0136 | PRJ-1016 | Technology Compliance 16 | Technology | Compliance | Taylor Reed | Testing | Testing Task 05 | High | Medium | Internal Team | 2025-12-09 | 2025-12-28 |  | Not Started | 0% | 4200 | 0 | 3 |  | 0 | 4200
TSK-0137 | PRJ-1017 | Finance Vendor Transition 17 | Finance | Vendor Transition | Cameron Diaz | Training | Training Task 05 | Medium | Medium | Apex Solutions | 2025-03-07 | 2025-03-11 |  | In Progress | 60% | 44600 | 38838.08 | 1 |  | 0 | 5761.92
TSK-0138 | PRJ-1018 | Human Resources System Implementation 18 | Human Resources | System Implementation | Riley Chen | Launch | Launch Task 05 | Medium | High | Internal Team | 2025-04-17 | 2025-05-11 | 2025-05-15 | Completed | 100% | 4400 | 4030.36 | 5 | 4 | 0 | 369.64
TSK-0139 | PRJ-1019 | Facilities Cost Reduction 19 | Facilities | Cost Reduction | Avery Brooks | Closeout | Closeout Task 05 | Medium | Medium | Northstar Consulting | 2025-04-01 | 2025-04-14 |  | Not Started | 0% | 30400 | 0 | 3 |  | 0 | 30400
TSK-0140 | PRJ-1020 | Marketing Automation 20 | Marketing | Automation | Jordan Lee | Discovery | Discovery Task 05 | High | Medium | Internal Team | 2025-05-18 | 2025-05-30 | 2025-05-29 | Completed | 100% | 29500 | 29286.78 | 2 | 0 | 0 | 213.22
TSK-0141 | PRJ-1021 | Procurement Process Improvement 21 | Procurement | Process Improvement | Morgan Patel | Planning | Planning Task 05 | High | High | BluePeak Services | 2025-09-16 | 2025-09-21 | 2025-09-17 | Completed | 100% | 17300 | 19345.88 | 3 | 0 | 0 | -2045.88
TSK-0142 | PRJ-1022 | Operations Facility Upgrade 22 | Operations | Facility Upgrade | Taylor Reed | Requirements | Requirements Task 05 | Critical | Low | Internal Team | 2025-10-26 | 2025-11-02 |  | Not Started | 0% | 38200 | 0 | 3 |  | 0 | 38200
TSK-0143 | PRJ-1023 | Technology Compliance 23 | Technology | Compliance | Cameron Diaz | Configuration | Configuration Task 05 | High | High | Internal Team | 2026-02-04 | 2026-03-03 | 2026-03-12 | Completed | 100% | 27500 | 30506.38 | 4 | 9 | 0 | -3006.38
TSK-0144 | PRJ-1024 | Finance Vendor Transition 24 | Finance | Vendor Transition | Riley Chen | Execution | Execution Task 05 | High | Medium | BluePeak Services | 2025-05-11 | 2025-05-15 |  | In Progress | 85% | 32800 | 38321.1 | 1 |  | 0 | -5521.1
TSK-0145 | PRJ-1025 | Human Resources System Implementation 25 | Human Resources | System Implementation | Avery Brooks | Testing | Testing Task 05 | High | Medium | Internal Team | 2025-12-20 | 2026-01-01 |  | On Hold | 50% | 40800 | 43944.91 | 4 |  | 0 | -3144.91
TSK-0146 | PRJ-1026 | Facilities Cost Reduction 26 | Facilities | Cost Reduction | Jordan Lee | Training | Training Task 05 | High | Low | Vertex Systems | 2025-07-23 | 2025-08-11 | 2025-08-26 | Completed | 100% | 36400 | 35575.97 | 2 | 15 | 0 | 824.03
TSK-0147 | PRJ-1027 | Marketing Automation 27 | Marketing | Automation | Morgan Patel | Launch | Launch Task 05 | High | High | Apex Solutions | 2026-02-02 | 2026-02-27 | 2026-03-05 | Completed | 100% | 38500 | 39624.32 | 5 | 6 | 0 | -1124.32
TSK-0148 | PRJ-1028 | Procurement Process Improvement 28 | Procurement | Process Improvement | Taylor Reed | Closeout | Closeout Task 05 | Medium | High | Internal Team | 2026-03-25 | 2026-03-30 |  | On Hold | 20% | 37000 | 46625.17 | 1 |  | 0 | -9625.17
TSK-0149 | PRJ-1029 | Operations Facility Upgrade 29 | Operations | Facility Upgrade | Cameron Diaz | Discovery | Discovery Task 05 | Medium | Low | Internal Team | 2026-04-08 | 2026-04-13 |  | In Progress | 25% | 15400 | 17887.62 | 2 |  | 0 | -2487.62
TSK-0150 | PRJ-1030 | Technology Compliance 30 | Technology | Compliance | Riley Chen | Requirements | Requirements Task 05 | Medium | Low | Internal Team | 2026-02-09 | 2026-03-06 | 2026-03-08 | Completed | 100% | 28300 | 25368.2 | 1 | 2 | 0 | 2931.8
TSK-0151 | PRJ-1001 | Operations Facility Upgrade 01 | Operations | Facility Upgrade | Avery Brooks | Configuration | Configuration Task 06 | Medium | Low | BluePeak Services | 2026-04-13 | 2026-04-29 |  | Completed | 0% | 14000 | 0 | 1 |  | 0 | 14000
TSK-0152 | PRJ-1002 | Technology Compliance 02 | Technology | Compliance | Jordan Lee | Execution | Execution Task 06 | Medium | Medium | Apex Solutions | 2025-04-01 | 2025-04-30 | 2025-05-04 | Completed | 100% | 27500 | 31671.63 | 2 | 4 | 0 | -4171.63
TSK-0153 | PRJ-1003 | Finance Vendor Transition 03 | Finance | Vendor Transition | Morgan Patel | Testing | Testing Task 06 | Medium | Low | Internal Team | 2025-04-18 | 2025-04-28 | 2025-05-04 | Completed | 100% | 24300 | 28452.56 | 0 | 6 | 0 | -4152.56
TSK-0154 | PRJ-1004 | Human Resources System Implementation 04 | Human Resources | System Implementation | Taylor Reed | Training | Training Task 06 | Medium | Medium | Apex Solutions | 2026-01-25 | 2026-02-09 | 2026-02-24 | Completed | 100% | 3400 | 3193.98 | 3 | 15 | 0 | 206.02
TSK-0155 | PRJ-1005 | Facilities Cost Reduction 05 | Facilities | Cost Reduction | Cameron Diaz | Launch | Launch Task 06 | High | Low | Internal Team | 2025-07-26 | 2025-08-21 | 2025-08-30 | Completed | 100% | 34400 | 38117.62 | 2 | 9 | 0 | -3717.62
TSK-0156 | PRJ-1006 | Marketing Automation 06 | Marketing | Automation | Riley Chen | Closeout | Closeout Task 06 | Medium | Medium | Summit Partners | 2025-09-06 | 2025-10-01 | 2025-10-08 | Completed | 100% | 9400 | 10674.18 | 3 | 7 | 0 | -1274.18
TSK-0157 | PRJ-1007 | Procurement Process Improvement 07 | Procurement | Process Improvement | Avery Brooks | Discovery | Discovery Task 06 | Critical | Low | Internal Team | 2025-06-20 | 2025-06-24 |  | Completed | 50% | 23900 | 27660.54 | 1 |  | 0 | -3760.54
TSK-0158 | PRJ-1008 | Operations Facility Upgrade 08 | Operations | Facility Upgrade | Jordan Lee | Planning | Planning Task 06 | Medium | Medium | Internal Team | 2025-06-17 | 2025-07-17 | 2025-07-23 | Completed | 100% | 6900 | 6528.91 | 0 | 6 | 0 | 371.09
TSK-0159 | PRJ-1009 | Technology Compliance 09 | Technology | Compliance | Morgan Patel | Requirements | Requirements Task 06 | High | High | Internal Team | 2026-03-06 | 2026-03-24 | 2026-04-06 | Completed | 100% | 17500 | 19168.95 | 2 | 13 | 0 | -1668.95
TSK-0160 | PRJ-1010 | Finance Vendor Transition 10 | Finance | Vendor Transition | Taylor Reed | Configuration | Configuration Task 06 | Low | Low | Internal Team | 2025-04-14 | 2025-05-04 |  | In Progress | 25% | 5000 | 4850.16 | 0 |  | 0 | 149.84
TSK-0161 | PRJ-1011 | Human Resources System Implementation 11 | Human Resources | System Implementation | Cameron Diaz | Execution | Execution Task 06 | High | Low | Vertex Systems | 2026-03-17 | 2026-04-03 |  | Not Started | 0% | 39300 | 0 | 5 |  | 0 | 39300
TSK-0162 | PRJ-1012 | Facilities Cost Reduction 12 | Facilities | Cost Reduction | Riley Chen | Testing | Testing Task 06 | Medium | High | BluePeak Services | 2026-02-08 | 2026-03-04 | 2026-02-26 | Completed | 100% | 31100 | 37931.69 | 4 | 0 | 0 | -6831.69
TSK-0163 | PRJ-1013 | Marketing Automation 13 | Marketing | Automation | Avery Brooks | Training | Training Task 06 | High | Medium | Internal Team | 2025-10-29 | 2025-11-08 | 2025-11-09 | Completed | 100% | 17400 | 15912.04 | 3 | 1 | 0 | 1487.96
TSK-0164 | PRJ-1014 | Procurement Process Improvement 14 | Procurement | Process Improvement | Jordan Lee | Launch | Launch Task 06 | High | Medium | BluePeak Services | 2025-05-25 | 2025-06-11 | 2025-06-05 | Completed | 100% | 18800 | 18038.53 | 1 | 0 | 0 | 761.47
TSK-0165 | PRJ-1015 | Operations Facility Upgrade 15 | Operations | Facility Upgrade | Morgan Patel | Closeout | Closeout Task 06 | Low | Medium | Apex Solutions | 2026-02-11 | 2026-03-03 |  | Not Started | 0% | 35200 | 0 | 1 |  | 0 | 35200
TSK-0166 | PRJ-1016 | Technology Compliance 16 | Technology | Compliance | Taylor Reed | Discovery | Discovery Task 06 | High | Medium | BluePeak Services | 2025-09-30 | 2025-10-06 |  | Not Started | 0% | 4700 | 0 | 3 |  | 0 | 4700
TSK-0167 | PRJ-1017 | Finance Vendor Transition 17 | Finance | Vendor Transition | Cameron Diaz | Planning | Planning Task 06 | Critical | Medium | BluePeak Services | 2025-04-13 | 2025-05-07 |  | In Progress | 25% | 25400 | 29813.56 | 1 |  | 0 | -4413.56
TSK-0168 | PRJ-1018 | Human Resources System Implementation 18 | Human Resources | System Implementation | Riley Chen | Requirements | Requirements Task 06 | Medium | Medium | Vertex Systems | 2025-03-06 | 2025-04-03 |  | In Progress | 40% | 6800 | 7547.5 | 2 |  | 0 | -747.5
TSK-0169 | PRJ-1019 | Facilities Cost Reduction 19 | Facilities | Cost Reduction | Avery Brooks | Configuration | Configuration Task 06 | High | Low | Apex Solutions | 2025-05-27 | 2025-06-13 | 2025-06-19 | Completed | 100% | 25500 | 25101.59 | 1 | 6 | 0 | 398.41
TSK-0170 | PRJ-1020 | Marketing Automation 20 | Marketing | Automation | Jordan Lee | Execution | Execution Task 06 | Medium | High | Vertex Systems | 2025-09-08 | 2025-09-24 | 2025-09-27 | Completed | 100% | 43800 | 45176.77 | 2 | 3 | 0 | -1376.77
TSK-0171 | PRJ-1021 | Procurement Process Improvement 21 | Procurement | Process Improvement | Morgan Patel | Testing | Testing Task 06 | High | Low | Summit Partners | 2025-09-23 | 2025-10-16 | 2025-10-12 | Completed | 100% | 34900 | 38725.05 | 2 | 0 | 0 | -3825.05
TSK-0172 | PRJ-1022 | Operations Facility Upgrade 22 | Operations | Facility Upgrade | Taylor Reed | Training | Training Task 06 | High | Medium | Apex Solutions | 2025-12-07 | 2025-12-15 |  | Not Started | 0% | 42200 | 0 | 5 |  | 0 | 42200
TSK-0173 | PRJ-1023 | Technology Compliance 23 | Technology | Compliance | Cameron Diaz | Launch | Launch Task 06 | Medium | Low | Internal Team | 2025-12-30 | 2026-01-22 |  | On Hold | 30% | 6900 | 6732.6 | 3 |  | 0 | 167.4
TSK-0174 | PRJ-1024 | Finance Vendor Transition 24 | Finance | Vendor Transition | Riley Chen | Closeout | Closeout Task 06 | Medium | Low | BluePeak Services | 2025-02-27 | 2025-03-07 | 2025-03-07 | Completed | 100% | 38200 | 33332.88 | 0 | 0 | 0 | 4867.12
TSK-0175 | PRJ-1025 | Human Resources System Implementation 25 | Human Resources | System Implementation | Avery Brooks | Discovery | Discovery Task 06 | Low | Low | Northstar Consulting | 2026-03-16 | 2026-03-27 | 2026-03-24 | Completed | 100% | 34900 | 30853.47 | 2 | 0 | 0 | 4046.53
TSK-0176 | PRJ-1026 | Facilities Cost Reduction 26 | Facilities | Cost Reduction | Jordan Lee | Planning | Planning Task 06 | Medium | Medium | Internal Team | 2025-07-03 | 2025-07-21 |  | In Progress | 90% | 31300 | 31532.42 | 2 |  | 0 | -232.42
TSK-0177 | PRJ-1027 | Marketing Automation 27 | Marketing | Automation | Morgan Patel | Requirements | Requirements Task 06 | Low | Low | Apex Solutions | 2026-02-28 | 2026-03-13 | 2026-03-11 | Completed | 100% | 33400 | 39470.41 | 3 | 0 | 0 | -6070.41
TSK-0178 | PRJ-1028 | Procurement Process Improvement 28 | Procurement | Process Improvement | Taylor Reed | Configuration | Configuration Task 06 | Medium | Low | Apex Solutions | 2026-02-23 | 2026-03-05 | 2026-02-20 | Completed | 100% | 13100 | 13370.5 | 2 | 0 | 0 | -270.5
TSK-0179 | PRJ-1029 | Operations Facility Upgrade 29 | Operations | Facility Upgrade | Cameron Diaz | Execution | Execution Task 06 | Medium | Low | Northstar Consulting | 2026-03-04 | 2026-04-03 | 2026-04-11 | Completed | 100% | 32900 | 25787.72 | 1 | 8 | 0 | 7112.28
TSK-0180 | PRJ-1030 | Technology Compliance 30 | Technology | Compliance | Riley Chen | Training | Training Task 06 | Critical | Low | Summit Partners | 2026-02-16 | 2026-02-19 |  | Not Started | 0% | 18600 | 0 | 0 |  | 0 | 18600
TSK-0181 | PRJ-1001 | Operations Facility Upgrade 01 | Operations | Facility Upgrade | Avery Brooks | Launch | Launch Task 07 | High | Low | Internal Team | 2026-03-29 | 2026-04-10 | 2026-04-13 | Completed | 100% | 38400 | 31237.71 | 2 | 3 | 0 | 7162.29
TSK-0182 | PRJ-1002 | Technology Compliance 02 | Technology | Compliance | Jordan Lee | Closeout | Closeout Task 07 | High | Medium | Internal Team | 2025-06-14 | 2025-06-18 | 2025-06-23 | Completed | 100% | 4700 | 5411 | 0 | 5 | 0 | -711
TSK-0183 | PRJ-1003 | Finance Vendor Transition 03 | Finance | Vendor Transition | Morgan Patel | Discovery | Discovery Task 07 | Medium | High | Vertex Systems | 2025-02-17 | 2025-02-24 |  | Completed | 50% | 17700 | 18850.49 | 5 |  | 0 | -1150.49
TSK-0184 | PRJ-1004 | Human Resources System Implementation 04 | Human Resources | System Implementation | Taylor Reed | Planning | Planning Task 07 | Medium | Low | Northstar Consulting | 2026-05-02 | 2026-05-21 |  | Completed | 0% | 3200 | 0 | 1 |  | 0 | 3200
TSK-0185 | PRJ-1005 | Facilities Cost Reduction 05 | Facilities | Cost Reduction | Cameron Diaz | Requirements | Requirements Task 07 | Medium | Low | BluePeak Services | 2025-06-30 | 2025-07-13 | 2025-07-03 | Completed | 100% | 15400 | 13873.45 | 2 | 0 | 0 | 1526.55
TSK-0186 | PRJ-1006 | Marketing Automation 06 | Marketing | Automation | Riley Chen | Configuration | Configuration Task 07 | High | Medium | Apex Solutions | 2025-09-18 | 2025-10-08 | 2025-10-03 | Completed | 100% | 2200 | 2138.21 | 1 | 0 | 0 | 61.79
TSK-0187 | PRJ-1007 | Procurement Process Improvement 07 | Procurement | Process Improvement | Avery Brooks | Execution | Execution Task 07 | Medium | Low | BluePeak Services | 2025-05-06 | 2025-05-28 | 2025-06-02 | Completed | 100% | 43600 | 46175.38 | 0 | 5 | 0 | -2575.38
TSK-0188 | PRJ-1008 | Operations Facility Upgrade 08 | Operations | Facility Upgrade | Jordan Lee | Testing | Testing Task 07 | High | Medium | Northstar Consulting | 2025-04-30 | 2025-05-19 | 2025-05-11 | Completed | 100% | 7900 | 6918.89 | 2 | 0 | 0 | 981.11
TSK-0189 | PRJ-1009 | Technology Compliance 09 | Technology | Compliance | Morgan Patel | Training | Training Task 07 | Critical | Low | Internal Team | 2026-04-08 | 2026-04-24 |  | Not Started | 0% | 31500 | 0 | 0 |  | 0 | 31500
TSK-0190 | PRJ-1010 | Finance Vendor Transition 10 | Finance | Vendor Transition | Taylor Reed | Launch | Launch Task 07 | Critical | High | Vertex Systems | 2025-03-14 | 2025-04-08 |  | Not Started | 0% | 10500 | 0 | 2 |  | 0 | 10500
TSK-0191 | PRJ-1011 | Human Resources System Implementation 11 | Human Resources | System Implementation | Cameron Diaz | Closeout | Closeout Task 07 | Medium | Low | Internal Team | 2026-05-03 | 2026-05-16 | 2026-05-27 | Completed | 100% | 30900 | 34978.52 | 0 | 11 | 0 | -4078.52
TSK-0192 | PRJ-1012 | Facilities Cost Reduction 12 | Facilities | Cost Reduction | Riley Chen | Discovery | Discovery Task 07 | High | Low | Apex Solutions | 2026-03-24 | 2026-04-04 | 2026-04-09 | Completed | 100% | 14400 | 18890.45 | 1 | 5 | 0 | -4490.45
TSK-0193 | PRJ-1013 | Marketing Automation 13 | Marketing | Automation | Avery Brooks | Planning | Planning Task 07 | High | Low | Internal Team | 2025-12-21 | 2026-01-02 |  | Not Started | 0% | 30900 | 0 | 0 |  | 0 | 30900
TSK-0194 | PRJ-1014 | Procurement Process Improvement 14 | Procurement | Process Improvement | Jordan Lee | Requirements | Requirements Task 07 | High | High | Summit Partners | 2025-05-04 | 2025-05-08 |  | In Progress | 85% | 4900 | 6278.24 | 5 |  | 0 | -1378.24
TSK-0195 | PRJ-1015 | Operations Facility Upgrade 15 | Operations | Facility Upgrade | Morgan Patel | Configuration | Configuration Task 07 | High | Low | Summit Partners | 2026-01-12 | 2026-02-01 | 2026-01-29 | Completed | 100% | 7500 | 6830.29 | 0 | 0 | 0 | 669.71
TSK-0196 | PRJ-1016 | Technology Compliance 16 | Technology | Compliance | Taylor Reed | Execution | Execution Task 07 | Medium | Medium | Apex Solutions | 2025-10-08 | 2025-10-12 |  | Not Started | 0% | 15900 | 0 | 2 |  | 0 | 15900
TSK-0197 | PRJ-1017 | Finance Vendor Transition 17 | Finance | Vendor Transition | Cameron Diaz | Testing | Testing Task 07 | Medium | High | BluePeak Services | 2025-03-03 | 2025-03-19 | 2025-03-27 | Completed | 100% | 29800 | 29347.07 | 3 | 8 | 0 | 452.93
TSK-0198 | PRJ-1018 | Human Resources System Implementation 18 | Human Resources | System Implementation | Riley Chen | Training | Training Task 07 | Medium | Low | Vertex Systems | 2025-06-16 | 2025-06-26 | 2025-06-22 | Completed | 100% | 33000 | 41059.21 | 0 | 0 | 0 | -8059.21
TSK-0199 | PRJ-1019 | Facilities Cost Reduction 19 | Facilities | Cost Reduction | Avery Brooks | Launch | Launch Task 07 | Medium | High | Internal Team | 2025-03-03 | 2025-04-01 |  | In Progress | 60% | 9600 | 10258.58 | 0 |  | 0 | -658.58
TSK-0200 | PRJ-1020 | Marketing Automation 20 | Marketing | Automation | Jordan Lee | Closeout | Closeout Task 07 | Medium | Low | Internal Team | 2025-05-24 | 2025-06-06 |  | In Progress | 85% | 25100 | 19085.08 | 1 |  | 0 | 6014.92
TSK-0201 | PRJ-1021 | Procurement Process Improvement 21 | Procurement | Process Improvement | Morgan Patel | Discovery | Discovery Task 07 | High | Low | Internal Team | 2025-06-02 | 2025-06-15 |  | Not Started | 0% | 21500 | 0 | 2 |  | 0 | 21500
TSK-0202 | PRJ-1022 | Operations Facility Upgrade 22 | Operations | Facility Upgrade | Taylor Reed | Planning | Planning Task 07 | High | Medium | Apex Solutions | 2025-11-09 | 2025-11-17 | 2025-11-14 | Completed | 100% | 20100 | 18776.19 | 1 | 0 | 0 | 1323.81
TSK-0203 | PRJ-1023 | Technology Compliance 23 | Technology | Compliance | Cameron Diaz | Requirements | Requirements Task 07 | Low | High | Apex Solutions | 2026-01-12 | 2026-01-15 |  | In Progress | 40% | 20900 | 24416.52 | 3 |  | 0 | -3516.52
TSK-0204 | PRJ-1024 | Finance Vendor Transition 24 | Finance | Vendor Transition | Riley Chen | Configuration | Configuration Task 07 | High | Medium | Internal Team | 2025-04-21 | 2025-05-16 |  | In Progress | 85% | 6600 | 7377.59 | 1 |  | 0 | -777.59
TSK-0205 | PRJ-1025 | Human Resources System Implementation 25 | Human Resources | System Implementation | Avery Brooks | Execution | Execution Task 07 | Medium | High | Vertex Systems | 2026-01-07 | 2026-02-01 |  | Not Started | 0% | 41400 | 0 | 2 |  | 0 | 41400
TSK-0206 | PRJ-1026 | Facilities Cost Reduction 26 | Facilities | Cost Reduction | Jordan Lee | Testing | Testing Task 07 | Medium | Low | Internal Team | 2025-07-21 | 2025-08-06 | 2025-08-17 | Completed | 100% | 41200 | 42400.56 | 0 | 11 | 0 | -1200.56
TSK-0207 | PRJ-1027 | Marketing Automation 27 | Marketing | Automation | Morgan Patel | Training | Training Task 07 | High | Medium | Vertex Systems | 2026-01-27 | 2026-02-15 |  | In Progress | 85% | 17200 | 18345.09 | 1 |  | 0 | -1145.09
TSK-0208 | PRJ-1028 | Procurement Process Improvement 28 | Procurement | Process Improvement | Taylor Reed | Launch | Launch Task 07 | High | High | Internal Team | 2026-04-20 | 2026-04-27 |  | Not Started | 0% | 38700 | 0 | 4 |  | 0 | 38700
TSK-0209 | PRJ-1029 | Operations Facility Upgrade 29 | Operations | Facility Upgrade | Cameron Diaz | Closeout | Closeout Task 07 | High | Low | BluePeak Services | 2026-04-24 | 2026-05-22 |  | Not Started | 0% | 7200 | 0 | 2 |  | 0 | 7200
TSK-0210 | PRJ-1030 | Technology Compliance 30 | Technology | Compliance | Riley Chen | Planning | Planning Task 07 | Medium | Medium | Internal Team | 2025-10-17 | 2025-11-01 |  | In Progress | 25% | 33900 | 33577.36 | 2 |  | 0 | 322.64
TSK-0211 | PRJ-1001 | Operations Facility Upgrade 01 | Operations | Facility Upgrade | Avery Brooks | Requirements | Requirements Task 08 | Medium | Low | BluePeak Services | 2025-12-16 | 2026-01-03 |  | Completed | 0% | 19300 | 0 | 0 |  | 0 | 19300
TSK-0212 | PRJ-1002 | Technology Compliance 02 | Technology | Compliance | Jordan Lee | Configuration | Configuration Task 08 | Critical | Medium | Internal Team | 2025-06-09 | 2025-06-26 | 2025-07-04 | Completed | 100% | 31200 | 29982.34 | 1 | 8 | 0 | 1217.66
TSK-0213 | PRJ-1003 | Finance Vendor Transition 03 | Finance | Vendor Transition | Morgan Patel | Execution | Execution Task 08 | High | Low | Internal Team | 2025-06-04 | 2025-06-19 | 2025-06-14 | Completed | 100% | 33200 | 33916.02 | 1 | 0 | 0 | -716.02
TSK-0214 | PRJ-1004 | Human Resources System Implementation 04 | Human Resources | System Implementation | Taylor Reed | Testing | Testing Task 08 | Low | Low | Vertex Systems | 2026-06-08 | 2026-06-24 | 2026-06-28 | Completed | 100% | 16600 | 15698.64 | 1 | 4 | 0 | 901.36
TSK-0215 | PRJ-1005 | Facilities Cost Reduction 05 | Facilities | Cost Reduction | Cameron Diaz | Training | Training Task 08 | High | Low | Summit Partners | 2025-09-10 | 2025-10-02 | 2025-10-20 | Completed | 100% | 39900 | 43665.38 | 1 | 18 | 0 | -3765.38
TSK-0216 | PRJ-1006 | Marketing Automation 06 | Marketing | Automation | Riley Chen | Launch | Launch Task 08 | Low | Low | Northstar Consulting | 2025-05-23 | 2025-06-02 | 2025-05-31 | Completed | 100% | 11000 | 11729.51 | 1 | 0 | 0 | -729.51
TSK-0217 | PRJ-1007 | Procurement Process Improvement 07 | Procurement | Process Improvement | Avery Brooks | Closeout | Closeout Task 08 | Medium | Low | Summit Partners | 2025-09-24 | 2025-10-07 | 2025-10-07 | Completed | 100% | 35100 | 36984.7 | 0 | 0 | 0 | -1884.7
TSK-0218 | PRJ-1008 | Operations Facility Upgrade 08 | Operations | Facility Upgrade | Jordan Lee | Discovery | Discovery Task 08 | High | High | Apex Solutions | 2025-07-01 | 2025-07-13 |  | Completed | 75% | 42800 | 53342.37 | 1 |  | 0 | -10542.37
TSK-0219 | PRJ-1009 | Technology Compliance 09 | Technology | Compliance | Morgan Patel | Planning | Planning Task 08 | High | Low | Apex Solutions | 2026-04-16 | 2026-05-09 | 2026-05-12 | Completed | 100% | 19600 | 18150.66 | 2 | 3 | 0 | 1449.34
TSK-0220 | PRJ-1010 | Finance Vendor Transition 10 | Finance | Vendor Transition | Taylor Reed | Requirements | Requirements Task 08 | High | Low | Summit Partners | 2025-05-14 | 2025-06-13 | 2025-06-20 | Completed | 100% | 36600 | 41782.85 | 0 | 7 | 0 | -5182.85
TSK-0221 | PRJ-1011 | Human Resources System Implementation 11 | Human Resources | System Implementation | Cameron Diaz | Configuration | Configuration Task 08 | Critical | Medium | Internal Team | 2026-02-18 | 2026-03-01 |  | In Progress | 85% | 4900 | 4504.53 | 2 |  | 0 | 395.47
TSK-0222 | PRJ-1012 | Facilities Cost Reduction 12 | Facilities | Cost Reduction | Riley Chen | Execution | Execution Task 08 | Medium | Medium | Internal Team | 2026-04-26 | 2026-05-20 | 2026-05-25 | Completed | 100% | 36500 | 37613.88 | 0 | 5 | 0 | -1113.88
TSK-0223 | PRJ-1013 | Marketing Automation 13 | Marketing | Automation | Avery Brooks | Testing | Testing Task 08 | Medium | Low | BluePeak Services | 2025-12-28 | 2025-12-31 |  | In Progress | 40% | 43400 | 40543.09 | 5 |  | 0 | 2856.91
TSK-0224 | PRJ-1014 | Procurement Process Improvement 14 | Procurement | Process Improvement | Jordan Lee | Training | Training Task 08 | Medium | Low | Northstar Consulting | 2025-04-12 | 2025-04-27 | 2025-05-18 | Completed | 100% | 25500 | 26448.29 | 0 | 21 | 0 | -948.29
TSK-0225 | PRJ-1015 | Operations Facility Upgrade 15 | Operations | Facility Upgrade | Morgan Patel | Launch | Launch Task 08 | Medium | Low | Internal Team | 2026-03-15 | 2026-04-02 | 2026-04-08 | Completed | 100% | 34600 | 29531.01 | 1 | 6 | 0 | 5068.99
TSK-0226 | PRJ-1016 | Technology Compliance 16 | Technology | Compliance | Taylor Reed | Closeout | Closeout Task 08 | Medium | Low | Summit Partners | 2025-09-16 | 2025-09-19 |  | In Progress | 75% | 26700 | 29023.6 | 1 |  | 0 | -2323.6
TSK-0227 | PRJ-1017 | Finance Vendor Transition 17 | Finance | Vendor Transition | Cameron Diaz | Discovery | Discovery Task 08 | Medium | Low | Summit Partners | 2025-05-29 | 2025-06-18 | 2025-06-22 | Completed | 100% | 31300 | 31631.82 | 4 | 4 | 0 | -331.82
TSK-0228 | PRJ-1018 | Human Resources System Implementation 18 | Human Resources | System Implementation | Riley Chen | Planning | Planning Task 08 | Critical | Medium | Apex Solutions | 2025-03-05 | 2025-03-31 | 2025-04-07 | Completed | 100% | 22700 | 26638.03 | 3 | 7 | 0 | -3938.03
TSK-0229 | PRJ-1019 | Facilities Cost Reduction 19 | Facilities | Cost Reduction | Avery Brooks | Requirements | Requirements Task 08 | High | Low | Internal Team | 2025-03-13 | 2025-04-11 | 2025-04-09 | Completed | 100% | 34700 | 29138.74 | 3 | 0 | 0 | 5561.26
TSK-0230 | PRJ-1020 | Marketing Automation 20 | Marketing | Automation | Jordan Lee | Configuration | Configuration Task 08 | Medium | Medium | Internal Team | 2025-09-03 | 2025-09-20 |  | In Progress | 75% | 29200 | 36275.06 | 1 |  | 0 | -7075.06
TSK-0231 | PRJ-1021 | Procurement Process Improvement 21 | Procurement | Process Improvement | Morgan Patel | Execution | Execution Task 08 | High | Low | Apex Solutions | 2025-08-18 | 2025-08-21 |  | Not Started | 0% | 32900 | 0 | 1 |  | 0 | 32900
TSK-0232 | PRJ-1022 | Operations Facility Upgrade 22 | Operations | Facility Upgrade | Taylor Reed | Testing | Testing Task 08 | Medium | Medium | Internal Team | 2025-11-05 | 2025-11-11 | 2025-11-08 | Completed | 100% | 28500 | 28714.7 | 2 | 0 | 0 | -214.7
TSK-0233 | PRJ-1023 | Technology Compliance 23 | Technology | Compliance | Cameron Diaz | Training | Training Task 08 | High | Low | BluePeak Services | 2026-03-07 | 2026-03-28 |  | In Progress | 85% | 11300 | 12688.77 | 0 |  | 0 | -1388.77
TSK-0234 | PRJ-1024 | Finance Vendor Transition 24 | Finance | Vendor Transition | Riley Chen | Launch | Launch Task 08 | High | High | Vertex Systems | 2025-02-11 | 2025-02-26 |  | In Progress | 75% | 22200 | 19416.18 | 2 |  | 0 | 2783.82
TSK-0235 | PRJ-1025 | Human Resources System Implementation 25 | Human Resources | System Implementation | Avery Brooks | Closeout | Closeout Task 08 | Low | Medium | Northstar Consulting | 2026-01-12 | 2026-02-02 |  | On Hold | 10% | 40400 | 35964.83 | 3 |  | 0 | 4435.17
TSK-0236 | PRJ-1026 | Facilities Cost Reduction 26 | Facilities | Cost Reduction | Jordan Lee | Discovery | Discovery Task 08 | Critical | Medium | Apex Solutions | 2025-06-25 | 2025-06-29 | 2025-06-29 | Completed | 100% | 31300 | 31108.67 | 3 | 0 | 0 | 191.33
TSK-0237 | PRJ-1027 | Marketing Automation 27 | Marketing | Automation | Morgan Patel | Planning | Planning Task 08 | High | Low | Summit Partners | 2026-01-11 | 2026-01-20 | 2026-01-22 | Completed | 100% | 18800 | 15910.11 | 2 | 2 | 0 | 2889.89
TSK-0238 | PRJ-1028 | Procurement Process Improvement 28 | Procurement | Process Improvement | Taylor Reed | Requirements | Requirements Task 08 | Medium | Medium | Internal Team | 2026-04-21 | 2026-05-04 |  | In Progress | 85% | 7600 | 7983.37 | 4 |  | 0 | -383.37
TSK-0239 | PRJ-1029 | Operations Facility Upgrade 29 | Operations | Facility Upgrade | Cameron Diaz | Configuration | Configuration Task 08 | Medium | High | Internal Team | 2026-04-21 | 2026-05-01 | 2026-05-02 | Completed | 100% | 16300 | 17972.69 | 0 | 1 | 0 | -1672.69
TSK-0240 | PRJ-1030 | Technology Compliance 30 | Technology | Compliance | Riley Chen | Testing | Testing Task 08 | Medium | Medium | Internal Team | 2025-12-20 | 2026-01-17 |  | On Hold | 50% | 11400 | 10478.25 | 1 |  | 0 | 921.75
TSK-0241 | PRJ-1001 | Operations Facility Upgrade 01 | Operations | Facility Upgrade | Avery Brooks | Training | Training Task 09 | Medium | Medium | Internal Team | 2026-02-12 | 2026-03-12 |  | Completed | 25% | 5100 | 5702.89 | 3 |  | 0 | -602.89
TSK-0242 | PRJ-1002 | Technology Compliance 02 | Technology | Compliance | Jordan Lee | Launch | Launch Task 09 | High | Medium | Internal Team | 2025-03-31 | 2025-04-05 |  | Completed | 0% | 14900 | 0 | 2 |  | 0 | 14900
TSK-0243 | PRJ-1003 | Finance Vendor Transition 03 | Finance | Vendor Transition | Morgan Patel | Closeout | Closeout Task 09 | Medium | Low | Internal Team | 2025-06-09 | 2025-06-28 |  | Completed | 25% | 5400 | 4753.27 | 1 |  | 0 | 646.73
TSK-0244 | PRJ-1004 | Human Resources System Implementation 04 | Human Resources | System Implementation | Taylor Reed | Discovery | Discovery Task 09 | High | High | Internal Team | 2026-05-05 | 2026-05-20 | 2026-05-21 | Completed | 100% | 44700 | 41610.94 | 3 | 1 | 0 | 3089.06
TSK-0245 | PRJ-1005 | Facilities Cost Reduction 05 | Facilities | Cost Reduction | Cameron Diaz | Planning | Planning Task 09 | High | Low | Internal Team | 2025-08-02 | 2025-08-20 |  | Completed | 0% | 8800 | 0 | 1 |  | 0 | 8800
TSK-0246 | PRJ-1006 | Marketing Automation 06 | Marketing | Automation | Riley Chen | Requirements | Requirements Task 09 | High | Low | BluePeak Services | 2025-09-14 | 2025-10-06 | 2025-10-14 | Completed | 100% | 21400 | 22008.78 | 1 | 8 | 0 | -608.78
TSK-0247 | PRJ-1007 | Procurement Process Improvement 07 | Procurement | Process Improvement | Avery Brooks | Configuration | Configuration Task 09 | Medium | Medium | Internal Team | 2025-07-23 | 2025-08-09 |  | Completed | 90% | 37300 | 34835.25 | 0 |  | 0 | 2464.75
TSK-0248 | PRJ-1008 | Operations Facility Upgrade 08 | Operations | Facility Upgrade | Jordan Lee | Execution | Execution Task 09 | Medium | Medium | Vertex Systems | 2025-07-18 | 2025-07-31 |  | Completed | 0% | 18800 | 0 | 4 |  | 0 | 18800
TSK-0249 | PRJ-1009 | Technology Compliance 09 | Technology | Compliance | Morgan Patel | Testing | Testing Task 09 | High | High | Vertex Systems | 2026-04-11 | 2026-04-26 |  | In Progress | 90% | 18600 | 21891.22 | 4 |  | 0 | -3291.22
TSK-0250 | PRJ-1010 | Finance Vendor Transition 10 | Finance | Vendor Transition | Taylor Reed | Training | Training Task 09 | High | Medium | Vertex Systems | 2025-07-17 | 2025-07-20 |  | On Hold | 50% | 42500 | 45446.3 | 4 |  | 0 | -2946.3
TSK-0251 | PRJ-1011 | Human Resources System Implementation 11 | Human Resources | System Implementation | Cameron Diaz | Launch | Launch Task 09 | High | Low | Summit Partners | 2026-04-01 | 2026-04-25 | 2026-04-24 | Completed | 100% | 30200 | 28966.14 | 1 | 0 | 0 | 1233.86
TSK-0252 | PRJ-1012 | Facilities Cost Reduction 12 | Facilities | Cost Reduction | Riley Chen | Closeout | Closeout Task 09 | Low | High | Apex Solutions | 2026-05-02 | 2026-05-22 | 2026-05-12 | Completed | 100% | 41500 | 42357.25 | 1 | 0 | 0 | -857.25
TSK-0253 | PRJ-1013 | Marketing Automation 13 | Marketing | Automation | Avery Brooks | Discovery | Discovery Task 09 | High | Low | BluePeak Services | 2026-02-26 | 2026-03-20 | 2026-04-01 | Completed | 100% | 30100 | 33586.58 | 0 | 12 | 0 | -3486.58
TSK-0254 | PRJ-1014 | Procurement Process Improvement 14 | Procurement | Process Improvement | Jordan Lee | Planning | Planning Task 09 | Low | High | Vertex Systems | 2025-06-01 | 2025-06-28 |  | In Progress | 90% | 20200 | 24147.6 | 4 |  | 0 | -3947.6
TSK-0255 | PRJ-1015 | Operations Facility Upgrade 15 | Operations | Facility Upgrade | Morgan Patel | Requirements | Requirements Task 09 | Medium | Low | Northstar Consulting | 2026-03-31 | 2026-04-10 |  | In Progress | 60% | 21600 | 22153.76 | 0 |  | 0 | -553.76
TSK-0256 | PRJ-1016 | Technology Compliance 16 | Technology | Compliance | Taylor Reed | Configuration | Configuration Task 09 | Medium | High | Apex Solutions | 2025-10-24 | 2025-11-09 | 2025-11-01 | Completed | 100% | 5200 | 6016.72 | 1 | 0 | 0 | -816.72
TSK-0257 | PRJ-1017 | Finance Vendor Transition 17 | Finance | Vendor Transition | Cameron Diaz | Execution | Execution Task 09 | Medium | Low | Vertex Systems | 2025-06-04 | 2025-06-22 |  | In Progress | 25% | 20600 | 20360.02 | 0 |  | 0 | 239.98
TSK-0258 | PRJ-1018 | Human Resources System Implementation 18 | Human Resources | System Implementation | Riley Chen | Testing | Testing Task 09 | Medium | Medium | Internal Team | 2025-04-18 | 2025-05-11 |  | Not Started | 0% | 36300 | 0 | 1 |  | 0 | 36300
TSK-0259 | PRJ-1019 | Facilities Cost Reduction 19 | Facilities | Cost Reduction | Avery Brooks | Training | Training Task 09 | Medium | Medium | Internal Team | 2025-06-11 | 2025-06-28 |  | In Progress | 60% | 28900 | 31288.44 | 3 |  | 0 | -2388.44
TSK-0260 | PRJ-1020 | Marketing Automation 20 | Marketing | Automation | Jordan Lee | Launch | Launch Task 09 | Medium | Medium | Summit Partners | 2025-08-20 | 2025-09-10 |  | In Progress | 25% | 32200 | 34466.95 | 4 |  | 0 | -2266.95
TSK-0261 | PRJ-1021 | Procurement Process Improvement 21 | Procurement | Process Improvement | Morgan Patel | Closeout | Closeout Task 09 | High | Low | Internal Team | 2025-09-19 | 2025-09-27 |  | In Progress | 40% | 21400 | 21464.3 | 4 |  | 0 | -64.3
TSK-0262 | PRJ-1022 | Operations Facility Upgrade 22 | Operations | Facility Upgrade | Taylor Reed | Discovery | Discovery Task 09 | Medium | Medium | Northstar Consulting | 2025-12-30 | 2026-01-20 |  | Not Started | 0% | 16800 | 0 | 2 |  | 0 | 16800
TSK-0263 | PRJ-1023 | Technology Compliance 23 | Technology | Compliance | Cameron Diaz | Planning | Planning Task 09 | High | Medium | BluePeak Services | 2025-12-01 | 2025-12-25 |  | Not Started | 0% | 6600 | 0 | 2 |  | 0 | 6600
TSK-0264 | PRJ-1024 | Finance Vendor Transition 24 | Finance | Vendor Transition | Riley Chen | Requirements | Requirements Task 09 | High | Low | Internal Team | 2025-02-23 | 2025-03-16 |  | In Progress | 40% | 22700 | 17707.24 | 1 |  | 0 | 4992.76
TSK-0265 | PRJ-1025 | Human Resources System Implementation 25 | Human Resources | System Implementation | Avery Brooks | Configuration | Configuration Task 09 | Critical | Low | Internal Team | 2026-01-01 | 2026-01-08 |  | In Progress | 90% | 21100 | 23588.08 | 2 |  | 0 | -2488.08
TSK-0266 | PRJ-1026 | Facilities Cost Reduction 26 | Facilities | Cost Reduction | Jordan Lee | Execution | Execution Task 09 | Low | Low | Summit Partners | 2025-09-07 | 2025-09-26 | 2025-09-21 | Completed | 100% | 32400 | 35288.71 | 0 | 0 | 0 | -2888.71
TSK-0267 | PRJ-1027 | Marketing Automation 27 | Marketing | Automation | Morgan Patel | Testing | Testing Task 09 | Medium | Medium | Internal Team | 2026-01-15 | 2026-01-26 |  | In Progress | 50% | 8800 | 9178.36 | 0 |  | 0 | -378.36
TSK-0268 | PRJ-1028 | Procurement Process Improvement 28 | Procurement | Process Improvement | Taylor Reed | Training | Training Task 09 | High | Medium | Internal Team | 2026-01-02 | 2026-01-13 | 2026-01-18 | Completed | 100% | 37300 | 32933.1 | 3 | 5 | 0 | 4366.9
TSK-0269 | PRJ-1029 | Operations Facility Upgrade 29 | Operations | Facility Upgrade | Cameron Diaz | Launch | Launch Task 09 | Low | Medium | Apex Solutions | 2026-04-18 | 2026-04-24 | 2026-04-23 | Completed | 100% | 39600 | 37690.36 | 3 | 0 | 0 | 1909.64
TSK-0270 | PRJ-1030 | Technology Compliance 30 | Technology | Compliance | Riley Chen | Discovery | Discovery Task 09 | High | Low | Summit Partners | 2025-11-11 | 2025-12-08 | 2025-12-11 | Completed | 100% | 10600 | 10673.42 | 0 | 3 | 0 | -73.42
TSK-0271 | PRJ-1001 | Operations Facility Upgrade 01 | Operations | Facility Upgrade | Avery Brooks | Planning | Planning Task 10 | High | Medium | Internal Team | 2026-01-03 | 2026-01-31 |  | Completed | 40% | 36500 | 32752.4 | 1 |  | 0 | 3747.6
TSK-0272 | PRJ-1002 | Technology Compliance 02 | Technology | Compliance | Jordan Lee | Requirements | Requirements Task 10 | High | Low | BluePeak Services | 2025-05-17 | 2025-05-29 | 2025-06-08 | Completed | 100% | 40700 | 39928.35 | 1 | 10 | 0 | 771.65
TSK-0273 | PRJ-1003 | Finance Vendor Transition 03 | Finance | Vendor Transition | Morgan Patel | Configuration | Configuration Task 10 | High | Low | Internal Team | 2025-03-29 | 2025-04-28 | 2025-04-27 | Completed | 100% | 32000 | 33970.41 | 2 | 0 | 0 | -1970.41
TSK-0274 | PRJ-1004 | Human Resources System Implementation 04 | Human Resources | System Implementation | Taylor Reed | Execution | Execution Task 10 | Medium | Low | Summit Partners | 2026-04-30 | 2026-05-18 |  | Completed | 0% | 29000 | 0 | 0 |  | 0 | 29000
TSK-0275 | PRJ-1005 | Facilities Cost Reduction 05 | Facilities | Cost Reduction | Cameron Diaz | Testing | Testing Task 10 | Low | Medium | Vertex Systems | 2025-09-06 | 2025-09-25 | 2025-09-22 | Completed | 100% | 21300 | 17213.17 | 0 | 0 | 0 | 4086.83
TSK-0276 | PRJ-1006 | Marketing Automation 06 | Marketing | Automation | Riley Chen | Training | Training Task 10 | High | Medium | Internal Team | 2025-09-05 | 2025-09-28 | 2025-10-01 | Completed | 100% | 17100 | 19586.16 | 2 | 3 | 0 | -2486.16
TSK-0277 | PRJ-1007 | Procurement Process Improvement 07 | Procurement | Process Improvement | Avery Brooks | Launch | Launch Task 10 | Medium | Low | Internal Team | 2025-07-07 | 2025-07-20 | 2025-07-17 | Completed | 100% | 26100 | 29834.1 | 0 | 0 | 0 | -3734.1
TSK-0278 | PRJ-1008 | Operations Facility Upgrade 08 | Operations | Facility Upgrade | Jordan Lee | Closeout | Closeout Task 10 | High | Low | Internal Team | 2025-07-13 | 2025-07-16 |  | Completed | 0% | 38800 | 0 | 1 |  | 0 | 38800
TSK-0279 | PRJ-1009 | Technology Compliance 09 | Technology | Compliance | Morgan Patel | Discovery | Discovery Task 10 | Critical | Low | Vertex Systems | 2026-02-20 | 2026-03-15 |  | In Progress | 90% | 42100 | 43003.41 | 1 |  | 0 | -903.41
TSK-0280 | PRJ-1010 | Finance Vendor Transition 10 | Finance | Vendor Transition | Taylor Reed | Planning | Planning Task 10 | Medium | Low | BluePeak Services | 2025-04-10 | 2025-04-14 |  | In Progress | 50% | 33100 | 39010.57 | 1 |  | 0 | -5910.57
TSK-0281 | PRJ-1011 | Human Resources System Implementation 11 | Human Resources | System Implementation | Cameron Diaz | Requirements | Requirements Task 10 | Low | Low | Internal Team | 2026-01-06 | 2026-01-13 | 2026-01-08 | Completed | 100% | 24100 | 24264.58 | 1 | 0 | 0 | -164.58
TSK-0282 | PRJ-1012 | Facilities Cost Reduction 12 | Facilities | Cost Reduction | Riley Chen | Configuration | Configuration Task 10 | Medium | Low | Summit Partners | 2026-02-22 | 2026-03-12 |  | Not Started | 0% | 18200 | 0 | 1 |  | 0 | 18200
TSK-0283 | PRJ-1013 | Marketing Automation 13 | Marketing | Automation | Avery Brooks | Execution | Execution Task 10 | Medium | High | Internal Team | 2025-11-15 | 2025-12-08 |  | On Hold | 20% | 4500 | 4188.45 | 2 |  | 0 | 311.55
TSK-0284 | PRJ-1014 | Procurement Process Improvement 14 | Procurement | Process Improvement | Jordan Lee | Testing | Testing Task 10 | Medium | Low | Internal Team | 2025-03-29 | 2025-04-14 | 2025-04-11 | Completed | 100% | 40500 | 42414.29 | 2 | 0 | 0 | -1914.29
TSK-0285 | PRJ-1015 | Operations Facility Upgrade 15 | Operations | Facility Upgrade | Morgan Patel | Training | Training Task 10 | High | Low | Internal Team | 2025-12-09 | 2025-12-19 |  | In Progress | 25% | 12300 | 13080.52 | 0 |  | 0 | -780.52
TSK-0286 | PRJ-1016 | Technology Compliance 16 | Technology | Compliance | Taylor Reed | Launch | Launch Task 10 | Medium | High | Internal Team | 2025-10-26 | 2025-11-04 | 2025-10-30 | Completed | 100% | 23700 | 25329.43 | 2 | 0 | 0 | -1629.43
TSK-0287 | PRJ-1017 | Finance Vendor Transition 17 | Finance | Vendor Transition | Cameron Diaz | Closeout | Closeout Task 10 | Low | High | BluePeak Services | 2025-05-28 | 2025-06-12 |  | Not Started | 0% | 23200 | 0 | 2 |  | 0 | 23200
TSK-0288 | PRJ-1018 | Human Resources System Implementation 18 | Human Resources | System Implementation | Riley Chen | Discovery | Discovery Task 10 | Critical | High | BluePeak Services | 2025-02-23 | 2025-03-10 | 2025-03-06 | Completed | 100% | 31200 | 32020.58 | 3 | 0 | 0 | -820.58
TSK-0289 | PRJ-1019 | Facilities Cost Reduction 19 | Facilities | Cost Reduction | Avery Brooks | Planning | Planning Task 10 | High | Low | Internal Team | 2025-04-30 | 2025-05-09 |  | Not Started | 0% | 4100 | 0 | 2 |  | 0 | 4100
TSK-0290 | PRJ-1020 | Marketing Automation 20 | Marketing | Automation | Jordan Lee | Requirements | Requirements Task 10 | High | Low | Internal Team | 2025-08-07 | 2025-08-12 | 2025-08-06 | Completed | 100% | 24900 | 26055.03 | 2 | 0 | 0 | -1155.03
TSK-0291 | PRJ-1021 | Procurement Process Improvement 21 | Procurement | Process Improvement | Morgan Patel | Configuration | Configuration Task 10 | Low | High | BluePeak Services | 2025-06-13 | 2025-07-03 |  | In Progress | 75% | 29100 | 33587.95 | 1 |  | 0 | -4487.95
TSK-0292 | PRJ-1022 | Operations Facility Upgrade 22 | Operations | Facility Upgrade | Taylor Reed | Execution | Execution Task 10 | Low | Medium | Vertex Systems | 2025-11-21 | 2025-11-25 |  | In Progress | 60% | 6500 | 6446.87 | 1 |  | 0 | 53.13
TSK-0293 | PRJ-1023 | Technology Compliance 23 | Technology | Compliance | Cameron Diaz | Testing | Testing Task 10 | High | Medium | Internal Team | 2025-11-13 | 2025-12-08 |  | Not Started | 0% | 2000 | 0 | 2 |  | 0 | 2000
TSK-0294 | PRJ-1024 | Finance Vendor Transition 24 | Finance | Vendor Transition | Riley Chen | Training | Training Task 10 | Medium | Medium | Internal Team | 2025-04-24 | 2025-05-01 | 2025-05-11 | Completed | 100% | 6600 | 5889.77 | 3 | 10 | 0 | 710.23
TSK-0295 | PRJ-1025 | Human Resources System Implementation 25 | Human Resources | System Implementation | Avery Brooks | Launch | Launch Task 10 | Medium | Medium | Internal Team | 2026-03-16 | 2026-04-08 |  | Not Started | 0% | 21300 | 0 | 1 |  | 0 | 21300
TSK-0296 | PRJ-1026 | Facilities Cost Reduction 26 | Facilities | Cost Reduction | Jordan Lee | Closeout | Closeout Task 10 | Medium | Low | Internal Team | 2025-05-13 | 2025-06-03 | 2025-06-11 | Completed | 100% | 6500 | 6627.03 | 1 | 8 | 0 | -127.03
TSK-0297 | PRJ-1027 | Marketing Automation 27 | Marketing | Automation | Morgan Patel | Discovery | Discovery Task 10 | High | Low | Internal Team | 2026-04-10 | 2026-04-25 | 2026-05-05 | Completed | 100% | 3000 | 3816.28 | 2 | 10 | 0 | -816.28
TSK-0298 | PRJ-1028 | Procurement Process Improvement 28 | Procurement | Process Improvement | Taylor Reed | Planning | Planning Task 10 | High | Low | Internal Team | 2026-02-23 | 2026-03-06 | 2026-02-26 | Completed | 100% | 26400 | 30105.78 | 3 | 0 | 0 | -3705.78
TSK-0299 | PRJ-1029 | Operations Facility Upgrade 29 | Operations | Facility Upgrade | Cameron Diaz | Requirements | Requirements Task 10 | Low | Low | Apex Solutions | 2026-01-11 | 2026-01-26 |  | Not Started | 0% | 21700 | 0 | 4 |  | 0 | 21700
TSK-0300 | PRJ-1030 | Technology Compliance 30 | Technology | Compliance | Riley Chen | Execution | Execution Task 10 | Medium | Medium | Internal Team | 2025-12-02 | 2025-12-14 | 2025-12-13 | Completed | 100% | 21700 | 25277.48 | 0 | 0 | 0 | -3577.48
TSK-0301 | PRJ-1001 | Operations Facility Upgrade 01 | Operations | Facility Upgrade | Avery Brooks | Testing | Testing Task 11 | High | Low | BluePeak Services | 2026-01-30 | 2026-02-06 |  | Completed | 0% | 19300 | 0 | 1 |  | 0 | 19300
TSK-0302 | PRJ-1002 | Technology Compliance 02 | Technology | Compliance | Jordan Lee | Training | Training Task 11 | High | High | BluePeak Services | 2025-03-04 | 2025-03-31 | 2025-04-08 | Completed | 100% | 38400 | 40805.64 | 2 | 8 | 0 | -2405.64
TSK-0303 | PRJ-1003 | Finance Vendor Transition 03 | Finance | Vendor Transition | Morgan Patel | Launch | Launch Task 11 | Medium | Low | Apex Solutions | 2025-02-02 | 2025-02-09 | 2025-02-24 | Completed | 100% | 40500 | 46852.46 | 0 | 15 | 0 | -6352.46
TSK-0304 | PRJ-1004 | Human Resources System Implementation 04 | Human Resources | System Implementation | Taylor Reed | Closeout | Closeout Task 11 | Medium | High | Internal Team | 2026-02-13 | 2026-03-04 |  | Completed | 0% | 37200 | 0 | 5 |  | 0 | 37200
TSK-0305 | PRJ-1005 | Facilities Cost Reduction 05 | Facilities | Cost Reduction | Cameron Diaz | Discovery | Discovery Task 11 | Medium | High | Internal Team | 2025-07-31 | 2025-08-30 |  | Completed | 90% | 18600 | 21102.65 | 4 |  | 0 | -2502.65
TSK-0306 | PRJ-1006 | Marketing Automation 06 | Marketing | Automation | Riley Chen | Planning | Planning Task 11 | Medium | Low | BluePeak Services | 2025-06-14 | 2025-07-11 | 2025-07-08 | Completed | 100% | 6200 | 6910.97 | 2 | 0 | 0 | -710.97
TSK-0307 | PRJ-1007 | Procurement Process Improvement 07 | Procurement | Process Improvement | Avery Brooks | Requirements | Requirements Task 11 | Medium | Low | Internal Team | 2025-06-22 | 2025-07-09 |  | Completed | 50% | 38600 | 45869.93 | 2 |  | 0 | -7269.93
TSK-0308 | PRJ-1008 | Operations Facility Upgrade 08 | Operations | Facility Upgrade | Jordan Lee | Configuration | Configuration Task 11 | Medium | Medium | Northstar Consulting | 2025-05-12 | 2025-06-10 | 2025-06-19 | Completed | 100% | 43600 | 50539.79 | 1 | 9 | 0 | -6939.79
TSK-0309 | PRJ-1009 | Technology Compliance 09 | Technology | Compliance | Morgan Patel | Execution | Execution Task 11 | Medium | Medium | Internal Team | 2026-05-01 | 2026-05-31 |  | In Progress | 85% | 25400 | 26445.07 | 2 |  | 0 | -1045.07
TSK-0310 | PRJ-1010 | Finance Vendor Transition 10 | Finance | Vendor Transition | Taylor Reed | Testing | Testing Task 11 | High | Low | Internal Team | 2025-04-24 | 2025-05-01 |  | In Progress | 60% | 17700 | 18560.11 | 0 |  | 0 | -860.11
TSK-0311 | PRJ-1011 | Human Resources System Implementation 11 | Human Resources | System Implementation | Cameron Diaz | Training | Training Task 11 | High | Low | Summit Partners | 2025-12-23 | 2025-12-28 |  | In Progress | 85% | 20800 | 18812.42 | 3 |  | 0 | 1987.58
TSK-0312 | PRJ-1012 | Facilities Cost Reduction 12 | Facilities | Cost Reduction | Riley Chen | Launch | Launch Task 11 | High | Low | Internal Team | 2026-05-18 | 2026-05-22 |  | Not Started | 0% | 26500 | 0 | 2 |  | 0 | 26500
TSK-0313 | PRJ-1013 | Marketing Automation 13 | Marketing | Automation | Avery Brooks | Closeout | Closeout Task 11 | Low | Medium | Internal Team | 2025-12-05 | 2025-12-13 |  | In Progress | 60% | 39900 | 36736.76 | 3 |  | 0 | 3163.24
TSK-0314 | PRJ-1014 | Procurement Process Improvement 14 | Procurement | Process Improvement | Jordan Lee | Discovery | Discovery Task 11 | Medium | Low | Internal Team | 2025-07-09 | 2025-07-27 |  | Not Started | 0% | 13700 | 0 | 2 |  | 0 | 13700
TSK-0315 | PRJ-1015 | Operations Facility Upgrade 15 | Operations | Facility Upgrade | Morgan Patel | Planning | Planning Task 11 | High | Medium | Northstar Consulting | 2026-03-23 | 2026-04-20 |  | Not Started | 0% | 18100 | 0 | 1 |  | 0 | 18100
TSK-0316 | PRJ-1016 | Technology Compliance 16 | Technology | Compliance | Taylor Reed | Requirements | Requirements Task 11 | High | Low | Apex Solutions | 2025-10-31 | 2025-11-15 |  | In Progress | 25% | 15400 | 13822.67 | 2 |  | 0 | 1577.33
TSK-0317 | PRJ-1017 | Finance Vendor Transition 17 | Finance | Vendor Transition | Cameron Diaz | Configuration | Configuration Task 11 | High | Low | BluePeak Services | 2025-06-06 | 2025-06-20 | 2025-07-07 | Completed | 100% | 45000 | 48143.55 | 1 | 17 | 0 | -3143.55
TSK-0318 | PRJ-1018 | Human Resources System Implementation 18 | Human Resources | System Implementation | Riley Chen | Execution | Execution Task 11 | High | Low | Summit Partners | 2025-02-04 | 2025-03-03 |  | On Hold | 20% | 26500 | 29903.61 | 1 |  | 0 | -3403.61
TSK-0319 | PRJ-1019 | Facilities Cost Reduction 19 | Facilities | Cost Reduction | Avery Brooks | Testing | Testing Task 11 | Critical | High | Internal Team | 2025-04-23 | 2025-05-14 |  | In Progress | 85% | 31800 | 34743.5 | 3 |  | 0 | -2943.5
TSK-0320 | PRJ-1020 | Marketing Automation 20 | Marketing | Automation | Jordan Lee | Training | Training Task 11 | High | High | Apex Solutions | 2025-09-18 | 2025-09-27 | 2025-10-06 | Completed | 100% | 25100 | 20052.92 | 3 | 9 | 0 | 5047.08
TSK-0321 | PRJ-1021 | Procurement Process Improvement 21 | Procurement | Process Improvement | Morgan Patel | Launch | Launch Task 11 | Low | Medium | Internal Team | 2025-09-04 | 2025-09-07 |  | In Progress | 75% | 10300 | 10787.36 | 3 |  | 0 | -487.36
TSK-0322 | PRJ-1022 | Operations Facility Upgrade 22 | Operations | Facility Upgrade | Taylor Reed | Closeout | Closeout Task 11 | Critical | Medium | Internal Team | 2025-09-26 | 2025-10-03 | 2025-10-13 | Completed | 100% | 41400 | 43572.5 | 0 | 10 | 0 | -2172.5
TSK-0323 | PRJ-1023 | Technology Compliance 23 | Technology | Compliance | Cameron Diaz | Discovery | Discovery Task 11 | High | High | Internal Team | 2026-02-19 | 2026-03-12 |  | Not Started | 0% | 14600 | 0 | 4 |  | 0 | 14600
TSK-0324 | PRJ-1024 | Finance Vendor Transition 24 | Finance | Vendor Transition | Riley Chen | Planning | Planning Task 11 | Critical | Medium | BluePeak Services | 2025-04-10 | 2025-04-18 | 2025-04-06 | Completed | 100% | 28200 | 26291.66 | 1 | 0 | 0 | 1908.34
TSK-0325 | PRJ-1025 | Human Resources System Implementation 25 | Human Resources | System Implementation | Avery Brooks | Requirements | Requirements Task 11 | High | Low | Vertex Systems | 2026-01-03 | 2026-01-10 |  | Not Started | 0% | 1600 | 0 | 1 |  | 0 | 1600
TSK-0326 | PRJ-1026 | Facilities Cost Reduction 26 | Facilities | Cost Reduction | Jordan Lee | Configuration | Configuration Task 11 | High | Medium | Apex Solutions | 2025-06-02 | 2025-06-24 |  | In Progress | 90% | 43600 | 38498.87 | 2 |  | 0 | 5101.13
TSK-0327 | PRJ-1027 | Marketing Automation 27 | Marketing | Automation | Morgan Patel | Execution | Execution Task 11 | Critical | Low | Vertex Systems | 2026-03-08 | 2026-03-22 |  | On Hold | 20% | 29200 | 33862.37 | 4 |  | 0 | -4662.37
TSK-0328 | PRJ-1028 | Procurement Process Improvement 28 | Procurement | Process Improvement | Taylor Reed | Testing | Testing Task 11 | High | Medium | Internal Team | 2025-12-06 | 2025-12-17 |  | In Progress | 85% | 4400 | 4281.38 | 2 |  | 0 | 118.62
TSK-0329 | PRJ-1029 | Operations Facility Upgrade 29 | Operations | Facility Upgrade | Cameron Diaz | Training | Training Task 11 | Low | Low | Vertex Systems | 2026-02-11 | 2026-02-27 | 2026-03-04 | Completed | 100% | 18000 | 17482.29 | 1 | 5 | 0 | 517.71
TSK-0330 | PRJ-1030 | Technology Compliance 30 | Technology | Compliance | Riley Chen | Closeout | Closeout Task 11 | Medium | High | Northstar Consulting | 2025-12-08 | 2025-12-16 |  | In Progress | 90% | 38300 | 39953.27 | 4 |  | 0 | -1653.27
TSK-0331 | PRJ-1001 | Operations Facility Upgrade 01 | Operations | Facility Upgrade | Avery Brooks | Discovery | Discovery Task 12 | Critical | Low | Internal Team | 2026-03-05 | 2026-03-13 | 2026-03-01 | Completed | 100% | 5600 | 5328.46 | 0 | 0 | 0 | 271.54
TSK-0332 | PRJ-1002 | Technology Compliance 02 | Technology | Compliance | Jordan Lee | Planning | Planning Task 12 | Medium | Low | BluePeak Services | 2025-04-15 | 2025-05-07 | 2025-05-04 | Completed | 100% | 8300 | 8964.19 | 2 | 0 | 0 | -664.19
TSK-0333 | PRJ-1003 | Finance Vendor Transition 03 | Finance | Vendor Transition | Morgan Patel | Requirements | Requirements Task 12 | Medium | Medium | Vertex Systems | 2025-06-05 | 2025-06-16 | 2025-06-17 | Completed | 100% | 18600 | 19850.35 | 0 | 1 | 0 | -1250.35
TSK-0334 | PRJ-1004 | Human Resources System Implementation 04 | Human Resources | System Implementation | Taylor Reed | Configuration | Configuration Task 12 | Low | Low | Internal Team | 2026-05-22 | 2026-05-31 |  | Completed | 0% | 10500 | 0 | 0 |  | 0 | 10500
TSK-0335 | PRJ-1005 | Facilities Cost Reduction 05 | Facilities | Cost Reduction | Cameron Diaz | Execution | Execution Task 12 | Medium | Low | Vertex Systems | 2025-09-23 | 2025-10-11 | 2025-09-28 | Completed | 100% | 13000 | 12370.27 | 0 | 0 | 0 | 629.73
TSK-0336 | PRJ-1006 | Marketing Automation 06 | Marketing | Automation | Riley Chen | Testing | Testing Task 12 | Medium | Low | Internal Team | 2025-05-22 | 2025-06-02 |  | Completed | 50% | 11300 | 11474.41 | 2 |  | 0 | -174.41
TSK-0337 | PRJ-1007 | Procurement Process Improvement 07 | Procurement | Process Improvement | Avery Brooks | Training | Training Task 12 | High | Medium | Internal Team | 2025-07-27 | 2025-08-24 | 2025-09-04 | Completed | 100% | 25600 | 25424.01 | 3 | 11 | 0 | 175.99
TSK-0338 | PRJ-1008 | Operations Facility Upgrade 08 | Operations | Facility Upgrade | Jordan Lee | Launch | Launch Task 12 | Medium | Medium | Summit Partners | 2025-07-17 | 2025-08-07 | 2025-07-29 | Completed | 100% | 22200 | 27280.82 | 3 | 0 | 0 | -5080.82
TSK-0339 | PRJ-1009 | Technology Compliance 09 | Technology | Compliance | Morgan Patel | Closeout | Closeout Task 12 | High | Low | BluePeak Services | 2026-06-13 | 2026-07-07 |  | In Progress | 20% | 6700 | 6854.5 | 0 |  | 0 | -154.5
TSK-0340 | PRJ-1010 | Finance Vendor Transition 10 | Finance | Vendor Transition | Taylor Reed | Discovery | Discovery Task 12 | Critical | High | Summit Partners | 2025-03-31 | 2025-04-04 |  | In Progress | 85% | 20400 | 24979.99 | 3 |  | 0 | -4579.99
TSK-0341 | PRJ-1011 | Human Resources System Implementation 11 | Human Resources | System Implementation | Cameron Diaz | Planning | Planning Task 12 | High | Low | BluePeak Services | 2026-01-04 | 2026-01-09 |  | In Progress | 60% | 25500 | 28119.32 | 0 |  | 0 | -2619.32
TSK-0342 | PRJ-1012 | Facilities Cost Reduction 12 | Facilities | Cost Reduction | Riley Chen | Requirements | Requirements Task 12 | Critical | Low | Vertex Systems | 2026-06-19 | 2026-07-08 | 2026-07-13 | Completed | 100% | 26100 | 27683.8 | 0 | 5 | 0 | -1583.8
TSK-0343 | PRJ-1013 | Marketing Automation 13 | Marketing | Automation | Avery Brooks | Configuration | Configuration Task 12 | Low | Low | Vertex Systems | 2025-12-24 | 2026-01-23 | 2026-01-16 | Completed | 100% | 16500 | 15318.57 | 2 | 0 | 0 | 1181.43
TSK-0344 | PRJ-1014 | Procurement Process Improvement 14 | Procurement | Process Improvement | Jordan Lee | Execution | Execution Task 12 | Medium | Medium | Internal Team | 2025-04-30 | 2025-05-15 |  | Not Started | 0% | 28000 | 0 | 1 |  | 0 | 28000
TSK-0345 | PRJ-1015 | Operations Facility Upgrade 15 | Operations | Facility Upgrade | Morgan Patel | Testing | Testing Task 12 | High | Low | Internal Team | 2026-03-05 | 2026-03-16 | 2026-03-31 | Completed | 100% | 14700 | 15372.06 | 1 | 15 | 0 | -672.06
TSK-0346 | PRJ-1016 | Technology Compliance 16 | Technology | Compliance | Taylor Reed | Training | Training Task 12 | High | Low | Summit Partners | 2025-09-13 | 2025-09-25 |  | On Hold | 50% | 35200 | 40326.31 | 0 |  | 0 | -5126.31
TSK-0347 | PRJ-1017 | Finance Vendor Transition 17 | Finance | Vendor Transition | Cameron Diaz | Launch | Launch Task 12 | High | Low | Internal Team | 2025-05-06 | 2025-06-01 | 2025-06-13 | Completed | 100% | 24000 | 23849.4 | 2 | 12 | 0 | 150.6
TSK-0348 | PRJ-1018 | Human Resources System Implementation 18 | Human Resources | System Implementation | Riley Chen | Closeout | Closeout Task 12 | High | Low | Vertex Systems | 2025-05-04 | 2025-05-11 | 2025-05-04 | Completed | 100% | 9100 | 9084.68 | 2 | 0 | 0 | 15.32
TSK-0349 | PRJ-1019 | Facilities Cost Reduction 19 | Facilities | Cost Reduction | Avery Brooks | Discovery | Discovery Task 12 | Low | Low | Internal Team | 2025-05-25 | 2025-06-19 |  | In Progress | 50% | 37300 | 36106.08 | 0 |  | 0 | 1193.92
TSK-0350 | PRJ-1020 | Marketing Automation 20 | Marketing | Automation | Jordan Lee | Planning | Planning Task 12 | Medium | Low | Internal Team | 2025-08-19 | 2025-08-27 |  | On Hold | 50% | 27000 | 27404.13 | 1 |  | 0 | -404.13
TSK-0351 | PRJ-1021 | Procurement Process Improvement 21 | Procurement | Process Improvement | Morgan Patel | Requirements | Requirements Task 12 | High | Medium | Vertex Systems | 2025-07-16 | 2025-07-19 |  | In Progress | 40% | 38600 | 41426.95 | 2 |  | 0 | -2826.95
TSK-0352 | PRJ-1022 | Operations Facility Upgrade 22 | Operations | Facility Upgrade | Taylor Reed | Configuration | Configuration Task 12 | Medium | Low | Internal Team | 2026-01-03 | 2026-01-22 |  | Not Started | 0% | 35400 | 0 | 1 |  | 0 | 35400
TSK-0353 | PRJ-1023 | Technology Compliance 23 | Technology | Compliance | Cameron Diaz | Execution | Execution Task 12 | Critical | Medium | Northstar Consulting | 2025-11-12 | 2025-11-22 |  | In Progress | 90% | 42500 | 42728.76 | 1 |  | 0 | -228.76
TSK-0354 | PRJ-1024 | Finance Vendor Transition 24 | Finance | Vendor Transition | Riley Chen | Testing | Testing Task 12 | Medium | High | Summit Partners | 2025-05-16 | 2025-05-27 |  | In Progress | 50% | 31000 | 27955.48 | 4 |  | 0 | 3044.52
TSK-0355 | PRJ-1025 | Human Resources System Implementation 25 | Human Resources | System Implementation | Avery Brooks | Training | Training Task 12 | Low | Low | Northstar Consulting | 2026-01-23 | 2026-02-12 | 2026-02-08 | Completed | 100% | 28000 | 28118.16 | 2 | 0 | 0 | -118.16
TSK-0356 | PRJ-1026 | Facilities Cost Reduction 26 | Facilities | Cost Reduction | Jordan Lee | Launch | Launch Task 12 | Low | High | Northstar Consulting | 2025-06-26 | 2025-07-07 | 2025-07-19 | Completed | 100% | 9700 | 9920.57 | 2 | 12 | 0 | -220.57
TSK-0357 | PRJ-1027 | Marketing Automation 27 | Marketing | Automation | Morgan Patel | Closeout | Closeout Task 12 | Low | High | Summit Partners | 2026-04-20 | 2026-05-14 |  | In Progress | 40% | 32900 | 34912.03 | 0 |  | 0 | -2012.03
TSK-0358 | PRJ-1028 | Procurement Process Improvement 28 | Procurement | Process Improvement | Taylor Reed | Discovery | Discovery Task 12 | Medium | Low | Internal Team | 2025-12-13 | 2026-01-03 | 2025-12-16 | Completed | 100% | 26400 | 28651.85 | 3 | 0 | 0 | -2251.85
TSK-0359 | PRJ-1029 | Operations Facility Upgrade 29 | Operations | Facility Upgrade | Cameron Diaz | Planning | Planning Task 12 | Medium | Medium | Vertex Systems | 2026-04-01 | 2026-04-20 |  | In Progress | 40% | 38100 | 40753.02 | 1 |  | 0 | -2653.02
TSK-0360 | PRJ-1030 | Technology Compliance 30 | Technology | Compliance | Riley Chen | Configuration | Configuration Task 12 | Low | Low | Internal Team | 2026-03-04 | 2026-03-31 | 2026-04-16 | Completed | 100% | 30000 | 28283.91 | 1 | 16 | 0 | 1716.09
TSK-0361 | PRJ-1001 | Operations Facility Upgrade 01 | Operations | Facility Upgrade | Avery Brooks | Execution | Execution Task 13 | High | Low | Summit Partners | 2026-03-04 | 2026-03-15 | 2026-03-22 | Completed | 100% | 21700 | 22719.52 | 1 | 7 | 0 | -1019.52
TSK-0362 | PRJ-1002 | Technology Compliance 02 | Technology | Compliance | Jordan Lee | Testing | Testing Task 13 | High | Medium | Northstar Consulting | 2025-07-02 | 2025-07-11 | 2025-07-18 | Completed | 100% | 14500 | 13633.23 | 4 | 7 | 0 | 866.77
TSK-0363 | PRJ-1003 | Finance Vendor Transition 03 | Finance | Vendor Transition | Morgan Patel | Training | Training Task 13 | Medium | Low | Internal Team | 2025-06-12 | 2025-06-29 |  | Completed | 0% | 39000 | 0 | 1 |  | 0 | 39000
TSK-0364 | PRJ-1004 | Human Resources System Implementation 04 | Human Resources | System Implementation | Taylor Reed | Launch | Launch Task 13 | Medium | High | Internal Team | 2026-02-03 | 2026-02-06 |  | Completed | 40% | 34600 | 38437.23 | 4 |  | 0 | -3837.23
TSK-0365 | PRJ-1005 | Facilities Cost Reduction 05 | Facilities | Cost Reduction | Cameron Diaz | Closeout | Closeout Task 13 | Medium | Medium | Internal Team | 2025-09-14 | 2025-10-07 |  | Completed | 60% | 43500 | 51466.11 | 1 |  | 0 | -7966.11
TSK-0366 | PRJ-1006 | Marketing Automation 06 | Marketing | Automation | Riley Chen | Discovery | Discovery Task 13 | Medium | Low | Internal Team | 2025-08-01 | 2025-08-28 | 2025-08-31 | Completed | 100% | 9800 | 9323.83 | 0 | 3 | 0 | 476.17
TSK-0367 | PRJ-1007 | Procurement Process Improvement 07 | Procurement | Process Improvement | Avery Brooks | Planning | Planning Task 13 | Medium | Medium | Internal Team | 2025-06-02 | 2025-06-08 |  | Completed | 75% | 14800 | 15552.73 | 2 |  | 0 | -752.73
TSK-0368 | PRJ-1008 | Operations Facility Upgrade 08 | Operations | Facility Upgrade | Jordan Lee | Requirements | Requirements Task 13 | Critical | Low | Apex Solutions | 2025-07-30 | 2025-08-12 |  | Completed | 85% | 44800 | 39859.4 | 4 |  | 0 | 4940.6
TSK-0369 | PRJ-1009 | Technology Compliance 09 | Technology | Compliance | Morgan Patel | Configuration | Configuration Task 13 | Medium | Low | BluePeak Services | 2026-05-01 | 2026-05-04 |  | In Progress | 85% | 44300 | 45433.67 | 1 |  | 0 | -1133.67
TSK-0370 | PRJ-1010 | Finance Vendor Transition 10 | Finance | Vendor Transition | Taylor Reed | Execution | Execution Task 13 | Medium | Low | Vertex Systems | 2025-03-08 | 2025-03-23 | 2025-03-25 | Completed | 100% | 3600 | 4161.55 | 3 | 2 | 0 | -561.55
TSK-0371 | PRJ-1011 | Human Resources System Implementation 11 | Human Resources | System Implementation | Cameron Diaz | Testing | Testing Task 13 | High | Low | Vertex Systems | 2026-04-03 | 2026-04-20 |  | In Progress | 75% | 12500 | 12682.32 | 1 |  | 0 | -182.32
TSK-0372 | PRJ-1012 | Facilities Cost Reduction 12 | Facilities | Cost Reduction | Riley Chen | Training | Training Task 13 | High | Low | Internal Team | 2026-02-14 | 2026-03-10 | 2026-03-07 | Completed | 100% | 28600 | 28173.4 | 0 | 0 | 0 | 426.6
TSK-0373 | PRJ-1013 | Marketing Automation 13 | Marketing | Automation | Avery Brooks | Launch | Launch Task 13 | High | Low | Northstar Consulting | 2025-12-23 | 2025-12-29 | 2025-12-21 | Completed | 100% | 35300 | 36081.59 | 3 | 0 | 0 | -781.59
TSK-0374 | PRJ-1014 | Procurement Process Improvement 14 | Procurement | Process Improvement | Jordan Lee | Closeout | Closeout Task 13 | Medium | Low | Internal Team | 2025-07-09 | 2025-07-27 | 2025-07-13 | Completed | 100% | 31400 | 29521.49 | 1 | 0 | 0 | 1878.51
TSK-0375 | PRJ-1015 | Operations Facility Upgrade 15 | Operations | Facility Upgrade | Morgan Patel | Discovery | Discovery Task 13 | Low | Low | Internal Team | 2026-03-30 | 2026-04-23 | 2026-05-07 | Completed | 100% | 4800 | 4609.23 | 1 | 14 | 0 | 190.77
TSK-0376 | PRJ-1016 | Technology Compliance 16 | Technology | Compliance | Taylor Reed | Planning | Planning Task 13 | High | Low | BluePeak Services | 2025-10-16 | 2025-11-02 |  | Not Started | 0% | 36900 | 0 | 3 |  | 0 | 36900
TSK-0377 | PRJ-1017 | Finance Vendor Transition 17 | Finance | Vendor Transition | Cameron Diaz | Requirements | Requirements Task 13 | Medium | Medium | Internal Team | 2025-02-20 | 2025-02-26 | 2025-02-18 | Completed | 100% | 40200 | 43413.14 | 2 | 0 | 0 | -3213.14
TSK-0378 | PRJ-1018 | Human Resources System Implementation 18 | Human Resources | System Implementation | Riley Chen | Configuration | Configuration Task 13 | High | Low | BluePeak Services | 2025-03-30 | 2025-04-25 |  | Not Started | 0% | 37000 | 0 | 2 |  | 0 | 37000
TSK-0379 | PRJ-1019 | Facilities Cost Reduction 19 | Facilities | Cost Reduction | Avery Brooks | Execution | Execution Task 13 | Critical | Low | Internal Team | 2025-06-24 | 2025-07-22 |  | In Progress | 90% | 8800 | 10024.82 | 3 |  | 0 | -1224.82
TSK-0380 | PRJ-1020 | Marketing Automation 20 | Marketing | Automation | Jordan Lee | Testing | Testing Task 13 | Critical | Medium | Internal Team | 2025-08-28 | 2025-09-25 | 2025-09-18 | Completed | 100% | 35400 | 38136.04 | 0 | 0 | 0 | -2736.04
TSK-0381 | PRJ-1021 | Procurement Process Improvement 21 | Procurement | Process Improvement | Morgan Patel | Training | Training Task 13 | High | Medium | BluePeak Services | 2025-09-05 | 2025-09-23 |  | Not Started | 0% | 19400 | 0 | 3 |  | 0 | 19400
TSK-0382 | PRJ-1022 | Operations Facility Upgrade 22 | Operations | Facility Upgrade | Taylor Reed | Launch | Launch Task 13 | Medium | Medium | Vertex Systems | 2026-02-15 | 2026-03-13 | 2026-03-17 | Completed | 100% | 44000 | 42757.23 | 1 | 4 | 0 | 1242.77
TSK-0383 | PRJ-1023 | Technology Compliance 23 | Technology | Compliance | Cameron Diaz | Closeout | Closeout Task 13 | Medium | Medium | Internal Team | 2026-01-12 | 2026-01-30 |  | In Progress | 85% | 29400 | 33586.76 | 4 |  | 0 | -4186.76
TSK-0384 | PRJ-1024 | Finance Vendor Transition 24 | Finance | Vendor Transition | Riley Chen | Discovery | Discovery Task 13 | High | Medium | Internal Team | 2025-02-28 | 2025-03-19 | 2025-03-29 | Completed | 100% | 4800 | 4041.5 | 1 | 10 | 0 | 758.5
TSK-0385 | PRJ-1025 | Human Resources System Implementation 25 | Human Resources | System Implementation | Avery Brooks | Planning | Planning Task 13 | Critical | Low | Internal Team | 2026-01-24 | 2026-02-08 | 2026-02-10 | Completed | 100% | 4900 | 4337.59 | 2 | 2 | 0 | 562.41
TSK-0386 | PRJ-1026 | Facilities Cost Reduction 26 | Facilities | Cost Reduction | Jordan Lee | Requirements | Requirements Task 13 | Low | Low | Internal Team | 2025-08-22 | 2025-09-17 | 2025-09-25 | Completed | 100% | 25700 | 27966.31 | 2 | 8 | 0 | -2266.31
TSK-0387 | PRJ-1027 | Marketing Automation 27 | Marketing | Automation | Morgan Patel | Configuration | Configuration Task 13 | High | Medium | Internal Team | 2026-05-17 | 2026-06-06 |  | In Progress | 85% | 21300 | 21727.09 | 0 |  | 0 | -427.09
TSK-0388 | PRJ-1028 | Procurement Process Improvement 28 | Procurement | Process Improvement | Taylor Reed | Execution | Execution Task 13 | High | Medium | Internal Team | 2026-04-04 | 2026-04-29 | 2026-05-12 | Completed | 100% | 32600 | 37816.41 | 3 | 13 | 0 | -5216.41
TSK-0389 | PRJ-1029 | Operations Facility Upgrade 29 | Operations | Facility Upgrade | Cameron Diaz | Testing | Testing Task 13 | Medium | Low | Summit Partners | 2026-03-15 | 2026-04-04 | 2026-04-05 | Completed | 100% | 8600 | 8495.42 | 3 | 1 | 0 | 104.58
TSK-0390 | PRJ-1030 | Technology Compliance 30 | Technology | Compliance | Riley Chen | Launch | Launch Task 13 | High | Low | Northstar Consulting | 2025-11-29 | 2025-12-05 | 2025-12-16 | Completed | 100% | 18600 | 15533.13 | 2 | 11 | 0 | 3066.87
TSK-0391 | PRJ-1001 | Operations Facility Upgrade 01 | Operations | Facility Upgrade | Avery Brooks | Closeout | Closeout Task 14 | High | Low | Internal Team | 2026-04-28 | 2026-05-04 | 2026-04-26 | Completed | 100% | 43100 | 46088.5 | 2 | 0 | 0 | -2988.5
TSK-0392 | PRJ-1002 | Technology Compliance 02 | Technology | Compliance | Jordan Lee | Discovery | Discovery Task 14 | Medium | Low | BluePeak Services | 2025-07-31 | 2025-08-18 | 2025-08-26 | Completed | 100% | 35500 | 41272.45 | 0 | 8 | 0 | -5772.45
TSK-0393 | PRJ-1003 | Finance Vendor Transition 03 | Finance | Vendor Transition | Morgan Patel | Planning | Planning Task 14 | Medium | Medium | Internal Team | 2025-04-10 | 2025-04-29 | 2025-04-23 | Completed | 100% | 31600 | 34561.82 | 2 | 0 | 0 | -2961.82
TSK-0394 | PRJ-1004 | Human Resources System Implementation 04 | Human Resources | System Implementation | Taylor Reed | Requirements | Requirements Task 14 | Medium | Low | Summit Partners | 2026-02-24 | 2026-03-12 | 2026-03-21 | Completed | 100% | 40100 | 32438.04 | 1 | 9 | 0 | 7661.96
TSK-0395 | PRJ-1005 | Facilities Cost Reduction 05 | Facilities | Cost Reduction | Cameron Diaz | Configuration | Configuration Task 14 | Medium | Low | Vertex Systems | 2025-10-14 | 2025-11-06 |  | Completed | 40% | 28700 | 28541.14 | 2 |  | 0 | 158.86
TSK-0396 | PRJ-1006 | Marketing Automation 06 | Marketing | Automation | Riley Chen | Execution | Execution Task 14 | High | High | Northstar Consulting | 2025-06-25 | 2025-07-14 | 2025-07-09 | Completed | 100% | 34600 | 32481.28 | 1 | 0 | 0 | 2118.72
TSK-0397 | PRJ-1007 | Procurement Process Improvement 07 | Procurement | Process Improvement | Avery Brooks | Testing | Testing Task 14 | Critical | Medium | Vertex Systems | 2025-09-13 | 2025-09-25 | 2025-09-23 | Completed | 100% | 19900 | 21333.34 | 2 | 0 | 0 | -1433.34
TSK-0398 | PRJ-1008 | Operations Facility Upgrade 08 | Operations | Facility Upgrade | Jordan Lee | Training | Training Task 14 | Medium | Low | Internal Team | 2025-05-25 | 2025-06-21 | 2025-07-04 | Completed | 100% | 7900 | 7921.88 | 3 | 13 | 0 | -21.88
TSK-0399 | PRJ-1009 | Technology Compliance 09 | Technology | Compliance | Morgan Patel | Launch | Launch Task 14 | Medium | Medium | Internal Team | 2026-05-13 | 2026-05-19 | 2026-05-26 | Completed | 100% | 30900 | 29276.24 | 1 | 7 | 0 | 1623.76
TSK-0400 | PRJ-1010 | Finance Vendor Transition 10 | Finance | Vendor Transition | Taylor Reed | Closeout | Closeout Task 14 | High | Low | Apex Solutions | 2025-05-11 | 2025-06-05 | 2025-06-13 | Completed | 100% | 43100 | 41869.74 | 2 | 8 | 0 | 1230.26
TSK-0401 | PRJ-1011 | Human Resources System Implementation 11 | Human Resources | System Implementation | Cameron Diaz | Discovery | Discovery Task 14 | Medium | Low | Internal Team | 2026-04-10 | 2026-05-09 |  | In Progress | 85% | 32200 | 32379.86 | 0 |  | 0 | -179.86
TSK-0402 | PRJ-1012 | Facilities Cost Reduction 12 | Facilities | Cost Reduction | Riley Chen | Planning | Planning Task 14 | Medium | Medium | Vertex Systems | 2026-03-10 | 2026-03-22 |  | In Progress | 85% | 4700 | 4100.04 | 4 |  | 0 | 599.96
TSK-0403 | PRJ-1013 | Marketing Automation 13 | Marketing | Automation | Avery Brooks | Requirements | Requirements Task 14 | Low | Low | Internal Team | 2025-12-18 | 2025-12-25 |  | Not Started | 0% | 38300 | 0 | 3 |  | 0 | 38300
TSK-0404 | PRJ-1014 | Procurement Process Improvement 14 | Procurement | Process Improvement | Jordan Lee | Configuration | Configuration Task 14 | Critical | Low | BluePeak Services | 2025-03-04 | 2025-03-31 | 2025-04-02 | Completed | 100% | 28300 | 26965.14 | 0 | 2 | 0 | 1334.86
TSK-0405 | PRJ-1015 | Operations Facility Upgrade 15 | Operations | Facility Upgrade | Morgan Patel | Execution | Execution Task 14 | High | Low | Vertex Systems | 2026-01-24 | 2026-02-12 |  | In Progress | 40% | 24100 | 24934.8 | 0 |  | 0 | -834.8
TSK-0406 | PRJ-1016 | Technology Compliance 16 | Technology | Compliance | Taylor Reed | Testing | Testing Task 14 | Medium | Low | Internal Team | 2025-10-03 | 2025-10-27 |  | In Progress | 50% | 14300 | 16663.55 | 1 |  | 0 | -2363.55
TSK-0407 | PRJ-1017 | Finance Vendor Transition 17 | Finance | Vendor Transition | Cameron Diaz | Training | Training Task 14 | Medium | Medium | Vertex Systems | 2025-01-24 | 2025-01-30 | 2025-01-18 | Completed | 100% | 28200 | 31014.78 | 0 | 0 | 0 | -2814.78
TSK-0408 | PRJ-1018 | Human Resources System Implementation 18 | Human Resources | System Implementation | Riley Chen | Launch | Launch Task 14 | High | Low | BluePeak Services | 2025-02-19 | 2025-03-06 |  | In Progress | 85% | 13800 | 11430.76 | 3 |  | 0 | 2369.24
TSK-0409 | PRJ-1019 | Facilities Cost Reduction 19 | Facilities | Cost Reduction | Avery Brooks | Closeout | Closeout Task 14 | Medium | Medium | Internal Team | 2025-03-05 | 2025-03-17 | 2025-03-12 | Completed | 100% | 9900 | 7458.18 | 1 | 0 | 0 | 2441.82
TSK-0410 | PRJ-1020 | Marketing Automation 20 | Marketing | Automation | Jordan Lee | Discovery | Discovery Task 14 | Medium | High | Apex Solutions | 2025-04-28 | 2025-05-21 |  | Not Started | 0% | 30700 | 0 | 0 |  | 0 | 30700
TSK-0411 | PRJ-1021 | Procurement Process Improvement 21 | Procurement | Process Improvement | Morgan Patel | Planning | Planning Task 14 | Medium | Low | Apex Solutions | 2025-08-24 | 2025-09-16 | 2025-09-28 | Completed | 100% | 2500 | 2733.26 | 1 | 12 | 0 | -233.26
TSK-0412 | PRJ-1022 | Operations Facility Upgrade 22 | Operations | Facility Upgrade | Taylor Reed | Requirements | Requirements Task 14 | Low | Low | Internal Team | 2025-10-09 | 2025-10-30 | 2025-10-30 | Completed | 100% | 41100 | 37780.79 | 2 | 0 | 0 | 3319.21
TSK-0413 | PRJ-1023 | Technology Compliance 23 | Technology | Compliance | Cameron Diaz | Configuration | Configuration Task 14 | Medium | Low | Internal Team | 2025-12-10 | 2025-12-30 |  | Not Started | 0% | 32800 | 0 | 2 |  | 0 | 32800
TSK-0414 | PRJ-1024 | Finance Vendor Transition 24 | Finance | Vendor Transition | Riley Chen | Execution | Execution Task 14 | Low | Medium | Internal Team | 2025-05-27 | 2025-06-02 |  | In Progress | 85% | 14600 | 17232.25 | 3 |  | 0 | -2632.25
TSK-0415 | PRJ-1025 | Human Resources System Implementation 25 | Human Resources | System Implementation | Avery Brooks | Testing | Testing Task 14 | Medium | Low | Northstar Consulting | 2026-02-18 | 2026-02-26 | 2026-03-05 | Completed | 100% | 36200 | 39921.4 | 0 | 7 | 0 | -3721.4
TSK-0416 | PRJ-1026 | Facilities Cost Reduction 26 | Facilities | Cost Reduction | Jordan Lee | Training | Training Task 14 | Medium | Medium | BluePeak Services | 2025-07-21 | 2025-07-24 | 2025-07-21 | Completed | 100% | 25600 | 26314.17 | 2 | 0 | 0 | -714.17
TSK-0417 | PRJ-1027 | Marketing Automation 27 | Marketing | Automation | Morgan Patel | Launch | Launch Task 14 | High | Medium | BluePeak Services | 2026-03-26 | 2026-04-04 | 2026-04-11 | Completed | 100% | 19500 | 18768.36 | 1 | 7 | 0 | 731.64
TSK-0418 | PRJ-1028 | Procurement Process Improvement 28 | Procurement | Process Improvement | Taylor Reed | Closeout | Closeout Task 14 | Medium | Low | Summit Partners | 2026-01-22 | 2026-01-28 |  | In Progress | 90% | 26200 | 23981.69 | 3 |  | 0 | 2218.31
TSK-0419 | PRJ-1029 | Operations Facility Upgrade 29 | Operations | Facility Upgrade | Cameron Diaz | Discovery | Discovery Task 14 | Critical | Medium | Northstar Consulting | 2026-01-18 | 2026-01-30 | 2026-02-05 | Completed | 100% | 12400 | 13231.32 | 3 | 6 | 0 | -831.32
TSK-0420 | PRJ-1030 | Technology Compliance 30 | Technology | Compliance | Riley Chen | Requirements | Requirements Task 14 | Critical | Low | Vertex Systems | 2025-12-11 | 2025-12-17 |  | In Progress | 25% | 40700 | 39489.45 | 2 |  | 0 | 1210.55
TSK-0421 | PRJ-1001 | Operations Facility Upgrade 01 | Operations | Facility Upgrade | Avery Brooks | Configuration | Configuration Task 15 | High | Low | Northstar Consulting | 2026-04-22 | 2026-05-13 |  | Completed | 50% | 43200 | 46079.31 | 2 |  | 0 | -2879.31
TSK-0422 | PRJ-1002 | Technology Compliance 02 | Technology | Compliance | Jordan Lee | Execution | Execution Task 15 | High | Medium | Northstar Consulting | 2025-05-13 | 2025-06-11 |  | Completed | 85% | 33400 | 37016.39 | 1 |  | 0 | -3616.39
TSK-0423 | PRJ-1003 | Finance Vendor Transition 03 | Finance | Vendor Transition | Morgan Patel | Testing | Testing Task 15 | Medium | Low | Apex Solutions | 2025-03-03 | 2025-03-26 | 2025-04-05 | Completed | 100% | 7600 | 6365.63 | 0 | 10 | 0 | 1234.37
TSK-0424 | PRJ-1004 | Human Resources System Implementation 04 | Human Resources | System Implementation | Taylor Reed | Training | Training Task 15 | High | Low | Internal Team | 2026-01-24 | 2026-02-23 | 2026-02-24 | Completed | 100% | 2900 | 2674.96 | 1 | 1 | 0 | 225.04
TSK-0425 | PRJ-1005 | Facilities Cost Reduction 05 | Facilities | Cost Reduction | Cameron Diaz | Launch | Launch Task 15 | High | High | Apex Solutions | 2025-10-12 | 2025-11-01 | 2025-11-04 | Completed | 100% | 11200 | 10822.91 | 3 | 3 | 0 | 377.09
TSK-0426 | PRJ-1006 | Marketing Automation 06 | Marketing | Automation | Riley Chen | Closeout | Closeout Task 15 | Medium | Low | Apex Solutions | 2025-08-20 | 2025-09-03 | 2025-08-25 | Completed | 100% | 30300 | 34394.7 | 0 | 0 | 0 | -4094.7
TSK-0427 | PRJ-1007 | Procurement Process Improvement 07 | Procurement | Process Improvement | Avery Brooks | Discovery | Discovery Task 15 | High | Low | Apex Solutions | 2025-08-22 | 2025-08-30 |  | Completed | 0% | 42800 | 0 | 0 |  | 0 | 42800
TSK-0428 | PRJ-1008 | Operations Facility Upgrade 08 | Operations | Facility Upgrade | Jordan Lee | Planning | Planning Task 15 | High | Low | Internal Team | 2025-05-13 | 2025-06-09 | 2025-06-17 | Completed | 100% | 3400 | 3606.2 | 2 | 8 | 0 | -206.2
TSK-0429 | PRJ-1009 | Technology Compliance 09 | Technology | Compliance | Morgan Patel | Requirements | Requirements Task 15 | Medium | Low | Apex Solutions | 2026-01-29 | 2026-02-02 |  | In Progress | 30% | 6000 | 7508.04 | 3 |  | 0 | -1508.04
TSK-0430 | PRJ-1010 | Finance Vendor Transition 10 | Finance | Vendor Transition | Taylor Reed | Configuration | Configuration Task 15 | Medium | Medium | Northstar Consulting | 2025-07-22 | 2025-07-30 |  | In Progress | 60% | 17400 | 17213.73 | 0 |  | 0 | 186.27
TSK-0431 | PRJ-1011 | Human Resources System Implementation 11 | Human Resources | System Implementation | Cameron Diaz | Execution | Execution Task 15 | Medium | Low | BluePeak Services | 2026-04-29 | 2026-05-14 |  | In Progress | 90% | 16500 | 13998.5 | 2 |  | 0 | 2501.5
TSK-0432 | PRJ-1012 | Facilities Cost Reduction 12 | Facilities | Cost Reduction | Riley Chen | Testing | Testing Task 15 | Low | High | Internal Team | 2026-03-19 | 2026-03-24 | 2026-03-12 | Completed | 100% | 13700 | 15176.26 | 4 | 0 | 0 | -1476.26
TSK-0433 | PRJ-1013 | Marketing Automation 13 | Marketing | Automation | Avery Brooks | Training | Training Task 15 | High | Medium | Northstar Consulting | 2026-01-26 | 2026-02-23 |  | In Progress | 25% | 22400 | 21167.97 | 2 |  | 0 | 1232.03
TSK-0434 | PRJ-1014 | Procurement Process Improvement 14 | Procurement | Process Improvement | Jordan Lee | Launch | Launch Task 15 | Medium | Medium | Internal Team | 2025-03-02 | 2025-03-09 | 2025-03-16 | Completed | 100% | 3200 | 3684.71 | 1 | 7 | 0 | -484.71
TSK-0435 | PRJ-1015 | Operations Facility Upgrade 15 | Operations | Facility Upgrade | Morgan Patel | Closeout | Closeout Task 15 | Medium | Low | BluePeak Services | 2026-03-28 | 2026-04-20 |  | Not Started | 0% | 32800 | 0 | 1 |  | 0 | 32800
TSK-0436 | PRJ-1016 | Technology Compliance 16 | Technology | Compliance | Taylor Reed | Discovery | Discovery Task 15 | Low | Low | BluePeak Services | 2025-12-11 | 2025-12-19 |  | In Progress | 60% | 27600 | 26044.63 | 2 |  | 0 | 1555.37
TSK-0437 | PRJ-1017 | Finance Vendor Transition 17 | Finance | Vendor Transition | Cameron Diaz | Planning | Planning Task 15 | Medium | Medium | Internal Team | 2025-04-19 | 2025-05-06 | 2025-04-26 | Completed | 100% | 4500 | 4399.87 | 2 | 0 | 0 | 100.13
TSK-0438 | PRJ-1018 | Human Resources System Implementation 18 | Human Resources | System Implementation | Riley Chen | Requirements | Requirements Task 15 | Low | Medium | BluePeak Services | 2025-05-08 | 2025-06-06 |  | Not Started | 0% | 5700 | 0 | 2 |  | 0 | 5700
TSK-0439 | PRJ-1019 | Facilities Cost Reduction 19 | Facilities | Cost Reduction | Avery Brooks | Configuration | Configuration Task 15 | Low | Medium | Apex Solutions | 2025-03-24 | 2025-03-29 | 2025-04-07 | Completed | 100% | 37500 | 42347.92 | 3 | 9 | 0 | -4847.92
TSK-0440 | PRJ-1020 | Marketing Automation 20 | Marketing | Automation | Jordan Lee | Execution | Execution Task 15 | High | Medium | Internal Team | 2025-05-08 | 2025-06-02 | 2025-05-28 | Completed | 100% | 11500 | 12450.78 | 0 | 0 | 0 | -950.78
TSK-0441 | PRJ-1021 | Procurement Process Improvement 21 | Procurement | Process Improvement | Morgan Patel | Testing | Testing Task 15 | Medium | Medium | Vertex Systems | 2025-09-29 | 2025-10-05 |  | In Progress | 50% | 22300 | 23278.47 | 4 |  | 0 | -978.47
TSK-0442 | PRJ-1022 | Operations Facility Upgrade 22 | Operations | Facility Upgrade | Taylor Reed | Training | Training Task 15 | Medium | High | Internal Team | 2025-11-08 | 2025-11-11 | 2025-11-15 | Completed | 100% | 6600 | 6137.46 | 5 | 4 | 0 | 462.54
TSK-0443 | PRJ-1023 | Technology Compliance 23 | Technology | Compliance | Cameron Diaz | Launch | Launch Task 15 | High | Low | Internal Team | 2025-12-19 | 2026-01-04 | 2026-01-06 | Completed | 100% | 12500 | 13634.43 | 0 | 2 | 0 | -1134.43
TSK-0444 | PRJ-1024 | Finance Vendor Transition 24 | Finance | Vendor Transition | Riley Chen | Closeout | Closeout Task 15 | Medium | Low | Vertex Systems | 2025-03-12 | 2025-03-28 | 2025-03-26 | Completed | 100% | 25800 | 25685.84 | 0 | 0 | 0 | 114.16
TSK-0445 | PRJ-1025 | Human Resources System Implementation 25 | Human Resources | System Implementation | Avery Brooks | Discovery | Discovery Task 15 | High | Medium | Internal Team | 2025-11-24 | 2025-12-24 | 2025-12-28 | Completed | 100% | 6700 | 6997.33 | 4 | 4 | 0 | -297.33
TSK-0446 | PRJ-1026 | Facilities Cost Reduction 26 | Facilities | Cost Reduction | Jordan Lee | Planning | Planning Task 15 | Critical | Low | Apex Solutions | 2025-07-12 | 2025-08-09 | 2025-08-07 | Completed | 100% | 8500 | 7285.67 | 1 | 0 | 0 | 1214.33
TSK-0447 | PRJ-1027 | Marketing Automation 27 | Marketing | Automation | Morgan Patel | Requirements | Requirements Task 15 | Low | Low | BluePeak Services | 2026-04-28 | 2026-05-03 |  | Not Started | 0% | 11100 | 0 | 2 |  | 0 | 11100
TSK-0448 | PRJ-1028 | Procurement Process Improvement 28 | Procurement | Process Improvement | Taylor Reed | Configuration | Configuration Task 15 | Medium | High | Northstar Consulting | 2026-04-16 | 2026-04-28 | 2026-05-01 | Completed | 100% | 27500 | 34706.3 | 2 | 3 | 0 | -7206.3
TSK-0449 | PRJ-1029 | Operations Facility Upgrade 29 | Operations | Facility Upgrade | Cameron Diaz | Execution | Execution Task 15 | High | Low | Internal Team | 2026-05-12 | 2026-05-24 |  | In Progress | 90% | 27600 | 25958.74 | 1 |  | 0 | 1641.26
TSK-0450 | PRJ-1030 | Technology Compliance 30 | Technology | Compliance | Riley Chen | Training | Training Task 15 | Medium | Low | Internal Team | 2025-10-12 | 2025-10-20 |  | Not Started | 0% | 13500 | 0 | 2 |  | 0 | 13500
TSK-0451 | PRJ-1001 | Operations Facility Upgrade 01 | Operations | Facility Upgrade | Avery Brooks | Launch | Launch Task 16 | Medium | Low | Internal Team | 2025-12-16 | 2025-12-21 | 2025-12-22 | Completed | 100% | 26900 | 23693.5 | 0 | 1 | 0 | 3206.5
TSK-0452 | PRJ-1002 | Technology Compliance 02 | Technology | Compliance | Jordan Lee | Closeout | Closeout Task 16 | Medium | High | Apex Solutions | 2025-06-15 | 2025-07-06 |  | Completed | 0% | 9100 | 0 | 1 |  | 0 | 9100
TSK-0453 | PRJ-1003 | Finance Vendor Transition 03 | Finance | Vendor Transition | Morgan Patel | Discovery | Discovery Task 16 | Medium | Low | Internal Team | 2025-05-29 | 2025-06-09 | 2025-06-11 | Completed | 100% | 36900 | 32068.91 | 0 | 2 | 0 | 4831.09
TSK-0454 | PRJ-1004 | Human Resources System Implementation 04 | Human Resources | System Implementation | Taylor Reed | Planning | Planning Task 16 | Critical | Medium | Vertex Systems | 2026-04-16 | 2026-05-13 |  | Completed | 60% | 40500 | 44616.75 | 1 |  | 0 | -4116.75
TSK-0455 | PRJ-1005 | Facilities Cost Reduction 05 | Facilities | Cost Reduction | Cameron Diaz | Requirements | Requirements Task 16 | Medium | Low | Vertex Systems | 2025-07-21 | 2025-08-14 | 2025-08-18 | Completed | 100% | 16900 | 15415.31 | 0 | 4 | 0 | 1484.69
TSK-0456 | PRJ-1006 | Marketing Automation 06 | Marketing | Automation | Riley Chen | Configuration | Configuration Task 16 | Medium | Low | Internal Team | 2025-08-06 | 2025-08-11 | 2025-08-11 | Completed | 100% | 9300 | 9205.34 | 2 | 0 | 0 | 94.66
TSK-0457 | PRJ-1007 | Procurement Process Improvement 07 | Procurement | Process Improvement | Avery Brooks | Execution | Execution Task 16 | High | Low | Vertex Systems | 2025-06-17 | 2025-07-05 | 2025-07-07 | Completed | 100% | 13000 | 14319.83 | 2 | 2 | 0 | -1319.83
TSK-0458 | PRJ-1008 | Operations Facility Upgrade 08 | Operations | Facility Upgrade | Jordan Lee | Testing | Testing Task 16 | High | Low | Vertex Systems | 2025-04-17 | 2025-04-22 | 2025-05-07 | Completed | 100% | 30400 | 26716.24 | 0 | 15 | 0 | 3683.76
TSK-0459 | PRJ-1009 | Technology Compliance 09 | Technology | Compliance | Morgan Patel | Training | Training Task 16 | Medium | Low | Apex Solutions | 2026-04-08 | 2026-04-26 | 2026-05-05 | Completed | 100% | 13500 | 12449.85 | 2 | 9 | 0 | 1050.15
TSK-0460 | PRJ-1010 | Finance Vendor Transition 10 | Finance | Vendor Transition | Taylor Reed | Launch | Launch Task 16 | Medium | Low | Vertex Systems | 2025-03-31 | 2025-04-04 | 2025-04-17 | Completed | 100% | 19900 | 20821.25 | 1 | 13 | 0 | -921.25
TSK-0461 | PRJ-1011 | Human Resources System Implementation 11 | Human Resources | System Implementation | Cameron Diaz | Closeout | Closeout Task 16 | Medium | High | Vertex Systems | 2026-04-14 | 2026-04-20 | 2026-04-12 | Completed | 100% | 2000 | 2223.5 | 3 | 0 | 0 | -223.5
TSK-0462 | PRJ-1012 | Facilities Cost Reduction 12 | Facilities | Cost Reduction | Riley Chen | Discovery | Discovery Task 16 | Medium | Medium | Internal Team | 2026-06-09 | 2026-06-20 |  | In Progress | 60% | 43200 | 50142.35 | 1 |  | 0 | -6942.35
TSK-0463 | PRJ-1013 | Marketing Automation 13 | Marketing | Automation | Avery Brooks | Planning | Planning Task 16 | Medium | Low | Vertex Systems | 2026-01-13 | 2026-02-12 |  | In Progress | 60% | 9300 | 10029.78 | 2 |  | 0 | -729.78
TSK-0464 | PRJ-1014 | Procurement Process Improvement 14 | Procurement | Process Improvement | Jordan Lee | Requirements | Requirements Task 16 | Medium | Low | Internal Team | 2025-04-20 | 2025-05-10 |  | In Progress | 60% | 10000 | 11257.3 | 2 |  | 0 | -1257.3
TSK-0465 | PRJ-1015 | Operations Facility Upgrade 15 | Operations | Facility Upgrade | Morgan Patel | Configuration | Configuration Task 16 | Medium | Low | Internal Team | 2025-12-08 | 2026-01-07 | 2025-12-29 | Completed | 100% | 24700 | 23934.81 | 3 | 0 | 0 | 765.19
TSK-0466 | PRJ-1016 | Technology Compliance 16 | Technology | Compliance | Taylor Reed | Execution | Execution Task 16 | Medium | High | Internal Team | 2025-09-04 | 2025-09-29 |  | Not Started | 0% | 10900 | 0 | 5 |  | 0 | 10900
TSK-0467 | PRJ-1017 | Finance Vendor Transition 17 | Finance | Vendor Transition | Cameron Diaz | Testing | Testing Task 16 | Low | Medium | Internal Team | 2025-04-24 | 2025-05-14 | 2025-05-18 | Completed | 100% | 19400 | 17965.66 | 1 | 4 | 0 | 1434.34
TSK-0468 | PRJ-1018 | Human Resources System Implementation 18 | Human Resources | System Implementation | Riley Chen | Training | Training Task 16 | High | Medium | Northstar Consulting | 2025-06-07 | 2025-06-15 |  | On Hold | 30% | 16900 | 19495.73 | 1 |  | 0 | -2595.73
TSK-0469 | PRJ-1019 | Facilities Cost Reduction 19 | Facilities | Cost Reduction | Avery Brooks | Launch | Launch Task 16 | High | High | Internal Team | 2025-05-06 | 2025-05-23 | 2025-05-18 | Completed | 100% | 7800 | 9117.31 | 5 | 0 | 0 | -1317.31
TSK-0470 | PRJ-1020 | Marketing Automation 20 | Marketing | Automation | Jordan Lee | Closeout | Closeout Task 16 | Medium | Medium | Northstar Consulting | 2025-05-15 | 2025-05-20 |  | Not Started | 0% | 11400 | 0 | 3 |  | 0 | 11400
TSK-0471 | PRJ-1021 | Procurement Process Improvement 21 | Procurement | Process Improvement | Morgan Patel | Discovery | Discovery Task 16 | Medium | Medium | Internal Team | 2025-08-26 | 2025-09-22 | 2025-09-18 | Completed | 100% | 43500 | 49191.04 | 1 | 0 | 0 | -5691.04
TSK-0472 | PRJ-1022 | Operations Facility Upgrade 22 | Operations | Facility Upgrade | Taylor Reed | Planning | Planning Task 16 | Low | Medium | Northstar Consulting | 2025-10-11 | 2025-10-20 |  | Not Started | 0% | 6000 | 0 | 4 |  | 0 | 6000
TSK-0473 | PRJ-1023 | Technology Compliance 23 | Technology | Compliance | Cameron Diaz | Requirements | Requirements Task 16 | Medium | Low | Internal Team | 2025-12-01 | 2025-12-07 |  | In Progress | 40% | 5200 | 5762.4 | 2 |  | 0 | -562.4
TSK-0474 | PRJ-1024 | Finance Vendor Transition 24 | Finance | Vendor Transition | Riley Chen | Configuration | Configuration Task 16 | Medium | Medium | Internal Team | 2025-02-20 | 2025-02-27 | 2025-02-26 | Completed | 100% | 8900 | 9975.46 | 2 | 0 | 0 | -1075.46
TSK-0475 | PRJ-1025 | Human Resources System Implementation 25 | Human Resources | System Implementation | Avery Brooks | Execution | Execution Task 16 | Critical | High | Apex Solutions | 2026-03-07 | 2026-03-18 | 2026-03-31 | Completed | 100% | 25000 | 31777.22 | 2 | 13 | 0 | -6777.22
TSK-0476 | PRJ-1026 | Facilities Cost Reduction 26 | Facilities | Cost Reduction | Jordan Lee | Testing | Testing Task 16 | High | High | Internal Team | 2025-08-31 | 2025-09-12 | 2025-09-10 | Completed | 100% | 22500 | 24228.54 | 4 | 0 | 0 | -1728.54
TSK-0477 | PRJ-1027 | Marketing Automation 27 | Marketing | Automation | Morgan Patel | Training | Training Task 16 | Medium | Low | Internal Team | 2026-01-09 | 2026-01-12 | 2026-01-14 | Completed | 100% | 14000 | 13447.45 | 0 | 2 | 0 | 552.55
TSK-0478 | PRJ-1028 | Procurement Process Improvement 28 | Procurement | Process Improvement | Taylor Reed | Launch | Launch Task 16 | Medium | Medium | Internal Team | 2026-03-24 | 2026-04-21 |  | In Progress | 40% | 36200 | 35594.95 | 1 |  | 0 | 605.05
TSK-0479 | PRJ-1029 | Operations Facility Upgrade 29 | Operations | Facility Upgrade | Cameron Diaz | Closeout | Closeout Task 16 | High | Low | Internal Team | 2026-04-09 | 2026-05-08 |  | In Progress | 50% | 4900 | 4894.05 | 0 |  | 0 | 5.95
TSK-0480 | PRJ-1030 | Technology Compliance 30 | Technology | Compliance | Riley Chen | Planning | Planning Task 16 | High | Medium | Vertex Systems | 2025-12-20 | 2026-01-01 | 2025-12-28 | Completed | 100% | 24600 | 24885.95 | 3 | 0 | 0 | -285.95
TSK-0481 | PRJ-1001 | Operations Facility Upgrade 01 | Operations | Facility Upgrade | Avery Brooks | Requirements | Requirements Task 17 | Low | Low | Internal Team | 2026-03-25 | 2026-04-16 |  | Completed | 85% | 28600 | 29409.23 | 1 |  | 0 | -809.23
TSK-0482 | PRJ-1002 | Technology Compliance 02 | Technology | Compliance | Jordan Lee | Configuration | Configuration Task 17 | Low | Medium | Internal Team | 2025-03-30 | 2025-04-11 |  | Completed | 85% | 20600 | 21995.96 | 2 |  | 0 | -1395.96
TSK-0483 | PRJ-1003 | Finance Vendor Transition 03 | Finance | Vendor Transition | Morgan Patel | Execution | Execution Task 17 | Low | Low | Internal Team | 2025-05-25 | 2025-06-08 | 2025-06-12 | Completed | 100% | 38200 | 35328.36 | 2 | 4 | 0 | 2871.64
TSK-0484 | PRJ-1004 | Human Resources System Implementation 04 | Human Resources | System Implementation | Taylor Reed | Testing | Testing Task 17 | High | Low | Apex Solutions | 2026-03-10 | 2026-04-08 |  | Completed | 60% | 37500 | 37830.88 | 3 |  | 0 | -330.88
TSK-0485 | PRJ-1005 | Facilities Cost Reduction 05 | Facilities | Cost Reduction | Cameron Diaz | Training | Training Task 17 | Medium | Medium | Internal Team | 2025-06-03 | 2025-06-12 | 2025-06-22 | Completed | 100% | 35000 | 24874.35 | 1 | 10 | 0 | 10125.65
TSK-0486 | PRJ-1006 | Marketing Automation 06 | Marketing | Automation | Riley Chen | Launch | Launch Task 17 | Medium | Medium | Internal Team | 2025-08-01 | 2025-08-09 | 2025-08-27 | Completed | 100% | 24200 | 26325.79 | 2 | 18 | 0 | -2125.79
TSK-0487 | PRJ-1007 | Procurement Process Improvement 07 | Procurement | Process Improvement | Avery Brooks | Closeout | Closeout Task 17 | Medium | High | Summit Partners | 2025-06-24 | 2025-06-30 |  | Completed | 60% | 15600 | 19139.46 | 4 |  | 0 | -3539.46
TSK-0488 | PRJ-1008 | Operations Facility Upgrade 08 | Operations | Facility Upgrade | Jordan Lee | Discovery | Discovery Task 17 | Low | Medium | Internal Team | 2025-03-28 | 2025-04-18 | 2025-04-25 | Completed | 100% | 22200 | 20707.93 | 1 | 7 | 0 | 1492.07
TSK-0489 | PRJ-1009 | Technology Compliance 09 | Technology | Compliance | Morgan Patel | Planning | Planning Task 17 | Low | Low | Internal Team | 2026-04-14 | 2026-05-11 | 2026-05-22 | Completed | 100% | 32000 | 34497.17 | 1 | 11 | 0 | -2497.17
TSK-0490 | PRJ-1010 | Finance Vendor Transition 10 | Finance | Vendor Transition | Taylor Reed | Requirements | Requirements Task 17 | Medium | High | Vertex Systems | 2025-05-26 | 2025-06-23 | 2025-06-21 | Completed | 100% | 33400 | 39284.71 | 3 | 0 | 0 | -5884.71
TSK-0491 | PRJ-1011 | Human Resources System Implementation 11 | Human Resources | System Implementation | Cameron Diaz | Configuration | Configuration Task 17 | High | Low | Internal Team | 2026-04-09 | 2026-04-29 |  | In Progress | 85% | 22800 | 20386.49 | 1 |  | 0 | 2413.51
TSK-0492 | PRJ-1012 | Facilities Cost Reduction 12 | Facilities | Cost Reduction | Riley Chen | Execution | Execution Task 17 | Medium | Low | Summit Partners | 2026-06-10 | 2026-06-18 |  | Not Started | 0% | 8200 | 0 | 2 |  | 0 | 8200
TSK-0493 | PRJ-1013 | Marketing Automation 13 | Marketing | Automation | Avery Brooks | Testing | Testing Task 17 | Medium | Low | Northstar Consulting | 2026-01-17 | 2026-02-12 |  | In Progress | 25% | 28500 | 26204.24 | 3 |  | 0 | 2295.76
TSK-0494 | PRJ-1014 | Procurement Process Improvement 14 | Procurement | Process Improvement | Jordan Lee | Training | Training Task 17 | Medium | Low | BluePeak Services | 2025-05-29 | 2025-06-07 | 2025-05-31 | Completed | 100% | 28200 | 28824.49 | 0 | 0 | 0 | -624.49
TSK-0495 | PRJ-1015 | Operations Facility Upgrade 15 | Operations | Facility Upgrade | Morgan Patel | Launch | Launch Task 17 | Low | Medium | Internal Team | 2025-12-07 | 2025-12-15 | 2025-12-26 | Completed | 100% | 10300 | 9991.51 | 2 | 11 | 0 | 308.49
TSK-0496 | PRJ-1016 | Technology Compliance 16 | Technology | Compliance | Taylor Reed | Closeout | Closeout Task 17 | High | Medium | Northstar Consulting | 2025-12-22 | 2026-01-13 | 2026-01-15 | Completed | 100% | 27900 | 31387.67 | 4 | 2 | 0 | -3487.67
TSK-0497 | PRJ-1017 | Finance Vendor Transition 17 | Finance | Vendor Transition | Cameron Diaz | Discovery | Discovery Task 17 | Medium | Low | Summit Partners | 2025-02-11 | 2025-02-28 | 2025-03-09 | Completed | 100% | 4100 | 3187.63 | 0 | 9 | 0 | 912.37
TSK-0498 | PRJ-1018 | Human Resources System Implementation 18 | Human Resources | System Implementation | Riley Chen | Planning | Planning Task 17 | Medium | Low | Vertex Systems | 2025-03-30 | 2025-04-18 |  | Not Started | 0% | 4600 | 0 | 4 |  | 0 | 4600
TSK-0499 | PRJ-1019 | Facilities Cost Reduction 19 | Facilities | Cost Reduction | Avery Brooks | Requirements | Requirements Task 17 | Critical | Low | Vertex Systems | 2025-07-08 | 2025-07-23 |  | In Progress | 75% | 30100 | 23429.32 | 0 |  | 0 | 6670.68
TSK-0500 | PRJ-1020 | Marketing Automation 20 | Marketing | Automation | Jordan Lee | Configuration | Configuration Task 17 | Medium | Medium | Vertex Systems | 2025-09-21 | 2025-10-05 | 2025-10-05 | Completed | 100% | 6000 | 5454.12 | 2 | 0 | 0 | 545.88
TSK-0501 | PRJ-1021 | Procurement Process Improvement 21 | Procurement | Process Improvement | Morgan Patel | Execution | Execution Task 17 | Medium | Medium | Apex Solutions | 2025-08-26 | 2025-09-09 | 2025-09-02 | Completed | 100% | 25400 | 31300.72 | 2 | 0 | 0 | -5900.72
TSK-0502 | PRJ-1022 | Operations Facility Upgrade 22 | Operations | Facility Upgrade | Taylor Reed | Testing | Testing Task 17 | Medium | Medium | Summit Partners | 2025-12-12 | 2026-01-03 |  | In Progress | 75% | 10800 | 11283.23 | 0 |  | 0 | -483.23
TSK-0503 | PRJ-1023 | Technology Compliance 23 | Technology | Compliance | Cameron Diaz | Training | Training Task 17 | Medium | High | Internal Team | 2026-02-19 | 2026-02-22 | 2026-03-05 | Completed | 100% | 24000 | 25300.22 | 4 | 11 | 0 | -1300.22
TSK-0504 | PRJ-1024 | Finance Vendor Transition 24 | Finance | Vendor Transition | Riley Chen | Launch | Launch Task 17 | Medium | Low | Summit Partners | 2025-01-24 | 2025-02-20 | 2025-02-22 | Completed | 100% | 31500 | 31415.37 | 3 | 2 | 0 | 84.63
TSK-0505 | PRJ-1025 | Human Resources System Implementation 25 | Human Resources | System Implementation | Avery Brooks | Closeout | Closeout Task 17 | Medium | High | Internal Team | 2025-10-29 | 2025-11-15 |  | In Progress | 40% | 13000 | 14743.86 | 2 |  | 0 | -1743.86
TSK-0506 | PRJ-1026 | Facilities Cost Reduction 26 | Facilities | Cost Reduction | Jordan Lee | Discovery | Discovery Task 17 | Medium | Low | Northstar Consulting | 2025-09-09 | 2025-09-18 | 2025-09-18 | Completed | 100% | 9000 | 7447.31 | 2 | 0 | 0 | 1552.69
TSK-0507 | PRJ-1027 | Marketing Automation 27 | Marketing | Automation | Morgan Patel | Planning | Planning Task 17 | High | High | Northstar Consulting | 2026-03-24 | 2026-03-28 | 2026-03-20 | Completed | 100% | 26600 | 29336.41 | 3 | 0 | 0 | -2736.41
TSK-0508 | PRJ-1028 | Procurement Process Improvement 28 | Procurement | Process Improvement | Taylor Reed | Requirements | Requirements Task 17 | High | Low | Summit Partners | 2026-03-20 | 2026-04-19 |  | Not Started | 0% | 35000 | 0 | 0 |  | 0 | 35000
TSK-0509 | PRJ-1029 | Operations Facility Upgrade 29 | Operations | Facility Upgrade | Cameron Diaz | Configuration | Configuration Task 17 | Critical | Medium | Northstar Consulting | 2026-01-13 | 2026-01-25 | 2026-01-23 | Completed | 100% | 15700 | 18034.05 | 1 | 0 | 0 | -2334.05
TSK-0510 | PRJ-1030 | Technology Compliance 30 | Technology | Compliance | Riley Chen | Testing | Testing Task 17 | High | High | BluePeak Services | 2026-03-08 | 2026-03-27 |  | Not Started | 0% | 20300 | 0 | 3 |  | 0 | 20300
TSK-0511 | PRJ-1001 | Operations Facility Upgrade 01 | Operations | Facility Upgrade | Avery Brooks | Training | Training Task 18 | Medium | Low | Vertex Systems | 2026-04-18 | 2026-05-03 |  | Completed | 60% | 23300 | 22353.03 | 1 |  | 0 | 946.97
TSK-0512 | PRJ-1002 | Technology Compliance 02 | Technology | Compliance | Jordan Lee | Launch | Launch Task 18 | Medium | Medium | Apex Solutions | 2025-07-28 | 2025-08-06 | 2025-08-04 | Completed | 100% | 44900 | 42161.23 | 2 | 0 | 0 | 2738.77
TSK-0513 | PRJ-1003 | Finance Vendor Transition 03 | Finance | Vendor Transition | Morgan Patel | Closeout | Closeout Task 18 | Medium | Low | Vertex Systems | 2025-06-14 | 2025-06-19 |  | Completed | 0% | 19500 | 0 | 2 |  | 0 | 19500
TSK-0514 | PRJ-1004 | Human Resources System Implementation 04 | Human Resources | System Implementation | Taylor Reed | Discovery | Discovery Task 18 | Medium | Medium | Vertex Systems | 2026-03-04 | 2026-03-18 | 2026-03-28 | Completed | 100% | 7800 | 7898.71 | 4 | 10 | 0 | -98.71
TSK-0515 | PRJ-1005 | Facilities Cost Reduction 05 | Facilities | Cost Reduction | Cameron Diaz | Planning | Planning Task 18 | Medium | Low | Vertex Systems | 2025-06-16 | 2025-06-22 | 2025-06-28 | Completed | 100% | 12100 | 11796.76 | 1 | 6 | 0 | 303.24
TSK-0516 | PRJ-1006 | Marketing Automation 06 | Marketing | Automation | Riley Chen | Requirements | Requirements Task 18 | High | Low | Internal Team | 2025-06-08 | 2025-06-20 |  | Completed | 25% | 15900 | 16142.31 | 0 |  | 0 | -242.31
TSK-0517 | PRJ-1007 | Procurement Process Improvement 07 | Procurement | Process Improvement | Avery Brooks | Configuration | Configuration Task 18 | Medium | Medium | Apex Solutions | 2025-06-05 | 2025-06-30 | 2025-07-11 | Completed | 100% | 30400 | 31517.88 | 2 | 11 | 0 | -1117.88
TSK-0518 | PRJ-1008 | Operations Facility Upgrade 08 | Operations | Facility Upgrade | Jordan Lee | Execution | Execution Task 18 | Medium | Medium | Northstar Consulting | 2025-03-31 | 2025-04-17 | 2025-04-20 | Completed | 100% | 1900 | 1810.78 | 2 | 3 | 0 | 89.22
TSK-0519 | PRJ-1009 | Technology Compliance 09 | Technology | Compliance | Morgan Patel | Testing | Testing Task 18 | High | Medium | Summit Partners | 2026-01-22 | 2026-02-03 | 2026-02-02 | Completed | 100% | 18100 | 17297.19 | 2 | 0 | 0 | 802.81
TSK-0520 | PRJ-1010 | Finance Vendor Transition 10 | Finance | Vendor Transition | Taylor Reed | Training | Training Task 18 | Medium | High | Apex Solutions | 2025-04-15 | 2025-04-24 | 2025-04-26 | Completed | 100% | 21400 | 23337.05 | 3 | 2 | 0 | -1937.05
TSK-0521 | PRJ-1011 | Human Resources System Implementation 11 | Human Resources | System Implementation | Cameron Diaz | Launch | Launch Task 18 | Medium | Medium | Internal Team | 2026-03-28 | 2026-04-23 |  | Not Started | 0% | 16600 | 0 | 3 |  | 0 | 16600
TSK-0522 | PRJ-1012 | Facilities Cost Reduction 12 | Facilities | Cost Reduction | Riley Chen | Closeout | Closeout Task 18 | Medium | High | Apex Solutions | 2026-02-04 | 2026-02-27 |  | In Progress | 60% | 40200 | 43442.64 | 3 |  | 0 | -3242.64
TSK-0523 | PRJ-1013 | Marketing Automation 13 | Marketing | Automation | Avery Brooks | Discovery | Discovery Task 18 | Medium | Low | Internal Team | 2026-01-20 | 2026-02-13 |  | Not Started | 0% | 33300 | 0 | 1 |  | 0 | 33300
TSK-0524 | PRJ-1014 | Procurement Process Improvement 14 | Procurement | Process Improvement | Jordan Lee | Planning | Planning Task 18 | High | Medium | Internal Team | 2025-07-15 | 2025-07-22 |  | In Progress | 50% | 41100 | 39221.52 | 3 |  | 0 | 1878.48
TSK-0525 | PRJ-1015 | Operations Facility Upgrade 15 | Operations | Facility Upgrade | Morgan Patel | Requirements | Requirements Task 18 | Medium | Low | Apex Solutions | 2025-12-25 | 2026-01-24 |  | Not Started | 0% | 31500 | 0 | 0 |  | 0 | 31500
TSK-0526 | PRJ-1016 | Technology Compliance 16 | Technology | Compliance | Taylor Reed | Configuration | Configuration Task 18 | Medium | High | Vertex Systems | 2026-01-01 | 2026-01-09 |  | In Progress | 75% | 24700 | 26098.21 | 2 |  | 0 | -1398.21
TSK-0527 | PRJ-1017 | Finance Vendor Transition 17 | Finance | Vendor Transition | Cameron Diaz | Execution | Execution Task 18 | High | Low | Internal Team | 2025-04-13 | 2025-04-29 |  | On Hold | 30% | 20800 | 25650.95 | 0 |  | 0 | -4850.95
TSK-0528 | PRJ-1018 | Human Resources System Implementation 18 | Human Resources | System Implementation | Riley Chen | Testing | Testing Task 18 | Critical | Low | Vertex Systems | 2025-02-17 | 2025-02-24 |  | In Progress | 90% | 44400 | 40344.77 | 0 |  | 0 | 4055.23
TSK-0529 | PRJ-1019 | Facilities Cost Reduction 19 | Facilities | Cost Reduction | Avery Brooks | Training | Training Task 18 | High | Medium | Internal Team | 2025-02-28 | 2025-03-14 |  | Not Started | 0% | 35400 | 0 | 4 |  | 0 | 35400
TSK-0530 | PRJ-1020 | Marketing Automation 20 | Marketing | Automation | Jordan Lee | Launch | Launch Task 18 | Medium | Medium | Internal Team | 2025-08-04 | 2025-08-22 | 2025-08-27 | Completed | 100% | 19300 | 20988.98 | 5 | 5 | 0 | -1688.98
TSK-0531 | PRJ-1021 | Procurement Process Improvement 21 | Procurement | Process Improvement | Morgan Patel | Closeout | Closeout Task 18 | Critical | Low | Vertex Systems | 2025-06-25 | 2025-07-22 |  | In Progress | 40% | 41800 | 40596.21 | 4 |  | 0 | 1203.79
TSK-0532 | PRJ-1022 | Operations Facility Upgrade 22 | Operations | Facility Upgrade | Taylor Reed | Discovery | Discovery Task 18 | Medium | Low | Apex Solutions | 2025-11-23 | 2025-12-09 |  | In Progress | 25% | 27900 | 27901.93 | 2 |  | 0 | -1.93
TSK-0533 | PRJ-1023 | Technology Compliance 23 | Technology | Compliance | Cameron Diaz | Planning | Planning Task 18 | Medium | High | Northstar Consulting | 2026-03-27 | 2026-04-15 | 2026-04-07 | Completed | 100% | 32100 | 35996.54 | 3 | 0 | 0 | -3896.54
TSK-0534 | PRJ-1024 | Finance Vendor Transition 24 | Finance | Vendor Transition | Riley Chen | Requirements | Requirements Task 18 | Medium | High | Summit Partners | 2025-03-22 | 2025-04-10 | 2025-04-14 | Completed | 100% | 18400 | 19629.91 | 3 | 4 | 0 | -1229.91
TSK-0535 | PRJ-1025 | Human Resources System Implementation 25 | Human Resources | System Implementation | Avery Brooks | Configuration | Configuration Task 18 | Medium | Low | Summit Partners | 2026-01-01 | 2026-01-18 |  | Not Started | 0% | 14300 | 0 | 3 |  | 0 | 14300
TSK-0536 | PRJ-1026 | Facilities Cost Reduction 26 | Facilities | Cost Reduction | Jordan Lee | Execution | Execution Task 18 | Critical | Low | Northstar Consulting | 2025-05-10 | 2025-06-05 | 2025-06-02 | Completed | 100% | 9300 | 7622.28 | 0 | 0 | 0 | 1677.72
TSK-0537 | PRJ-1027 | Marketing Automation 27 | Marketing | Automation | Morgan Patel | Testing | Testing Task 18 | Medium | Low | Internal Team | 2026-01-13 | 2026-01-21 |  | In Progress | 85% | 40500 | 42742.96 | 1 |  | 0 | -2242.96
TSK-0538 | PRJ-1028 | Procurement Process Improvement 28 | Procurement | Process Improvement | Taylor Reed | Training | Training Task 18 | Medium | Medium | Vertex Systems | 2026-01-14 | 2026-02-08 | 2026-02-19 | Completed | 100% | 29100 | 32398.21 | 3 | 11 | 0 | -3298.21
TSK-0539 | PRJ-1029 | Operations Facility Upgrade 29 | Operations | Facility Upgrade | Cameron Diaz | Launch | Launch Task 18 | High | High | Northstar Consulting | 2026-02-09 | 2026-02-24 | 2026-03-04 | Completed | 100% | 3400 | 3799.16 | 4 | 8 | 0 | -399.16
TSK-0540 | PRJ-1030 | Technology Compliance 30 | Technology | Compliance | Riley Chen | Discovery | Discovery Task 18 | High | High | Internal Team | 2025-11-18 | 2025-11-26 | 2025-12-04 | Completed | 100% | 33300 | 36627.01 | 4 | 8 | 0 | -3327.01
TSK-0541 | PRJ-1001 | Operations Facility Upgrade 01 | Operations | Facility Upgrade | Avery Brooks | Planning | Planning Task 19 | Medium | High | BluePeak Services | 2025-11-29 | 2025-12-21 | 2025-12-22 | Completed | 100% | 2000 | 1881.51 | 3 | 1 | 0 | 118.49
TSK-0542 | PRJ-1002 | Technology Compliance 02 | Technology | Compliance | Jordan Lee | Requirements | Requirements Task 19 | High | Medium | Apex Solutions | 2025-04-28 | 2025-05-19 | 2025-05-14 | Completed | 100% | 27700 | 29197.09 | 4 | 0 | 0 | -1497.09
TSK-0543 | PRJ-1003 | Finance Vendor Transition 03 | Finance | Vendor Transition | Morgan Patel | Configuration | Configuration Task 19 | Medium | Medium | Summit Partners | 2025-03-12 | 2025-03-16 |  | Completed | 25% | 29900 | 30778.84 | 4 |  | 0 | -878.84
TSK-0544 | PRJ-1004 | Human Resources System Implementation 04 | Human Resources | System Implementation | Taylor Reed | Execution | Execution Task 19 | High | Medium | Internal Team | 2026-02-11 | 2026-02-15 |  | Completed | 0% | 44700 | 0 | 2 |  | 0 | 44700
TSK-0545 | PRJ-1005 | Facilities Cost Reduction 05 | Facilities | Cost Reduction | Cameron Diaz | Testing | Testing Task 19 | High | Medium | Northstar Consulting | 2025-10-16 | 2025-10-24 |  | Completed | 65% | 17200 | 18857.73 | 4 |  | 0 | -1657.73
TSK-0546 | PRJ-1006 | Marketing Automation 06 | Marketing | Automation | Riley Chen | Training | Training Task 19 | Medium | High | Summit Partners | 2025-08-28 | 2025-09-26 | 2025-10-01 | Completed | 100% | 14200 | 16790.18 | 4 | 5 | 0 | -2590.18
TSK-0547 | PRJ-1007 | Procurement Process Improvement 07 | Procurement | Process Improvement | Avery Brooks | Launch | Launch Task 19 | Medium | Medium | Apex Solutions | 2025-06-22 | 2025-07-14 |  | Completed | 0% | 26400 | 0 | 1 |  | 0 | 26400
TSK-0548 | PRJ-1008 | Operations Facility Upgrade 08 | Operations | Facility Upgrade | Jordan Lee | Closeout | Closeout Task 19 | Low | Medium | Northstar Consulting | 2025-05-30 | 2025-06-15 | 2025-06-14 | Completed | 100% | 44800 | 51195.04 | 1 | 0 | 0 | -6395.04
TSK-0549 | PRJ-1009 | Technology Compliance 09 | Technology | Compliance | Morgan Patel | Discovery | Discovery Task 19 | Medium | Low | Northstar Consulting | 2026-05-24 | 2026-06-21 |  | Not Started | 0% | 28000 | 0 | 0 |  | 0 | 28000
TSK-0550 | PRJ-1010 | Finance Vendor Transition 10 | Finance | Vendor Transition | Taylor Reed | Planning | Planning Task 19 | Low | Low | Northstar Consulting | 2025-03-29 | 2025-04-24 | 2025-04-07 | Completed | 100% | 36300 | 41154.4 | 1 | 0 | 0 | -4854.4
TSK-0551 | PRJ-1011 | Human Resources System Implementation 11 | Human Resources | System Implementation | Cameron Diaz | Requirements | Requirements Task 19 | Medium | Medium | Northstar Consulting | 2025-12-20 | 2026-01-12 |  | In Progress | 50% | 12600 | 13918.49 | 2 |  | 0 | -1318.49
TSK-0552 | PRJ-1012 | Facilities Cost Reduction 12 | Facilities | Cost Reduction | Riley Chen | Configuration | Configuration Task 19 | Medium | Medium | Internal Team | 2026-04-15 | 2026-04-28 |  | In Progress | 75% | 28300 | 30768.46 | 2 |  | 0 | -2468.46
TSK-0553 | PRJ-1013 | Marketing Automation 13 | Marketing | Automation | Avery Brooks | Execution | Execution Task 19 | Medium | Low | Vertex Systems | 2026-02-10 | 2026-03-10 |  | Not Started | 0% | 7400 | 0 | 2 |  | 0 | 7400
TSK-0554 | PRJ-1014 | Procurement Process Improvement 14 | Procurement | Process Improvement | Jordan Lee | Testing | Testing Task 19 | High | High | Apex Solutions | 2025-06-04 | 2025-06-30 |  | Not Started | 0% | 24200 | 0 | 2 |  | 0 | 24200
TSK-0555 | PRJ-1015 | Operations Facility Upgrade 15 | Operations | Facility Upgrade | Morgan Patel | Training | Training Task 19 | Medium | Low | Northstar Consulting | 2026-01-27 | 2026-02-24 | 2026-02-27 | Completed | 100% | 8000 | 7847.65 | 2 | 3 | 0 | 152.35
TSK-0556 | PRJ-1016 | Technology Compliance 16 | Technology | Compliance | Taylor Reed | Launch | Launch Task 19 | Medium | Medium | Internal Team | 2025-11-17 | 2025-11-25 | 2025-11-22 | Completed | 100% | 39100 | 39947.06 | 0 | 0 | 0 | -847.06
TSK-0557 | PRJ-1017 | Finance Vendor Transition 17 | Finance | Vendor Transition | Cameron Diaz | Closeout | Closeout Task 19 | Medium | Low | Internal Team | 2025-05-29 | 2025-06-08 |  | In Progress | 90% | 42900 | 44603.47 | 2 |  | 0 | -1703.47
TSK-0558 | PRJ-1018 | Human Resources System Implementation 18 | Human Resources | System Implementation | Riley Chen | Discovery | Discovery Task 19 | Low | Medium | Vertex Systems | 2025-02-13 | 2025-03-02 | 2025-03-09 | Completed | 100% | 8200 | 6499.2 | 1 | 7 | 0 | 1700.8
TSK-0559 | PRJ-1019 | Facilities Cost Reduction 19 | Facilities | Cost Reduction | Avery Brooks | Planning | Planning Task 19 | High | Low | Internal Team | 2025-03-19 | 2025-04-17 |  | On Hold | 65% | 30900 | 34815.27 | 3 |  | 0 | -3915.27
TSK-0560 | PRJ-1020 | Marketing Automation 20 | Marketing | Automation | Jordan Lee | Requirements | Requirements Task 19 | Medium | Medium | Apex Solutions | 2025-04-28 | 2025-05-10 | 2025-05-20 | Completed | 100% | 31400 | 30804.89 | 1 | 10 | 0 | 595.11
TSK-0561 | PRJ-1021 | Procurement Process Improvement 21 | Procurement | Process Improvement | Morgan Patel | Configuration | Configuration Task 19 | Medium | Low | Apex Solutions | 2025-07-23 | 2025-07-26 | 2025-07-22 | Completed | 100% | 15500 | 19137.4 | 2 | 0 | 0 | -3637.4
TSK-0562 | PRJ-1022 | Operations Facility Upgrade 22 | Operations | Facility Upgrade | Taylor Reed | Execution | Execution Task 19 | Medium | Low | Internal Team | 2025-10-29 | 2025-11-06 |  | In Progress | 25% | 43200 | 47641.96 | 1 |  | 0 | -4441.96
TSK-0563 | PRJ-1023 | Technology Compliance 23 | Technology | Compliance | Cameron Diaz | Testing | Testing Task 19 | Medium | Medium | Internal Team | 2026-01-21 | 2026-02-11 |  | In Progress | 25% | 15000 | 15019.38 | 3 |  | 0 | -19.38
TSK-0564 | PRJ-1024 | Finance Vendor Transition 24 | Finance | Vendor Transition | Riley Chen | Training | Training Task 19 | Low | Low | BluePeak Services | 2025-01-31 | 2025-02-06 |  | In Progress | 25% | 20100 | 18774.35 | 2 |  | 0 | 1325.65
TSK-0565 | PRJ-1025 | Human Resources System Implementation 25 | Human Resources | System Implementation | Avery Brooks | Launch | Launch Task 19 | High | Medium | Vertex Systems | 2026-01-19 | 2026-01-31 |  | In Progress | 40% | 32500 | 37492.68 | 1 |  | 0 | -4992.68
TSK-0566 | PRJ-1026 | Facilities Cost Reduction 26 | Facilities | Cost Reduction | Jordan Lee | Closeout | Closeout Task 19 | Critical | Medium | Apex Solutions | 2025-05-20 | 2025-05-25 | 2025-05-19 | Completed | 100% | 41500 | 37395.57 | 2 | 0 | 0 | 4104.43
TSK-0567 | PRJ-1027 | Marketing Automation 27 | Marketing | Automation | Morgan Patel | Discovery | Discovery Task 19 | High | Medium | Apex Solutions | 2026-03-07 | 2026-03-17 |  | Not Started | 0% | 40500 | 0 | 3 |  | 0 | 40500
TSK-0568 | PRJ-1028 | Procurement Process Improvement 28 | Procurement | Process Improvement | Taylor Reed | Planning | Planning Task 19 | Medium | High | Internal Team | 2026-02-25 | 2026-03-14 | 2026-03-19 | Completed | 100% | 22300 | 24340.36 | 4 | 5 | 0 | -2040.36
TSK-0569 | PRJ-1029 | Operations Facility Upgrade 29 | Operations | Facility Upgrade | Cameron Diaz | Requirements | Requirements Task 19 | Medium | Medium | Apex Solutions | 2026-04-13 | 2026-05-12 | 2026-05-09 | Completed | 100% | 6200 | 6078.51 | 2 | 0 | 0 | 121.49
TSK-0570 | PRJ-1030 | Technology Compliance 30 | Technology | Compliance | Riley Chen | Execution | Execution Task 19 | Medium | Low | Northstar Consulting | 2025-12-12 | 2026-01-03 |  | In Progress | 40% | 43900 | 41493.36 | 2 |  | 0 | 2406.64
TSK-0571 | PRJ-1001 | Operations Facility Upgrade 01 | Operations | Facility Upgrade | Avery Brooks | Testing | Testing Task 20 | High | Medium | Vertex Systems | 2026-03-20 | 2026-04-10 | 2026-04-07 | Completed | 100% | 30300 | 30230.44 | 4 | 0 | 0 | 69.56
TSK-0572 | PRJ-1002 | Technology Compliance 02 | Technology | Compliance | Jordan Lee | Training | Training Task 20 | High | Low | Northstar Consulting | 2025-06-30 | 2025-07-13 | 2025-07-23 | Completed | 100% | 37300 | 42632.27 | 4 | 10 | 0 | -5332.27
TSK-0573 | PRJ-1003 | Finance Vendor Transition 03 | Finance | Vendor Transition | Morgan Patel | Launch | Launch Task 20 | Low | Low | Summit Partners | 2025-04-25 | 2025-05-08 | 2025-05-08 | Completed | 100% | 37000 | 36241.93 | 3 | 0 | 0 | 758.07
TSK-0574 | PRJ-1004 | Human Resources System Implementation 04 | Human Resources | System Implementation | Taylor Reed | Closeout | Closeout Task 20 | High | Low | Internal Team | 2026-02-27 | 2026-03-16 | 2026-03-08 | Completed | 100% | 18500 | 17684.88 | 1 | 0 | 0 | 815.12
TSK-0575 | PRJ-1005 | Facilities Cost Reduction 05 | Facilities | Cost Reduction | Cameron Diaz | Discovery | Discovery Task 20 | High | Low | Northstar Consulting | 2025-08-11 | 2025-08-27 | 2025-09-16 | Completed | 100% | 26800 | 22772.97 | 0 | 20 | 0 | 4027.03
TSK-0576 | PRJ-1006 | Marketing Automation 06 | Marketing | Automation | Riley Chen | Planning | Planning Task 20 | High | High | Internal Team | 2025-09-28 | 2025-10-02 |  | Completed | 0% | 25900 | 0 | 4 |  | 0 | 25900
TSK-0577 | PRJ-1007 | Procurement Process Improvement 07 | Procurement | Process Improvement | Avery Brooks | Requirements | Requirements Task 20 | Medium | Low | Internal Team | 2025-08-08 | 2025-08-31 |  | Completed | 60% | 19200 | 19448.12 | 0 |  | 0 | -248.12
TSK-0578 | PRJ-1008 | Operations Facility Upgrade 08 | Operations | Facility Upgrade | Jordan Lee | Configuration | Configuration Task 20 | Medium | Low | Apex Solutions | 2025-06-18 | 2025-07-17 |  | Completed | 50% | 44900 | 47145.48 | 1 |  | 0 | -2245.48
TSK-0579 | PRJ-1009 | Technology Compliance 09 | Technology | Compliance | Morgan Patel | Execution | Execution Task 20 | Low | Low | Vertex Systems | 2026-05-22 | 2026-06-15 |  | In Progress | 40% | 5200 | 5034.76 | 0 |  | 0 | 165.24
TSK-0580 | PRJ-1010 | Finance Vendor Transition 10 | Finance | Vendor Transition | Taylor Reed | Testing | Testing Task 20 | Medium | Medium | Northstar Consulting | 2025-06-15 | 2025-07-07 |  | Not Started | 0% | 23700 | 0 | 0 |  | 0 | 23700
TSK-0581 | PRJ-1011 | Human Resources System Implementation 11 | Human Resources | System Implementation | Cameron Diaz | Training | Training Task 20 | Medium | Low | Northstar Consulting | 2026-05-14 | 2026-06-01 | 2026-06-01 | Completed | 100% | 11800 | 10700.9 | 1 | 0 | 0 | 1099.1
TSK-0582 | PRJ-1012 | Facilities Cost Reduction 12 | Facilities | Cost Reduction | Riley Chen | Launch | Launch Task 20 | Medium | Low | BluePeak Services | 2026-06-14 | 2026-07-02 | 2026-07-10 | Completed | 100% | 31500 | 34721.9 | 3 | 8 | 0 | -3221.9
TSK-0583 | PRJ-1013 | Marketing Automation 13 | Marketing | Automation | Avery Brooks | Closeout | Closeout Task 20 | Critical | High | Vertex Systems | 2026-02-08 | 2026-02-27 |  | Not Started | 0% | 40200 | 0 | 4 |  | 0 | 40200
TSK-0584 | PRJ-1014 | Procurement Process Improvement 14 | Procurement | Process Improvement | Jordan Lee | Discovery | Discovery Task 20 | High | High | Internal Team | 2025-07-07 | 2025-08-04 | 2025-08-10 | Completed | 100% | 28200 | 33329.81 | 2 | 6 | 0 | -5129.81
TSK-0585 | PRJ-1015 | Operations Facility Upgrade 15 | Operations | Facility Upgrade | Morgan Patel | Planning | Planning Task 20 | Low | Low | BluePeak Services | 2026-03-30 | 2026-04-25 |  | In Progress | 50% | 43300 | 45340.31 | 0 |  | 0 | -2040.31
TSK-0586 | PRJ-1016 | Technology Compliance 16 | Technology | Compliance | Taylor Reed | Requirements | Requirements Task 20 | Low | High | Vertex Systems | 2026-01-01 | 2026-01-12 |  | Not Started | 0% | 22100 | 0 | 3 |  | 0 | 22100
TSK-0587 | PRJ-1017 | Finance Vendor Transition 17 | Finance | Vendor Transition | Cameron Diaz | Configuration | Configuration Task 20 | Critical | Medium | Northstar Consulting | 2025-04-05 | 2025-04-23 |  | Not Started | 0% | 23500 | 0 | 1 |  | 0 | 23500
TSK-0588 | PRJ-1018 | Human Resources System Implementation 18 | Human Resources | System Implementation | Riley Chen | Execution | Execution Task 20 | Medium | Low | Summit Partners | 2025-01-24 | 2025-02-19 |  | Not Started | 0% | 9100 | 0 | 1 |  | 0 | 9100
TSK-0589 | PRJ-1019 | Facilities Cost Reduction 19 | Facilities | Cost Reduction | Avery Brooks | Testing | Testing Task 20 | Medium | Medium | Internal Team | 2025-04-23 | 2025-05-11 |  | In Progress | 75% | 39000 | 38787.61 | 2 |  | 0 | 212.39
TSK-0590 | PRJ-1020 | Marketing Automation 20 | Marketing | Automation | Jordan Lee | Training | Training Task 20 | Medium | High | Internal Team | 2025-08-31 | 2025-09-27 |  | On Hold | 50% | 11900 | 10998.19 | 4 |  | 0 | 901.81
TSK-0591 | PRJ-1021 | Procurement Process Improvement 21 | Procurement | Process Improvement | Morgan Patel | Launch | Launch Task 20 | Medium | Medium | Internal Team | 2025-07-11 | 2025-08-07 | 2025-08-16 | Completed | 100% | 22200 | 23527.79 | 0 | 9 | 0 | -1327.79
TSK-0592 | PRJ-1022 | Operations Facility Upgrade 22 | Operations | Facility Upgrade | Taylor Reed | Closeout | Closeout Task 20 | Critical | Low | Vertex Systems | 2025-12-29 | 2026-01-16 |  | In Progress | 75% | 39400 | 41755.06 | 4 |  | 0 | -2355.06
TSK-0593 | PRJ-1023 | Technology Compliance 23 | Technology | Compliance | Cameron Diaz | Discovery | Discovery Task 20 | Medium | Medium | BluePeak Services | 2025-11-20 | 2025-11-26 | 2025-11-29 | Completed | 100% | 29200 | 33070.57 | 1 | 3 | 0 | -3870.57
TSK-0594 | PRJ-1024 | Finance Vendor Transition 24 | Finance | Vendor Transition | Riley Chen | Planning | Planning Task 20 | Critical | High | Internal Team | 2025-03-28 | 2025-04-25 |  | Not Started | 0% | 30000 | 0 | 4 |  | 0 | 30000
TSK-0595 | PRJ-1025 | Human Resources System Implementation 25 | Human Resources | System Implementation | Avery Brooks | Requirements | Requirements Task 20 | High | Medium | Northstar Consulting | 2025-12-08 | 2025-12-27 |  | In Progress | 85% | 44700 | 45316.38 | 2 |  | 0 | -616.38
TSK-0596 | PRJ-1026 | Facilities Cost Reduction 26 | Facilities | Cost Reduction | Jordan Lee | Configuration | Configuration Task 20 | Low | Low | Internal Team | 2025-08-29 | 2025-09-04 | 2025-08-30 | Completed | 100% | 12500 | 14525.63 | 3 | 0 | 0 | -2025.63
TSK-0597 | PRJ-1027 | Marketing Automation 27 | Marketing | Automation | Morgan Patel | Execution | Execution Task 20 | Low | Medium | BluePeak Services | 2026-03-03 | 2026-03-25 | 2026-03-29 | Completed | 100% | 32300 | 38049.77 | 3 | 4 | 0 | -5749.77
TSK-0598 | PRJ-1028 | Procurement Process Improvement 28 | Procurement | Process Improvement | Taylor Reed | Testing | Testing Task 20 | Medium | Medium | BluePeak Services | 2026-04-27 | 2026-05-25 |  | On Hold | 10% | 31800 | 32353.77 | 3 |  | 0 | -553.77
TSK-0599 | PRJ-1029 | Operations Facility Upgrade 29 | Operations | Facility Upgrade | Cameron Diaz | Training | Training Task 20 | Critical | Medium | BluePeak Services | 2026-03-11 | 2026-04-07 |  | In Progress | 85% | 35000 | 34681.45 | 2 |  | 0 | 318.55
TSK-0600 | PRJ-1030 | Technology Compliance 30 | Technology | Compliance | Riley Chen | Closeout | Closeout Task 20 | Low | Medium | Internal Team | 2026-01-05 | 2026-01-09 |  | In Progress | 90% | 13000 | 11710.99 | 2 |  | 0 | 1289.01
TSK-0601 | PRJ-1001 | Operations Facility Upgrade 01 | Operations | Facility Upgrade | Avery Brooks | Discovery | Discovery Task 21 | Critical | Medium | Internal Team | 2026-04-03 | 2026-04-09 |  | Completed | 0% | 34900 | 0 | 4 |  | 0 | 34900
TSK-0602 | PRJ-1002 | Technology Compliance 02 | Technology | Compliance | Jordan Lee | Planning | Planning Task 21 | Critical | Medium | Internal Team | 2025-03-22 | 2025-03-27 | 2025-03-29 | Completed | 100% | 40500 | 46150.88 | 3 | 2 | 0 | -5650.88
TSK-0603 | PRJ-1003 | Finance Vendor Transition 03 | Finance | Vendor Transition | Morgan Patel | Requirements | Requirements Task 21 | Critical | Medium | Internal Team | 2025-04-12 | 2025-04-27 | 2025-05-07 | Completed | 100% | 23900 | 27216.81 | 1 | 10 | 0 | -3316.81
TSK-0604 | PRJ-1004 | Human Resources System Implementation 04 | Human Resources | System Implementation | Taylor Reed | Configuration | Configuration Task 21 | Medium | Medium | Vertex Systems | 2026-02-06 | 2026-02-26 |  | Completed | 60% | 43000 | 46107.57 | 0 |  | 0 | -3107.57
TSK-0605 | PRJ-1005 | Facilities Cost Reduction 05 | Facilities | Cost Reduction | Cameron Diaz | Execution | Execution Task 21 | Medium | High | Internal Team | 2025-08-11 | 2025-08-26 |  | Completed | 0% | 44900 | 0 | 2 |  | 0 | 44900
TSK-0606 | PRJ-1006 | Marketing Automation 06 | Marketing | Automation | Riley Chen | Testing | Testing Task 21 | High | Low | Summit Partners | 2025-07-24 | 2025-08-16 |  | Completed | 75% | 3200 | 3092.89 | 2 |  | 0 | 107.11
TSK-0607 | PRJ-1007 | Procurement Process Improvement 07 | Procurement | Process Improvement | Avery Brooks | Training | Training Task 21 | High | High | Northstar Consulting | 2025-07-30 | 2025-08-17 |  | Completed | 0% | 29000 | 0 | 2 |  | 0 | 29000
TSK-0608 | PRJ-1008 | Operations Facility Upgrade 08 | Operations | Facility Upgrade | Jordan Lee | Launch | Launch Task 21 | Medium | Medium | Northstar Consulting | 2025-07-21 | 2025-08-05 |  | Completed | 0% | 25000 | 0 | 3 |  | 0 | 25000
TSK-0609 | PRJ-1009 | Technology Compliance 09 | Technology | Compliance | Morgan Patel | Closeout | Closeout Task 21 | High | Low | BluePeak Services | 2026-01-27 | 2026-02-09 |  | Not Started | 0% | 35800 | 0 | 1 |  | 0 | 35800
TSK-0610 | PRJ-1010 | Finance Vendor Transition 10 | Finance | Vendor Transition | Taylor Reed | Discovery | Discovery Task 21 | High | Medium | Apex Solutions | 2025-07-14 | 2025-07-21 | 2025-07-23 | Completed | 100% | 33500 | 35586.77 | 1 | 2 | 0 | -2086.77
TSK-0611 | PRJ-1011 | Human Resources System Implementation 11 | Human Resources | System Implementation | Cameron Diaz | Planning | Planning Task 21 | Critical | Medium | Internal Team | 2026-01-20 | 2026-01-23 |  | Not Started | 0% | 3700 | 0 | 1 |  | 0 | 3700
TSK-0612 | PRJ-1012 | Facilities Cost Reduction 12 | Facilities | Cost Reduction | Riley Chen | Requirements | Requirements Task 21 | Medium | Low | Northstar Consulting | 2026-02-16 | 2026-02-22 | 2026-03-08 | Completed | 100% | 36300 | 38352.25 | 4 | 14 | 0 | -2052.25
TSK-0613 | PRJ-1013 | Marketing Automation 13 | Marketing | Automation | Avery Brooks | Configuration | Configuration Task 21 | Medium | Medium | BluePeak Services | 2026-01-22 | 2026-02-04 |  | Not Started | 0% | 31300 | 0 | 1 |  | 0 | 31300
TSK-0614 | PRJ-1014 | Procurement Process Improvement 14 | Procurement | Process Improvement | Jordan Lee | Execution | Execution Task 21 | Critical | Low | Internal Team | 2025-04-04 | 2025-04-17 |  | Not Started | 0% | 13400 | 0 | 0 |  | 0 | 13400
TSK-0615 | PRJ-1015 | Operations Facility Upgrade 15 | Operations | Facility Upgrade | Morgan Patel | Testing | Testing Task 21 | Medium | Low | Internal Team | 2026-04-01 | 2026-04-05 |  | Not Started | 0% | 35900 | 0 | 0 |  | 0 | 35900
TSK-0616 | PRJ-1016 | Technology Compliance 16 | Technology | Compliance | Taylor Reed | Training | Training Task 21 | Medium | High | Internal Team | 2025-08-11 | 2025-08-19 | 2025-08-18 | Completed | 100% | 13800 | 12803.35 | 2 | 0 | 0 | 996.65
TSK-0617 | PRJ-1017 | Finance Vendor Transition 17 | Finance | Vendor Transition | Cameron Diaz | Launch | Launch Task 21 | Medium | Low | Internal Team | 2025-04-01 | 2025-04-20 |  | In Progress | 40% | 42300 | 35411.53 | 1 |  | 0 | 6888.47
TSK-0618 | PRJ-1018 | Human Resources System Implementation 18 | Human Resources | System Implementation | Riley Chen | Closeout | Closeout Task 21 | Medium | Low | BluePeak Services | 2025-04-08 | 2025-04-22 |  | In Progress | 75% | 11800 | 11805.93 | 2 |  | 0 | -5.93
TSK-0619 | PRJ-1019 | Facilities Cost Reduction 19 | Facilities | Cost Reduction | Avery Brooks | Discovery | Discovery Task 21 | Low | Low | Vertex Systems | 2025-07-10 | 2025-07-29 |  | In Progress | 90% | 28800 | 31996.89 | 1 |  | 0 | -3196.89
TSK-0620 | PRJ-1020 | Marketing Automation 20 | Marketing | Automation | Jordan Lee | Planning | Planning Task 21 | Low | Low | Summit Partners | 2025-08-26 | 2025-09-13 |  | Not Started | 0% | 30700 | 0 | 3 |  | 0 | 30700
TSK-0621 | PRJ-1021 | Procurement Process Improvement 21 | Procurement | Process Improvement | Morgan Patel | Requirements | Requirements Task 21 | Medium | Low | Internal Team | 2025-08-29 | 2025-09-02 |  | Not Started | 0% | 3800 | 0 | 0 |  | 0 | 3800
TSK-0622 | PRJ-1022 | Operations Facility Upgrade 22 | Operations | Facility Upgrade | Taylor Reed | Configuration | Configuration Task 21 | Low | Low | Internal Team | 2025-11-20 | 2025-12-16 |  | In Progress | 75% | 15700 | 15778.38 | 2 |  | 0 | -78.38
TSK-0623 | PRJ-1023 | Technology Compliance 23 | Technology | Compliance | Cameron Diaz | Execution | Execution Task 21 | Medium | Medium | Internal Team | 2025-12-05 | 2025-12-15 | 2025-12-27 | Completed | 100% | 39300 | 37920.27 | 2 | 12 | 0 | 1379.73
TSK-0624 | PRJ-1024 | Finance Vendor Transition 24 | Finance | Vendor Transition | Riley Chen | Testing | Testing Task 21 | Medium | Low | BluePeak Services | 2025-02-25 | 2025-03-06 | 2025-03-01 | Completed | 100% | 7400 | 7772.84 | 1 | 0 | 0 | -372.84
TSK-0625 | PRJ-1025 | Human Resources System Implementation 25 | Human Resources | System Implementation | Avery Brooks | Training | Training Task 21 | Critical | Low | Internal Team | 2026-03-14 | 2026-03-18 |  | In Progress | 25% | 38500 | 33388.95 | 0 |  | 0 | 5111.05
TSK-0626 | PRJ-1026 | Facilities Cost Reduction 26 | Facilities | Cost Reduction | Jordan Lee | Launch | Launch Task 21 | Medium | High | Northstar Consulting | 2025-05-30 | 2025-06-20 |  | On Hold | 20% | 5300 | 5762.94 | 4 |  | 0 | -462.94
TSK-0627 | PRJ-1027 | Marketing Automation 27 | Marketing | Automation | Morgan Patel | Closeout | Closeout Task 21 | Critical | Medium | Summit Partners | 2026-03-19 | 2026-03-22 | 2026-03-18 | Completed | 100% | 33500 | 34238.98 | 3 | 0 | 0 | -738.98
TSK-0628 | PRJ-1028 | Procurement Process Improvement 28 | Procurement | Process Improvement | Taylor Reed | Discovery | Discovery Task 21 | High | High | Northstar Consulting | 2026-01-11 | 2026-02-01 | 2026-02-01 | Completed | 100% | 44600 | 48450.9 | 3 | 0 | 0 | -3850.9
TSK-0629 | PRJ-1029 | Operations Facility Upgrade 29 | Operations | Facility Upgrade | Cameron Diaz | Planning | Planning Task 21 | Medium | Low | Summit Partners | 2026-01-25 | 2026-02-11 | 2026-02-05 | Completed | 100% | 5100 | 5218.68 | 0 | 0 | 0 | -118.68
TSK-0630 | PRJ-1030 | Technology Compliance 30 | Technology | Compliance | Riley Chen | Configuration | Configuration Task 21 | Medium | Low | Internal Team | 2025-12-12 | 2026-01-04 |  | On Hold | 10% | 22400 | 21550.59 | 3 |  | 0 | 849.41
TSK-0631 | PRJ-1001 | Operations Facility Upgrade 01 | Operations | Facility Upgrade | Avery Brooks | Execution | Execution Task 22 | High | Medium | Internal Team | 2026-03-25 | 2026-04-11 | 2026-04-18 | Completed | 100% | 35900 | 33756.59 | 1 | 7 | 0 | 2143.41
TSK-0632 | PRJ-1002 | Technology Compliance 02 | Technology | Compliance | Jordan Lee | Testing | Testing Task 22 | High | High | Internal Team | 2025-05-28 | 2025-06-16 |  | Completed | 0% | 20000 | 0 | 3 |  | 0 | 20000
TSK-0633 | PRJ-1003 | Finance Vendor Transition 03 | Finance | Vendor Transition | Morgan Patel | Training | Training Task 22 | Medium | Medium | Vertex Systems | 2025-02-07 | 2025-03-01 | 2025-03-20 | Completed | 100% | 33500 | 42532.61 | 3 | 19 | 0 | -9032.61
TSK-0634 | PRJ-1004 | Human Resources System Implementation 04 | Human Resources | System Implementation | Taylor Reed | Launch | Launch Task 22 | High | High | Internal Team | 2026-04-23 | 2026-05-10 | 2026-05-09 | Completed | 100% | 25800 | 28923.38 | 5 | 0 | 0 | -3123.38
TSK-0635 | PRJ-1005 | Facilities Cost Reduction 05 | Facilities | Cost Reduction | Cameron Diaz | Closeout | Closeout Task 22 | Medium | High | Internal Team | 2025-06-24 | 2025-07-17 | 2025-07-23 | Completed | 100% | 42400 | 35037.95 | 1 | 6 | 0 | 7362.05
TSK-0636 | PRJ-1006 | Marketing Automation 06 | Marketing | Automation | Riley Chen | Discovery | Discovery Task 22 | Medium | Medium | Internal Team | 2025-08-09 | 2025-08-20 | 2025-08-20 | Completed | 100% | 17700 | 18357.34 | 0 | 0 | 0 | -657.34
TSK-0637 | PRJ-1007 | Procurement Process Improvement 07 | Procurement | Process Improvement | Avery Brooks | Planning | Planning Task 22 | High | Low | Apex Solutions | 2025-09-13 | 2025-09-25 |  | Completed | 50% | 36300 | 38413.82 | 3 |  | 0 | -2113.82
TSK-0638 | PRJ-1008 | Operations Facility Upgrade 08 | Operations | Facility Upgrade | Jordan Lee | Requirements | Requirements Task 22 | Critical | Low | BluePeak Services | 2025-07-13 | 2025-07-18 |  | Completed | 0% | 40600 | 0 | 0 |  | 0 | 40600
TSK-0639 | PRJ-1009 | Technology Compliance 09 | Technology | Compliance | Morgan Patel | Configuration | Configuration Task 22 | Low | Low | Vertex Systems | 2026-05-25 | 2026-06-01 | 2026-06-20 | Completed | 100% | 24100 | 23042.96 | 0 | 19 | 0 | 1057.04
TSK-0640 | PRJ-1010 | Finance Vendor Transition 10 | Finance | Vendor Transition | Taylor Reed | Execution | Execution Task 22 | Critical | Medium | Internal Team | 2025-05-26 | 2025-06-11 |  | In Progress | 85% | 2400 | 2468.82 | 2 |  | 0 | -68.82
TSK-0641 | PRJ-1011 | Human Resources System Implementation 11 | Human Resources | System Implementation | Cameron Diaz | Testing | Testing Task 22 | High | Medium | Apex Solutions | 2026-03-13 | 2026-03-29 | 2026-03-24 | Completed | 100% | 22600 | 19425.22 | 1 | 0 | 0 | 3174.78
TSK-0642 | PRJ-1012 | Facilities Cost Reduction 12 | Facilities | Cost Reduction | Riley Chen | Training | Training Task 22 | Medium | Low | Apex Solutions | 2026-04-08 | 2026-04-16 | 2026-04-11 | Completed | 100% | 11400 | 10911.29 | 2 | 0 | 0 | 488.71
TSK-0643 | PRJ-1013 | Marketing Automation 13 | Marketing | Automation | Avery Brooks | Launch | Launch Task 22 | High | Low | Internal Team | 2025-11-23 | 2025-12-15 | 2025-12-16 | Completed | 100% | 43800 | 40840.6 | 2 | 1 | 0 | 2959.4
TSK-0644 | PRJ-1014 | Procurement Process Improvement 14 | Procurement | Process Improvement | Jordan Lee | Closeout | Closeout Task 22 | High | Low | Internal Team | 2025-03-01 | 2025-03-14 | 2025-03-07 | Completed | 100% | 20700 | 20060.05 | 2 | 0 | 0 | 639.95
TSK-0645 | PRJ-1015 | Operations Facility Upgrade 15 | Operations | Facility Upgrade | Morgan Patel | Discovery | Discovery Task 22 | High | Medium | BluePeak Services | 2025-12-11 | 2025-12-25 |  | In Progress | 40% | 24700 | 25635.08 | 2 |  | 0 | -935.08
TSK-0646 | PRJ-1016 | Technology Compliance 16 | Technology | Compliance | Taylor Reed | Planning | Planning Task 22 | Critical | Medium | BluePeak Services | 2025-10-30 | 2025-11-06 |  | Not Started | 0% | 33600 | 0 | 2 |  | 0 | 33600
TSK-0647 | PRJ-1017 | Finance Vendor Transition 17 | Finance | Vendor Transition | Cameron Diaz | Requirements | Requirements Task 22 | High | Low | Internal Team | 2025-06-17 | 2025-07-11 |  | Not Started | 0% | 26100 | 0 | 0 |  | 0 | 26100
TSK-0648 | PRJ-1018 | Human Resources System Implementation 18 | Human Resources | System Implementation | Riley Chen | Configuration | Configuration Task 22 | High | Medium | BluePeak Services | 2025-02-25 | 2025-03-21 | 2025-03-20 | Completed | 100% | 38100 | 42829.68 | 1 | 0 | 0 | -4729.68
TSK-0649 | PRJ-1019 | Facilities Cost Reduction 19 | Facilities | Cost Reduction | Avery Brooks | Execution | Execution Task 22 | Low | Medium | Northstar Consulting | 2025-04-19 | 2025-05-17 | 2025-05-20 | Completed | 100% | 13600 | 15713.56 | 2 | 3 | 0 | -2113.56
TSK-0650 | PRJ-1020 | Marketing Automation 20 | Marketing | Automation | Jordan Lee | Testing | Testing Task 22 | Medium | Medium | Internal Team | 2025-09-05 | 2025-09-20 |  | In Progress | 50% | 27700 | 27221.83 | 2 |  | 0 | 478.17
TSK-0651 | PRJ-1021 | Procurement Process Improvement 21 | Procurement | Process Improvement | Morgan Patel | Training | Training Task 22 | High | Low | Vertex Systems | 2025-08-22 | 2025-09-05 |  | In Progress | 25% | 13900 | 11673 | 4 |  | 0 | 2227
TSK-0652 | PRJ-1022 | Operations Facility Upgrade 22 | Operations | Facility Upgrade | Taylor Reed | Launch | Launch Task 22 | High | Low | Vertex Systems | 2026-01-12 | 2026-02-07 |  | On Hold | 50% | 14100 | 15792.08 | 0 |  | 0 | -1692.08
TSK-0653 | PRJ-1023 | Technology Compliance 23 | Technology | Compliance | Cameron Diaz | Closeout | Closeout Task 22 | Medium | High | Internal Team | 2026-04-09 | 2026-05-01 |  | Not Started | 0% | 10500 | 0 | 3 |  | 0 | 10500
TSK-0654 | PRJ-1024 | Finance Vendor Transition 24 | Finance | Vendor Transition | Riley Chen | Discovery | Discovery Task 22 | Critical | Low | BluePeak Services | 2025-04-25 | 2025-04-30 |  | Not Started | 0% | 29300 | 0 | 2 |  | 0 | 29300
TSK-0655 | PRJ-1025 | Human Resources System Implementation 25 | Human Resources | System Implementation | Avery Brooks | Planning | Planning Task 22 | Medium | Medium | BluePeak Services | 2025-12-10 | 2025-12-18 | 2025-12-18 | Completed | 100% | 37300 | 42665.72 | 1 | 0 | 0 | -5365.72
TSK-0656 | PRJ-1026 | Facilities Cost Reduction 26 | Facilities | Cost Reduction | Jordan Lee | Requirements | Requirements Task 22 | Medium | Medium | Internal Team | 2025-04-17 | 2025-04-24 |  | In Progress | 85% | 37800 | 43780.41 | 0 |  | 0 | -5980.41
TSK-0657 | PRJ-1027 | Marketing Automation 27 | Marketing | Automation | Morgan Patel | Configuration | Configuration Task 22 | High | Low | Apex Solutions | 2026-03-10 | 2026-03-13 |  | Not Started | 0% | 13600 | 0 | 2 |  | 0 | 13600
TSK-0658 | PRJ-1028 | Procurement Process Improvement 28 | Procurement | Process Improvement | Taylor Reed | Execution | Execution Task 22 | High | Medium | Apex Solutions | 2026-02-08 | 2026-03-03 | 2026-03-05 | Completed | 100% | 43900 | 46719.62 | 1 | 2 | 0 | -2819.62
TSK-0659 | PRJ-1029 | Operations Facility Upgrade 29 | Operations | Facility Upgrade | Cameron Diaz | Testing | Testing Task 22 | High | Low | Internal Team | 2026-05-28 | 2026-06-01 |  | Not Started | 0% | 21600 | 0 | 0 |  | 0 | 21600
TSK-0660 | PRJ-1030 | Technology Compliance 30 | Technology | Compliance | Riley Chen | Launch | Launch Task 22 | Low | Low | Northstar Consulting | 2026-01-11 | 2026-01-15 |  | In Progress | 75% | 29300 | 31759.9 | 2 |  | 0 | -2459.9
TSK-0661 | PRJ-1001 | Operations Facility Upgrade 01 | Operations | Facility Upgrade | Avery Brooks | Closeout | Closeout Task 23 | High | Medium | Northstar Consulting | 2026-01-10 | 2026-01-30 |  | Completed | 50% | 37500 | 36862.71 | 1 |  | 0 | 637.29
TSK-0662 | PRJ-1002 | Technology Compliance 02 | Technology | Compliance | Jordan Lee | Discovery | Discovery Task 23 | High | Medium | Internal Team | 2025-07-30 | 2025-08-13 | 2025-08-23 | Completed | 100% | 17700 | 18244.46 | 1 | 10 | 0 | -544.46
TSK-0663 | PRJ-1003 | Finance Vendor Transition 03 | Finance | Vendor Transition | Morgan Patel | Planning | Planning Task 23 | Critical | Low | Internal Team | 2025-03-15 | 2025-04-13 |  | Completed | 75% | 28200 | 29032.06 | 2 |  | 0 | -832.06
TSK-0664 | PRJ-1004 | Human Resources System Implementation 04 | Human Resources | System Implementation | Taylor Reed | Requirements | Requirements Task 23 | Medium | Medium | Vertex Systems | 2026-02-18 | 2026-03-06 | 2026-03-01 | Completed | 100% | 4800 | 5397.74 | 0 | 0 | 0 | -597.74
TSK-0665 | PRJ-1005 | Facilities Cost Reduction 05 | Facilities | Cost Reduction | Cameron Diaz | Configuration | Configuration Task 23 | Medium | Low | Internal Team | 2025-09-16 | 2025-10-08 | 2025-10-14 | Completed | 100% | 14800 | 14909.14 | 1 | 6 | 0 | -109.14
TSK-0666 | PRJ-1006 | Marketing Automation 06 | Marketing | Automation | Riley Chen | Execution | Execution Task 23 | Medium | Medium | Vertex Systems | 2025-07-28 | 2025-08-04 |  | Completed | 25% | 20000 | 19295.23 | 2 |  | 0 | 704.77
TSK-0667 | PRJ-1007 | Procurement Process Improvement 07 | Procurement | Process Improvement | Avery Brooks | Testing | Testing Task 23 | Low | Low | Internal Team | 2025-06-19 | 2025-06-25 |  | Completed | 0% | 30200 | 0 | 0 |  | 0 | 30200
TSK-0668 | PRJ-1008 | Operations Facility Upgrade 08 | Operations | Facility Upgrade | Jordan Lee | Training | Training Task 23 | Critical | Low | Internal Team | 2025-03-20 | 2025-04-16 |  | Completed | 0% | 6900 | 0 | 0 |  | 0 | 6900
TSK-0669 | PRJ-1009 | Technology Compliance 09 | Technology | Compliance | Morgan Patel | Launch | Launch Task 23 | Medium | Medium | Internal Team | 2026-02-24 | 2026-03-26 | 2026-03-22 | Completed | 100% | 13600 | 12649.33 | 1 | 0 | 0 | 950.67
TSK-0670 | PRJ-1010 | Finance Vendor Transition 10 | Finance | Vendor Transition | Taylor Reed | Closeout | Closeout Task 23 | High | Medium | Northstar Consulting | 2025-07-06 | 2025-07-27 |  | Not Started | 0% | 37200 | 0 | 0 |  | 0 | 37200
TSK-0671 | PRJ-1011 | Human Resources System Implementation 11 | Human Resources | System Implementation | Cameron Diaz | Discovery | Discovery Task 23 | High | High | Internal Team | 2026-05-04 | 2026-05-07 |  | On Hold | 10% | 41700 | 52479.54 | 2 |  | 0 | -10779.54
TSK-0672 | PRJ-1012 | Facilities Cost Reduction 12 | Facilities | Cost Reduction | Riley Chen | Planning | Planning Task 23 | Medium | Medium | Internal Team | 2026-02-16 | 2026-02-24 | 2026-03-05 | Completed | 100% | 23900 | 24054.26 | 0 | 9 | 0 | -154.26
TSK-0673 | PRJ-1013 | Marketing Automation 13 | Marketing | Automation | Avery Brooks | Requirements | Requirements Task 23 | Medium | Low | Apex Solutions | 2026-02-15 | 2026-03-14 |  | In Progress | 50% | 25700 | 28839.62 | 2 |  | 0 | -3139.62
TSK-0674 | PRJ-1014 | Procurement Process Improvement 14 | Procurement | Process Improvement | Jordan Lee | Configuration | Configuration Task 23 | Low | Low | Northstar Consulting | 2025-05-09 | 2025-06-02 |  | On Hold | 50% | 11300 | 11805.78 | 0 |  | 0 | -505.78
TSK-0675 | PRJ-1015 | Operations Facility Upgrade 15 | Operations | Facility Upgrade | Morgan Patel | Execution | Execution Task 23 | Medium | High | BluePeak Services | 2026-03-05 | 2026-03-29 |  | In Progress | 25% | 44900 | 55915.77 | 2 |  | 0 | -11015.77
TSK-0676 | PRJ-1016 | Technology Compliance 16 | Technology | Compliance | Taylor Reed | Testing | Testing Task 23 | Medium | Medium | Internal Team | 2025-09-15 | 2025-09-30 |  | In Progress | 75% | 44000 | 44999.68 | 2 |  | 0 | -999.68
TSK-0677 | PRJ-1017 | Finance Vendor Transition 17 | Finance | Vendor Transition | Cameron Diaz | Training | Training Task 23 | Medium | Low | Internal Team | 2025-03-14 | 2025-04-05 | 2025-03-23 | Completed | 100% | 19100 | 19719.33 | 3 | 0 | 0 | -619.33
TSK-0678 | PRJ-1018 | Human Resources System Implementation 18 | Human Resources | System Implementation | Riley Chen | Launch | Launch Task 23 | Medium | Medium | Vertex Systems | 2025-03-31 | 2025-04-27 | 2025-04-25 | Completed | 100% | 22200 | 20704.08 | 1 | 0 | 0 | 1495.92
TSK-0679 | PRJ-1019 | Facilities Cost Reduction 19 | Facilities | Cost Reduction | Avery Brooks | Closeout | Closeout Task 23 | Medium | Low | Vertex Systems | 2025-03-21 | 2025-03-27 |  | In Progress | 60% | 11500 | 10952.43 | 1 |  | 0 | 547.57
TSK-0680 | PRJ-1020 | Marketing Automation 20 | Marketing | Automation | Jordan Lee | Discovery | Discovery Task 23 | High | Medium | Apex Solutions | 2025-05-03 | 2025-05-11 |  | In Progress | 85% | 15700 | 15863.8 | 1 |  | 0 | -163.8
TSK-0681 | PRJ-1021 | Procurement Process Improvement 21 | Procurement | Process Improvement | Morgan Patel | Planning | Planning Task 23 | High | Medium | Apex Solutions | 2025-09-08 | 2025-10-06 | 2025-10-17 | Completed | 100% | 14300 | 12721.27 | 2 | 11 | 0 | 1578.73
TSK-0682 | PRJ-1022 | Operations Facility Upgrade 22 | Operations | Facility Upgrade | Taylor Reed | Requirements | Requirements Task 23 | Medium | Medium | Apex Solutions | 2025-09-25 | 2025-10-22 |  | Not Started | 0% | 20200 | 0 | 1 |  | 0 | 20200
TSK-0683 | PRJ-1023 | Technology Compliance 23 | Technology | Compliance | Cameron Diaz | Configuration | Configuration Task 23 | Medium | Low | Apex Solutions | 2025-11-18 | 2025-11-26 | 2025-12-02 | Completed | 100% | 32200 | 30529.26 | 1 | 6 | 0 | 1670.74
TSK-0684 | PRJ-1024 | Finance Vendor Transition 24 | Finance | Vendor Transition | Riley Chen | Execution | Execution Task 23 | High | Low | Internal Team | 2025-05-24 | 2025-06-17 | 2025-06-19 | Completed | 100% | 25000 | 22028.53 | 2 | 2 | 0 | 2971.47
TSK-0685 | PRJ-1025 | Human Resources System Implementation 25 | Human Resources | System Implementation | Avery Brooks | Testing | Testing Task 23 | Medium | Low | Internal Team | 2026-01-24 | 2026-02-15 | 2026-02-18 | Completed | 100% | 4200 | 3908.04 | 1 | 3 | 0 | 291.96
TSK-0686 | PRJ-1026 | Facilities Cost Reduction 26 | Facilities | Cost Reduction | Jordan Lee | Training | Training Task 23 | Medium | Medium | Northstar Consulting | 2025-07-13 | 2025-07-28 |  | Not Started | 0% | 16500 | 0 | 1 |  | 0 | 16500
TSK-0687 | PRJ-1027 | Marketing Automation 27 | Marketing | Automation | Morgan Patel | Launch | Launch Task 23 | High | Low | Northstar Consulting | 2026-01-28 | 2026-02-22 |  | Not Started | 0% | 14800 | 0 | 1 |  | 0 | 14800
TSK-0688 | PRJ-1028 | Procurement Process Improvement 28 | Procurement | Process Improvement | Taylor Reed | Closeout | Closeout Task 23 | Medium | Low | Summit Partners | 2026-04-28 | 2026-05-17 | 2026-05-20 | Completed | 100% | 13100 | 12722.86 | 0 | 3 | 0 | 377.14
TSK-0689 | PRJ-1029 | Operations Facility Upgrade 29 | Operations | Facility Upgrade | Cameron Diaz | Discovery | Discovery Task 23 | Critical | Low | Internal Team | 2026-05-26 | 2026-06-01 | 2026-06-11 | Completed | 100% | 16100 | 17983.71 | 0 | 10 | 0 | -1883.71
TSK-0690 | PRJ-1030 | Technology Compliance 30 | Technology | Compliance | Riley Chen | Requirements | Requirements Task 23 | Medium | Medium | Internal Team | 2026-01-31 | 2026-02-09 | 2026-02-11 | Completed | 100% | 38400 | 41039.7 | 0 | 2 | 0 | -2639.7
TSK-0691 | PRJ-1001 | Operations Facility Upgrade 01 | Operations | Facility Upgrade | Avery Brooks | Configuration | Configuration Task 24 | Medium | Low | Internal Team | 2026-04-24 | 2026-05-09 | 2026-04-29 | Completed | 100% | 32700 | 26968.28 | 0 | 0 | 0 | 5731.72
TSK-0692 | PRJ-1002 | Technology Compliance 02 | Technology | Compliance | Jordan Lee | Execution | Execution Task 24 | Medium | Medium | Apex Solutions | 2025-06-21 | 2025-06-30 |  | Completed | 25% | 29800 | 28325.62 | 1 |  | 0 | 1474.38
TSK-0693 | PRJ-1003 | Finance Vendor Transition 03 | Finance | Vendor Transition | Morgan Patel | Testing | Testing Task 24 | Medium | Medium | Internal Team | 2025-04-30 | 2025-05-11 | 2025-05-25 | Completed | 100% | 21200 | 21748.17 | 1 | 14 | 0 | -548.17
TSK-0694 | PRJ-1004 | Human Resources System Implementation 04 | Human Resources | System Implementation | Taylor Reed | Training | Training Task 24 | Low | Medium | Summit Partners | 2026-06-16 | 2026-07-04 |  | Completed | 90% | 33800 | 25913.3 | 2 |  | 0 | 7886.7
TSK-0695 | PRJ-1005 | Facilities Cost Reduction 05 | Facilities | Cost Reduction | Cameron Diaz | Launch | Launch Task 24 | Medium | Medium | Vertex Systems | 2025-09-14 | 2025-10-05 | 2025-10-11 | Completed | 100% | 21600 | 22616.28 | 2 | 6 | 0 | -1016.28
TSK-0696 | PRJ-1006 | Marketing Automation 06 | Marketing | Automation | Riley Chen | Closeout | Closeout Task 24 | High | Medium | Internal Team | 2025-05-27 | 2025-06-19 |  | Completed | 60% | 13100 | 15744.77 | 2 |  | 0 | -2644.77
TSK-0697 | PRJ-1007 | Procurement Process Improvement 07 | Procurement | Process Improvement | Avery Brooks | Discovery | Discovery Task 24 | High | Low | Internal Team | 2025-06-07 | 2025-06-16 |  | Completed | 0% | 36200 | 0 | 1 |  | 0 | 36200
TSK-0698 | PRJ-1008 | Operations Facility Upgrade 08 | Operations | Facility Upgrade | Jordan Lee | Planning | Planning Task 24 | Critical | Low | BluePeak Services | 2025-05-08 | 2025-05-16 |  | Completed | 25% | 12700 | 14449.19 | 2 |  | 0 | -1749.19
TSK-0699 | PRJ-1009 | Technology Compliance 09 | Technology | Compliance | Morgan Patel | Requirements | Requirements Task 24 | Medium | High | BluePeak Services | 2026-05-22 | 2026-06-19 |  | Not Started | 0% | 38900 | 0 | 5 |  | 0 | 38900
TSK-0700 | PRJ-1010 | Finance Vendor Transition 10 | Finance | Vendor Transition | Taylor Reed | Configuration | Configuration Task 24 | High | High | Internal Team | 2025-05-31 | 2025-06-24 | 2025-07-01 | Completed | 100% | 5400 | 6671.29 | 2 | 7 | 0 | -1271.29
TSK-0701 | PRJ-1011 | Human Resources System Implementation 11 | Human Resources | System Implementation | Cameron Diaz | Execution | Execution Task 24 | Medium | Low | Vertex Systems | 2026-01-17 | 2026-02-05 | 2026-01-27 | Completed | 100% | 24300 | 22550.76 | 1 | 0 | 0 | 1749.24
TSK-0702 | PRJ-1012 | Facilities Cost Reduction 12 | Facilities | Cost Reduction | Riley Chen | Testing | Testing Task 24 | High | Medium | Internal Team | 2026-06-18 | 2026-07-14 |  | In Progress | 85% | 33900 | 34614.16 | 3 |  | 0 | -714.16
TSK-0703 | PRJ-1013 | Marketing Automation 13 | Marketing | Automation | Avery Brooks | Training | Training Task 24 | Low | Low | Internal Team | 2026-01-24 | 2026-02-04 | 2026-02-04 | Completed | 100% | 3900 | 3327.31 | 1 | 0 | 0 | 572.69
TSK-0704 | PRJ-1014 | Procurement Process Improvement 14 | Procurement | Process Improvement | Jordan Lee | Launch | Launch Task 24 | Low | Medium | Apex Solutions | 2025-04-23 | 2025-05-04 | 2025-05-12 | Completed | 100% | 32600 | 31938.27 | 2 | 8 | 0 | 661.73
TSK-0705 | PRJ-1015 | Operations Facility Upgrade 15 | Operations | Facility Upgrade | Morgan Patel | Closeout | Closeout Task 24 | Critical | Medium | Summit Partners | 2025-11-17 | 2025-12-12 | 2025-12-13 | Completed | 100% | 30700 | 31251.63 | 3 | 1 | 0 | -551.63
TSK-0706 | PRJ-1016 | Technology Compliance 16 | Technology | Compliance | Taylor Reed | Discovery | Discovery Task 24 | High | Medium | BluePeak Services | 2025-09-10 | 2025-09-30 | 2025-10-06 | Completed | 100% | 41100 | 38425.34 | 0 | 6 | 0 | 2674.66
TSK-0707 | PRJ-1017 | Finance Vendor Transition 17 | Finance | Vendor Transition | Cameron Diaz | Planning | Planning Task 24 | Medium | Low | Summit Partners | 2025-03-23 | 2025-04-04 |  | In Progress | 40% | 41300 | 49944.22 | 0 |  | 0 | -8644.22
TSK-0708 | PRJ-1018 | Human Resources System Implementation 18 | Human Resources | System Implementation | Riley Chen | Requirements | Requirements Task 24 | High | Low | Internal Team | 2025-02-10 | 2025-03-11 | 2025-03-02 | Completed | 100% | 22900 | 22886.3 | 0 | 0 | 0 | 13.7
TSK-0709 | PRJ-1019 | Facilities Cost Reduction 19 | Facilities | Cost Reduction | Avery Brooks | Configuration | Configuration Task 24 | Medium | Low | BluePeak Services | 2025-03-19 | 2025-04-17 |  | Not Started | 0% | 12900 | 0 | 2 |  | 0 | 12900
TSK-0710 | PRJ-1020 | Marketing Automation 20 | Marketing | Automation | Jordan Lee | Execution | Execution Task 24 | High | Medium | Internal Team | 2025-05-04 | 2025-05-31 |  | Not Started | 0% | 29400 | 0 | 0 |  | 0 | 29400
TSK-0711 | PRJ-1021 | Procurement Process Improvement 21 | Procurement | Process Improvement | Morgan Patel | Testing | Testing Task 24 | Medium | Low | Northstar Consulting | 2025-07-24 | 2025-08-14 |  | Not Started | 0% | 8400 | 0 | 1 |  | 0 | 8400
TSK-0712 | PRJ-1022 | Operations Facility Upgrade 22 | Operations | Facility Upgrade | Taylor Reed | Training | Training Task 24 | High | Medium | Summit Partners | 2026-01-04 | 2026-02-01 | 2026-01-20 | Completed | 100% | 7300 | 7936.03 | 3 | 0 | 0 | -636.03
TSK-0713 | PRJ-1023 | Technology Compliance 23 | Technology | Compliance | Cameron Diaz | Launch | Launch Task 24 | Medium | Low | Internal Team | 2026-02-12 | 2026-02-20 |  | In Progress | 60% | 42600 | 49023.04 | 2 |  | 0 | -6423.04
TSK-0714 | PRJ-1024 | Finance Vendor Transition 24 | Finance | Vendor Transition | Riley Chen | Closeout | Closeout Task 24 | Critical | High | Northstar Consulting | 2025-03-18 | 2025-03-23 |  | On Hold | 20% | 12900 | 13130.72 | 3 |  | 0 | -230.72
TSK-0715 | PRJ-1025 | Human Resources System Implementation 25 | Human Resources | System Implementation | Avery Brooks | Discovery | Discovery Task 24 | High | Medium | Internal Team | 2026-01-22 | 2026-01-30 |  | On Hold | 10% | 2100 | 2082.78 | 0 |  | 0 | 17.22
TSK-0716 | PRJ-1026 | Facilities Cost Reduction 26 | Facilities | Cost Reduction | Jordan Lee | Planning | Planning Task 24 | Critical | Medium | Apex Solutions | 2025-06-13 | 2025-07-08 |  | In Progress | 90% | 36900 | 36507.6 | 1 |  | 0 | 392.4
TSK-0717 | PRJ-1027 | Marketing Automation 27 | Marketing | Automation | Morgan Patel | Requirements | Requirements Task 24 | Medium | Low | Internal Team | 2026-03-03 | 2026-04-01 |  | In Progress | 85% | 9700 | 11652.44 | 2 |  | 0 | -1952.44
TSK-0718 | PRJ-1028 | Procurement Process Improvement 28 | Procurement | Process Improvement | Taylor Reed | Configuration | Configuration Task 24 | Low | High | Internal Team | 2026-03-29 | 2026-04-08 |  | In Progress | 85% | 29700 | 37026.97 | 4 |  | 0 | -7326.97
TSK-0719 | PRJ-1029 | Operations Facility Upgrade 29 | Operations | Facility Upgrade | Cameron Diaz | Execution | Execution Task 24 | High | High | Internal Team | 2026-02-23 | 2026-03-20 |  | In Progress | 60% | 33500 | 37971.76 | 3 |  | 0 | -4471.76
TSK-0720 | PRJ-1030 | Technology Compliance 30 | Technology | Compliance | Riley Chen | Training | Training Task 24 | Low | Low | Internal Team | 2026-01-10 | 2026-02-01 | 2026-02-06 | Completed | 100% | 43600 | 37976.04 | 0 | 5 | 0 | 5623.96
TSK-0721 | PRJ-1001 | Operations Facility Upgrade 01 | Operations | Facility Upgrade | Avery Brooks | Launch | Launch Task 25 | Low | Low | Northstar Consulting | 2026-02-14 | 2026-03-01 | 2026-03-13 | Completed | 100% | 3300 | 3931.87 | 2 | 12 | 0 | -631.87
TSK-0722 | PRJ-1002 | Technology Compliance 02 | Technology | Compliance | Jordan Lee | Closeout | Closeout Task 25 | Medium | Low | Apex Solutions | 2025-03-26 | 2025-04-08 | 2025-04-14 | Completed | 100% | 20300 | 20579.51 | 2 | 6 | 0 | -279.51
TSK-0723 | PRJ-1003 | Finance Vendor Transition 03 | Finance | Vendor Transition | Morgan Patel | Discovery | Discovery Task 25 | Critical | Low | BluePeak Services | 2025-03-30 | 2025-04-25 |  | Completed | 60% | 13800 | 15572.79 | 0 |  | 0 | -1772.79
TSK-0724 | PRJ-1004 | Human Resources System Implementation 04 | Human Resources | System Implementation | Taylor Reed | Planning | Planning Task 25 | High | Low | Internal Team | 2026-03-03 | 2026-03-16 | 2026-03-01 | Completed | 100% | 25700 | 26593.23 | 3 | 0 | 0 | -893.23
TSK-0725 | PRJ-1005 | Facilities Cost Reduction 05 | Facilities | Cost Reduction | Cameron Diaz | Requirements | Requirements Task 25 | Medium | Low | Internal Team | 2025-07-11 | 2025-07-15 | 2025-07-12 | Completed | 100% | 8600 | 8312.16 | 1 | 0 | 0 | 287.84
TSK-0726 | PRJ-1006 | Marketing Automation 06 | Marketing | Automation | Riley Chen | Configuration | Configuration Task 25 | High | Low | Internal Team | 2025-10-01 | 2025-10-19 |  | Completed | 25% | 38300 | 40516.57 | 1 |  | 0 | -2216.57
TSK-0727 | PRJ-1007 | Procurement Process Improvement 07 | Procurement | Process Improvement | Avery Brooks | Execution | Execution Task 25 | Low | High | Internal Team | 2025-06-12 | 2025-07-08 | 2025-07-08 | Completed | 100% | 27000 | 35077.75 | 0 | 0 | 0 | -8077.75
TSK-0728 | PRJ-1008 | Operations Facility Upgrade 08 | Operations | Facility Upgrade | Jordan Lee | Testing | Testing Task 25 | Medium | Medium | Internal Team | 2025-04-06 | 2025-04-16 | 2025-04-09 | Completed | 100% | 30900 | 32110.41 | 2 | 0 | 0 | -1210.41
TSK-0729 | PRJ-1009 | Technology Compliance 09 | Technology | Compliance | Morgan Patel | Training | Training Task 25 | High | Medium | Internal Team | 2026-02-14 | 2026-03-15 |  | In Progress | 25% | 5000 | 5492.06 | 0 |  | 0 | -492.06
TSK-0730 | PRJ-1010 | Finance Vendor Transition 10 | Finance | Vendor Transition | Taylor Reed | Launch | Launch Task 25 | Medium | High | Northstar Consulting | 2025-02-28 | 2025-03-13 |  | On Hold | 65% | 42900 | 42432.17 | 5 |  | 0 | 467.83
TSK-0731 | PRJ-1011 | Human Resources System Implementation 11 | Human Resources | System Implementation | Cameron Diaz | Closeout | Closeout Task 25 | High | High | Apex Solutions | 2026-02-10 | 2026-03-12 |  | Not Started | 0% | 29500 | 0 | 3 |  | 0 | 29500
TSK-0732 | PRJ-1012 | Facilities Cost Reduction 12 | Facilities | Cost Reduction | Riley Chen | Discovery | Discovery Task 25 | Low | High | Internal Team | 2026-05-02 | 2026-05-13 |  | Not Started | 0% | 43500 | 0 | 3 |  | 0 | 43500
TSK-0733 | PRJ-1013 | Marketing Automation 13 | Marketing | Automation | Avery Brooks | Planning | Planning Task 25 | High | Low | Vertex Systems | 2025-12-23 | 2026-01-15 | 2026-01-15 | Completed | 100% | 22900 | 22305.97 | 0 | 0 | 0 | 594.03
TSK-0734 | PRJ-1014 | Procurement Process Improvement 14 | Procurement | Process Improvement | Jordan Lee | Requirements | Requirements Task 25 | Medium | Medium | Internal Team | 2025-03-15 | 2025-04-13 |  | In Progress | 40% | 22800 | 25129.84 | 3 |  | 0 | -2329.84
TSK-0735 | PRJ-1015 | Operations Facility Upgrade 15 | Operations | Facility Upgrade | Morgan Patel | Configuration | Configuration Task 25 | Medium | Low | Vertex Systems | 2026-02-06 | 2026-02-28 |  | In Progress | 85% | 20000 | 18749.75 | 2 |  | 0 | 1250.25
TSK-0736 | PRJ-1016 | Technology Compliance 16 | Technology | Compliance | Taylor Reed | Execution | Execution Task 25 | Medium | Low | Vertex Systems | 2025-09-18 | 2025-10-06 | 2025-10-10 | Completed | 100% | 29700 | 33466.36 | 2 | 4 | 0 | -3766.36
TSK-0737 | PRJ-1017 | Finance Vendor Transition 17 | Finance | Vendor Transition | Cameron Diaz | Testing | Testing Task 25 | Low | Medium | Internal Team | 2025-02-23 | 2025-03-19 | 2025-03-26 | Completed | 100% | 14400 | 13070.55 | 2 | 7 | 0 | 1329.45
TSK-0738 | PRJ-1018 | Human Resources System Implementation 18 | Human Resources | System Implementation | Riley Chen | Training | Training Task 25 | Low | Low | Internal Team | 2025-02-14 | 2025-03-03 | 2025-03-06 | Completed | 100% | 26200 | 26677.05 | 2 | 3 | 0 | -477.05
TSK-0739 | PRJ-1019 | Facilities Cost Reduction 19 | Facilities | Cost Reduction | Avery Brooks | Launch | Launch Task 25 | Low | Low | Internal Team | 2025-06-20 | 2025-06-28 | 2025-07-01 | Completed | 100% | 19600 | 19444.49 | 1 | 3 | 0 | 155.51
TSK-0740 | PRJ-1020 | Marketing Automation 20 | Marketing | Automation | Jordan Lee | Closeout | Closeout Task 25 | High | Medium | Internal Team | 2025-07-03 | 2025-07-16 |  | On Hold | 20% | 10700 | 9933.94 | 5 |  | 0 | 766.06
TSK-0741 | PRJ-1021 | Procurement Process Improvement 21 | Procurement | Process Improvement | Morgan Patel | Discovery | Discovery Task 25 | Medium | Medium | Internal Team | 2025-05-09 | 2025-05-12 |  | In Progress | 25% | 9000 | 10506.04 | 0 |  | 0 | -1506.04
TSK-0742 | PRJ-1022 | Operations Facility Upgrade 22 | Operations | Facility Upgrade | Taylor Reed | Planning | Planning Task 25 | High | High | Northstar Consulting | 2026-01-23 | 2026-02-04 | 2026-02-08 | Completed | 100% | 43900 | 42340.11 | 4 | 4 | 0 | 1559.89
TSK-0743 | PRJ-1023 | Technology Compliance 23 | Technology | Compliance | Cameron Diaz | Requirements | Requirements Task 25 | High | Low | Internal Team | 2025-12-12 | 2025-12-19 |  | Not Started | 0% | 6400 | 0 | 2 |  | 0 | 6400
TSK-0744 | PRJ-1024 | Finance Vendor Transition 24 | Finance | Vendor Transition | Riley Chen | Configuration | Configuration Task 25 | High | Low | Northstar Consulting | 2025-03-21 | 2025-04-06 | 2025-04-13 | Completed | 100% | 5200 | 4750.72 | 1 | 7 | 0 | 449.28
TSK-0745 | PRJ-1025 | Human Resources System Implementation 25 | Human Resources | System Implementation | Avery Brooks | Execution | Execution Task 25 | Medium | Low | BluePeak Services | 2026-02-10 | 2026-02-28 | 2026-02-26 | Completed | 100% | 38900 | 37210.37 | 1 | 0 | 0 | 1689.63
TSK-0746 | PRJ-1026 | Facilities Cost Reduction 26 | Facilities | Cost Reduction | Jordan Lee | Testing | Testing Task 25 | Medium | Medium | Internal Team | 2025-04-19 | 2025-04-25 | 2025-04-23 | Completed | 100% | 38400 | 27706.39 | 2 | 0 | 0 | 10693.61
TSK-0747 | PRJ-1027 | Marketing Automation 27 | Marketing | Automation | Morgan Patel | Training | Training Task 25 | Medium | Low | Apex Solutions | 2026-05-11 | 2026-05-30 | 2026-05-23 | Completed | 100% | 28100 | 26194.67 | 0 | 0 | 0 | 1905.33
TSK-0748 | PRJ-1028 | Procurement Process Improvement 28 | Procurement | Process Improvement | Taylor Reed | Launch | Launch Task 25 | Medium | Medium | Apex Solutions | 2026-03-22 | 2026-04-12 |  | In Progress | 25% | 13200 | 11647.76 | 0 |  | 0 | 1552.24
TSK-0749 | PRJ-1029 | Operations Facility Upgrade 29 | Operations | Facility Upgrade | Cameron Diaz | Closeout | Closeout Task 25 | Low | Medium | Northstar Consulting | 2026-04-24 | 2026-05-19 |  | In Progress | 40% | 14000 | 14782.2 | 3 |  | 0 | -782.2
TSK-0750 | PRJ-1030 | Technology Compliance 30 | Technology | Compliance | Riley Chen | Planning | Planning Task 25 | Medium | Low | BluePeak Services | 2026-01-06 | 2026-01-28 | 2026-01-28 | Completed | 100% | 39900 | 35881.08 | 1 | 0 | 0 | 4018.92

## PM Task Workload
Count of Task ID | Column Labels
Row Labels | Completed | In Progress | Not Started | On Hold | Active Workload | Grand Total
Avery Brooks | 82 | 23 | 14 | 6 | 29 | 154
Cameron Diaz | 69 | 33 | 19 | 4 | 37 | 162
Jordan Lee | 89 | 19 | 12 | 5 | 24 | 149
Morgan Patel | 68 | 35 | 21 | 1 | 36 | 161
Riley Chen | 81 | 24 | 15 | 5 | 29 | 154
Taylor Reed | 67 | 32 | 19 | 7 | 39 | 164
Grand Total | 456 | 166 | 100 | 28 | 194 | 944

## Project Delays
Row Labels | Sum of Days Delayed
Facilities Cost Reduction 05 | 115
Cameron Diaz | 115
Technology Compliance 02 | 93
Jordan Lee | 93
Technology Compliance 30 | 92
Riley Chen | 92
Finance Vendor Transition 03 | 82
Morgan Patel | 82
Operations Facility Upgrade 08 | 65
Jordan Lee | 65
Facilities Cost Reduction 26 | 64
Jordan Lee | 64
Marketing Automation 06 | 63
Riley Chen | 63
Technology Compliance 09 | 62
Morgan Patel | 62
Operations Facility Upgrade 15 | 61
Morgan Patel | 61
Finance Vendor Transition 17 | 61
Cameron Diaz | 61
Procurement Process Improvement 28 | 60
Taylor Reed | 60
Operations Facility Upgrade 29 | 58
Cameron Diaz | 58
Human Resources System Implementation 04 | 55
Taylor Reed | 55
Technology Compliance 23 | 51
Cameron Diaz | 51
Procurement Process Improvement 07 | 51
Avery Brooks | 51
Finance Vendor Transition 24 | 48
Riley Chen | 48
Facilities Cost Reduction 12 | 46
Riley Chen | 46
Procurement Process Improvement 14 | 46
Jordan Lee | 46
Finance Vendor Transition 10 | 46
Taylor Reed | 46
Marketing Automation 27 | 45
Morgan Patel | 45
Human Resources System Implementation 25 | 40
Avery Brooks | 40
Marketing Automation 20 | 35
Jordan Lee | 35
Procurement Process Improvement 21 | 32
Morgan Patel | 32
Operations Facility Upgrade 01 | 31
Avery Brooks | 31
Facilities Cost Reduction 19 | 30
Avery Brooks | 30
Operations Facility Upgrade 22 | 24
Taylor Reed | 24
Human Resources System Implementation 18 | 23
Riley Chen | 23
Technology Compliance 16 | 20
Taylor Reed | 20
Marketing Automation 13 | 15
Avery Brooks | 15
Human Resources System Implementation 11 | 11
Cameron Diaz | 11
Grand Total | 1525

## PM Portfolio Summary
Row Labels | Sum of Days Delayed | Count of Task ID | Sum of Unique Project Flag
Avery Brooks | 167 | 125 | 5
Cameron Diaz | 296 | 125 | 5
Jordan Lee | 303 | 125 | 5
Morgan Patel | 282 | 125 | 5
Riley Chen | 272 | 125 | 5
Taylor Reed | 205 | 125 | 5
Grand Total | 1525 | 750 | 30

## Department Risk Analysis
Count of Task ID | Column Labels
Row Labels | High | Low | Medium | Grand Total
Facilities | 19 | 45 | 36 | 100
Finance | 18 | 52 | 30 | 100
Human Resources | 16 | 53 | 31 | 100
Marketing | 14 | 48 | 38 | 100
Operations | 14 | 64 | 47 | 125
Procurement | 17 | 48 | 35 | 100
Technology | 24 | 59 | 42 | 125
Grand Total | 122 | 369 | 259 | 750

## Project Issues & Delays
Row Labels | Sum of Issue Count | Sum of Days Delayed
Facilities Cost Reduction 05 | 40 | 115
Technology Compliance 02 | 49 | 93
Technology Compliance 30 | 40 | 92
Finance Vendor Transition 03 | 40 | 82
Operations Facility Upgrade 08 | 38 | 65
Facilities Cost Reduction 26 | 43 | 64
Marketing Automation 06 | 37 | 63
Technology Compliance 09 | 36 | 62
Operations Facility Upgrade 15 | 28 | 61
Finance Vendor Transition 17 | 33 | 61
Procurement Process Improvement 28 | 56 | 60
Operations Facility Upgrade 29 | 46 | 58
Human Resources System Implementation 04 | 56 | 55
Technology Compliance 23 | 55 | 51
Procurement Process Improvement 07 | 34 | 51
Finance Vendor Transition 24 | 47 | 48
Facilities Cost Reduction 12 | 49 | 46
Procurement Process Improvement 14 | 42 | 46
Finance Vendor Transition 10 | 41 | 46
Marketing Automation 27 | 47 | 45
Human Resources System Implementation 25 | 40 | 40
Marketing Automation 20 | 56 | 35
Procurement Process Improvement 21 | 48 | 32
Operations Facility Upgrade 01 | 39 | 31
Facilities Cost Reduction 19 | 52 | 30
Operations Facility Upgrade 22 | 51 | 24
Human Resources System Implementation 18 | 40 | 23
Technology Compliance 16 | 46 | 20
Marketing Automation 13 | 47 | 15
Human Resources System Implementation 11 | 47 | 11
Grand Total | 1323 | 1525

## Schedule & Budget Performance
Row Labels | Sum of Days Delayed | Sum of Budget Variance
Facilities Cost Reduction 05 | 115 | 74912.39
Facilities Cost Reduction 12 | 46 | 55432.14
Facilities Cost Reduction 19 | 30 | 72678.2
Facilities Cost Reduction 26 | 64 | 31782.12
Finance Vendor Transition 03 | 82 | 75744.07
Finance Vendor Transition 10 | 46 | 26623.6
Finance Vendor Transition 17 | 61 | 97677.46
Finance Vendor Transition 24 | 48 | 101529.83
Human Resources System Implementation 04 | 55 | 225384.27
Human Resources System Implementation 11 | 11 | 88118.17
Human Resources System Implementation 18 | 23 | 75505.59
Human Resources System Implementation 25 | 40 | 63954.84
Marketing Automation 06 | 63 | 35644.88
Marketing Automation 13 | 15 | 184483.97
Marketing Automation 20 | 35 | 144391.68
Marketing Automation 27 | 45 | 64888.28
Operations Facility Upgrade 01 | 31 | 106289.31
Operations Facility Upgrade 08 | 65 | 101489.37
Operations Facility Upgrade 15 | 61 | 137685.25
Operations Facility Upgrade 22 | 24 | 153716.96
Operations Facility Upgrade 29 | 58 | 85334.7
Procurement Process Improvement 07 | 51 | 157360.22
Procurement Process Improvement 14 | 46 | 98856.99
Procurement Process Improvement 21 | 32 | 86147.12
Procurement Process Improvement 28 | 60 | 33002.11
Technology Compliance 02 | 93 | 57239.82
Technology Compliance 09 | 62 | 149971.54
Technology Compliance 16 | 20 | 133160.03
Technology Compliance 23 | 51 | 39878.32
Technology Compliance 30 | 92 | 58738.15
Grand Total | 1525 | 2817621.38

## Department Budget Analysis
Row Labels | Sum of Budget Variance
Facilities | 234804.85
Facilities Cost Reduction 05 | 74912.39
Facilities Cost Reduction 12 | 55432.14
Facilities Cost Reduction 19 | 72678.2
Facilities Cost Reduction 26 | 31782.12
Finance | 301574.96
Finance Vendor Transition 03 | 75744.07
Finance Vendor Transition 10 | 26623.6
Finance Vendor Transition 17 | 97677.46
Finance Vendor Transition 24 | 101529.83
Human Resources | 452962.87
Human Resources System Implementation 04 | 225384.27
Human Resources System Implementation 11 | 88118.17
Human Resources System Implementation 18 | 75505.59
Human Resources System Implementation 25 | 63954.84
Marketing | 429408.81
Marketing Automation 06 | 35644.88
Marketing Automation 13 | 184483.97
Marketing Automation 20 | 144391.68
Marketing Automation 27 | 64888.28
Operations | 584515.59
Operations Facility Upgrade 01 | 106289.31
Operations Facility Upgrade 08 | 101489.37
Operations Facility Upgrade 15 | 137685.25
Operations Facility Upgrade 22 | 153716.96
Operations Facility Upgrade 29 | 85334.7
Procurement | 375366.44
Procurement Process Improvement 07 | 157360.22
Procurement Process Improvement 14 | 98856.99
Procurement Process Improvement 21 | 86147.12
Procurement Process Improvement 28 | 33002.11
Technology | 438987.86
Technology Compliance 02 | 57239.82
Technology Compliance 09 | 149971.54
Technology Compliance 16 | 133160.03
Technology Compliance 23 | 39878.32
Technology Compliance 30 | 58738.15
Grand Total | 2817621.38

## Department Performance Summary
Row Labels | Sum of Days Delayed | Sum of Budget Variance
Facilities | 255 | 234804.85
Finance | 237 | 301574.96
Human Resources | 129 | 452962.87
Marketing | 158 | 429408.81
Operations | 239 | 584515.59
Procurement | 189 | 375366.44
Technology | 318 | 438987.86
Grand Total | 1525 | 2817621.38

## PM Workload Backup
Count of Task ID | Column Labels
Row Labels | Completed | In Progress | Not Started | On Hold | Active Workload | Grand Total
Avery Brooks | 82 | 23 | 14 | 6 | 29 | 154
Cameron Diaz | 69 | 33 | 19 | 4 | 37 | 162
Jordan Lee | 89 | 19 | 12 | 5 | 24 | 149
Morgan Patel | 68 | 35 | 21 | 1 | 36 | 161
Riley Chen | 81 | 24 | 15 | 5 | 29 | 154
Taylor Reed | 67 | 32 | 19 | 7 | 39 | 164
Grand Total | 456 | 166 | 100 | 28 | 194 | 944